## Reference
Status With Honeywell | Document through WF Status | Status with Systra
Not Submitted from HNWL | Under SMO Review | Under Systra Review
Under CJV review | Approved with Comments | Rejected
Under Safety Review | Released to Systra | Approved with Comments
Under HNWL update due to CJV comments | Returned from SMO | Approved
Approved from CJV | On Hold | Not Submitted
Under HNWL update due to SYS comments
Under HNWL update due to safety comments
Under HNWL update due to SMO comments
Under HNWL update

## Conclusion
Transmittal/Status | Total No. of Documents (1st Batch) | Total submitted from HNWL | % of Total submitted from HNWL | Not Submitted from HNWL | % of Total Not submitted from HNWL | Under HNWL updated | Under CJV Review | Under Safety Review | Under SMO Review | Under Systra Review | Approved with Comments | % of Approved from SYS | Rejected | % of Rejected from SYS
ELV Detailed Design | 1067 | 803 | 75.26% | 264 | 24.74% | 138 | 34 | 5 | 23 | 201 | 424 | 52.8% | 50 | 6.227%
ICT Detailed Design | 435 | 369 | 84.83% | 66 | 15.17% | 72 | 0 | 9 | 53 | 98 | 210 | 35.63% | 16 | 4.336%
SDS | 14 | 14 | 100% | 0 | 0% | 0 | 0 | 0 | 0 | 2 | 11 | 78.57% | 2 | 14.29%
Installation Details | 11 | 8 | 72.73% | 3 | 27.27% | 1 | 0 | 0 | 0 | 1 | 6 | 12.5% | 0 | 0%
Technical Rooms | 232 | 215 | 92.67% | 17 | 7.328% | 68 | 44 | 0 | 20 | 28 | 54 | 25.12% | 1 | 0.4651%
Method of Statement | 14 | 9 | 64.29% | 5 | 35.71% | 0 | 0 | 0 | 0 | 1 | 6 | 66.67% | 2 | 22.22%
Factory Test Acceptance (FAT) | 15 | 13 | 86.67% | 2 | 13.33% | 1 | 1 | 0 | 0 | 2 | 9 | 69.23% | 0 | 0%
Factory Test Report | 15 | 8 | 53.33% | 7 | 46.67% | 0 | 0 | 0 | 0 | 0 | 8 | 100% | 0 | 0%
Wayside DD (ICT, ELV) | 17 | 0 | 0% | 17 | 100% | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
Total | 1820 | 1439 | 79.07% | 381 | 20.93% | 280 | 79 | 14 | 96 | 333 | 728 | 50.59% | 71 | 4.934%
Transmittal/Status | Under HNWL updated | Under CJV Review | Under Systra Review | Closed with Systra | Not Submitted
Provision Drawings | 2 | 0 | 11 | 5 | 3

## ICT DD (Stations)
Cutoff 03-09-2026
[7 empty] | Internal Review |  | SMO Review |  |  | Systra Review
No. | STATION NAME | Station Ref. | TEL Sub-Systems | Document Title | Document No. | Rev. | Status With Honeywell | Status Date | Document through WF Status | WF no. | Date | Status with Systra | Status Date | REASONS OF RETURN | Comment
1 | NEW CAPITAL | GLB02 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLB02-1200001 | B | Approved from CJV |  | Released to Systra | WF- 019781 | 2026-03-02 | Approved with Comments | 2026-02-03
2 | NEW CAPITAL | GLB02 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLB02-1200002 | B | Approved from CJV |  | Released to Systra | WF- 019781 | 2026-03-02 | Approved with Comments | 2026-02-03
3 | NEW CAPITAL | GLB02 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLB02-1200003 | B | Approved from CJV |  | Released to Systra | WF- 019781 | 2026-03-02 | Approved with Comments | 2026-02-03
4 | NEW CAPITAL | GLB02 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLB02-1200004 | A | Approved from CJV |  | Released to Systra | WF-019166 | 29/1/2026 | Approved with Comments | 2026-02-03
5 | NEW CAPITAL | GLB02 | WIFI | Railway WIFI System - Cable Schedule | HSR-SOA-DES-TELWIFIS-GLB02-1200004 | A | Approved from CJV |  | Released to Systra | WF-018775 | 2026-08-01 | Approved with Comments | 2026-04-02
6 | NEW CAPITAL | GLB02 | WIFI | Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLB02-1200002 | B | Approved from CJV |  | Released to Systra | WF-018778 | 2026-08-01 | Approved with Comments | 2026-04-02
7 | NEW CAPITAL | GLB02 | WIFI | WIFI System - Overall Architecture (SLD) | HSR-SOA-DRW-TELWIFI-GLB02-1200001 | C | Approved from CJV |  | Released to Systra | WF-018778 | 2026-08-01 | Approved with Comments | 2026-04-02
8 | NEW CAPITAL | GLB02 | WIFI | WIFI System - Equipment Layout – (Ground Floor) | HSR-SOA-DRW-TELWIFI-GLB02-1200002 | C | Approved from CJV |  | Released to Systra | WF-018778 | 2026-08-01 | Approved with Comments | 2026-04-02
9 | NEW CAPITAL | GLB02 | WIFI | WIFI System - Cable routing plan (Ground Floor) | HSR-SOA-DRW-TELWIFI-GLB02-1200003 | B | Approved from CJV |  | Released to Systra | WF-018778 | 2026-08-01 | Approved with Comments | 2026-04-02
10 | NEW CAPITAL | GLB02 | MSN | MSN SYSTEM-System Overall Architecture | HSR-SOA-DRW-TELMSN-GLB02-1200002 | A | Approved from CJV |  | Under SMO Review | WF-019157 |  |  |  |  | Pending on AFCl "Omnia"-SYE PSS/Network Approval"Ali Haidar"
11 | NEW CAPITAL | GLB02 | MSN | MSN SYSTEM-System Equipment Layout | HSR-SOA-DRW-TELMSN-GLB02-1200003 | A | Approved from CJV |  | Under SMO Review | WF-019157 |  |  |  |  | Pending on AFCl "Omnia"-SYE PSS/Network Approval"Ali Haidar"
12 | NEW CAPITAL | GLB02 | MSN | MSN SYSTEM-System Cable routing plan | HSR-SOA-DRW-TELMSN-GLB02-1200001 | A | Approved from CJV |  | Under SMO Review | WF-019157 |  |  |  |  | Pending on AFCl "Omnia"-SYE PSS/Network Approval"Ali Haidar"
13 | MOHAMED NAGUIB | GLB03 | WIFI | Railway WIFI System - Cable Schedule Mohamed Naguib Station | HSR-SOA-DES-TELWIFI-GLB03-1200004 | A | Approved from CJV |  | Released to Systra | WF-018501 | 2026-08-01 | Approved with Comments
14 | MOHAMED NAGUIB | GLB03 | WIFI | Wi-Fi – Heat Map Specifications - Mohamed Naguib Station | HSR-SOA-DES-TELWIFI-GLB03-1200002 | B | Approved from CJV |  | Released to Systra | WF-018503 | 2026-08-01 | Approved with Comments
15 | MOHAMED NAGUIB | GLB03 | WIFI | WIFI System - Overall Architecture (SLD) - Mohamed Naguib Station | HSR-SOA-DRW-TELWIFI-GLB03-1200001 | C | Approved from CJV |  | Released to Systra | WF-018503 | 2026-08-01 | Approved with Comments
16 | MOHAMED NAGUIB | GLB03 | WIFI | WIFI System - Equipment Layout – (Ground Floor) - Mohamed Naguib Station | HSR-SOA-DRW-TELWIFI-GLB03-1200002 | C | Approved from CJV |  | Released to Systra | WF-018503 | 2026-08-01 | Approved with Comments
17 | MOHAMED NAGUIB | GLB03 | WIFI | WIFI System - Cable routing plan (Ground Floor) - Mohamed Naguib Station | HSR-SOA-DRW-TELWIFI-GLB03-1200003 | B | Approved from CJV |  | Released to Systra | WF-018503 | 2026-08-01 | Approved with Comments
18 | MOHAMED NAGUIB | GLB03 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLB03-1200001 | B | Approved from CJV |  | Released to Systra | WF-018619 | 14/1/2026 | Approved with Comments
19 | MOHAMED NAGUIB | GLB03 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLB03-1200002 | B | Approved from CJV |  | Released to Systra | WF-018619 | 14/1/2026 | Approved with Comments
20 | MOHAMED NAGUIB | GLB03 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLB03-1200003 | B | Approved from CJV |  | Released to Systra | WF-018619 | 14/1/2026 | Approved with Comments
21 | MOHAMED NAGUIB | GLB03 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLB03-1200004 | A | Approved from CJV |  | Released to Systra | WF-018616 | 23/1/2026 | Approved with Comments
22 | MOHAMED NAGUIB | GLB03 | MSN | MSN SYSTEM-System Overall Architecture | HSR-SOA-DRW-TELMSN-GLB03-1200001 | A | Under HNWL update | [7 empty] | Pending due to despute MSN points
23 | MOHAMED NAGUIB | GLB03 | MSN | MSN SYSTEM-System Equipment Layout | HSR-SOA-DRW-TELMSN-GLB03-1200002 | A | Under HNWL update | [7 empty] | Pending due to despute MSN points
24 | MOHAMED NAGUIB | GLB03 | MSN | MSN SYSTEM-System Cable routing plan | HSR-SOA-DRW-TELMSN-GLB03-1200003 | A | Under HNWL update | [7 empty] | Pending due to despute MSN points
25 | ALAMIAN | GLH15 | WIFI | Railway Wi-Fi – Heat Map Specifications _ Al Alameen Station | HSR-SOA-DES-TELWIFI-GLH15-1200002 | B | Approved from CJV |  | Released to Systra | WF-018496 | 2026-08-01 | Approved with Comments
26 | ALAMIAN | GLH15 | WIFI | WIFI System - Overall Architecture (SLD) _ Al Alameen Station | HSR-SOA-DRW-TELWIFI-GLH15-1200001 | B | Approved from CJV |  | Released to Systra | WF-018496 | 2026-08-01 | Approved with Comments
27 | ALAMIAN | GLH15 | WIFI | WIFI System - Equipment Layout - (Ground Floor) _ Al Alameen Station | HSR-SOA-DRW-TELWIFI-GLH15-1200002 | B | Approved from CJV |  | Released to Systra | WF-018496 | 2026-08-01 | Approved with Comments
28 | ALAMIAN | GLH15 | WIFI | WIFI System - Cable routing plan - (Ground Floor) _ Al Alameen Station | HSR-SOA-DRW-TELWIFI-GLH15-1200003 | B | Approved from CJV |  | Released to Systra | WF-018496 | 2026-08-01 | Approved with Comments
29 | ALAMIAN | GLH15 | WIFI | Railway WIFI System- Cable Schedule | HSR-SOA-DES-TELWIFI-GLH15-1200004 | A | Approved from CJV |  | Released to Systra | WF-018495 | 2026-08-01 | Approved with Comments
30 | ALAMIAN | GLH15 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLH15-1200001 | A | Approved from CJV |  | Released to Systra | WF-018647 | 14/1/2026 | Approved with Comments
31 | ALAMIAN | GLH15 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLH15-1200002 | A | Approved from CJV |  | Released to Systra | WF-018647 | 14/1/2026 | Approved with Comments
32 | ALAMIAN | GLH15 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLH15-1200003 | A | Approved from CJV |  | Released to Systra | WF-018647 | 14/1/2026 | Approved with Comments
33 | ALAMIAN | GLH15 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLH15-1200004 | A | Approved from CJV |  | Released to Systra | WF-018646 | 23/1/2026 | Approved with Comments
34 | ALAMIAN | GLH15 | MSN | MSN SYSTEM-System Overall Architecture | HSR-SOA-DRW-TELMSN-GLH15-1200001 | A | Under HNWL update | [7 empty] | Pending due to despute MSN points
35 | ALAMIAN | GLH15 | MSN | MSN SYSTEM-System Equipment Layout | HSR-SOA-DRW-TELMSN-GLH15-1200002 | A | Under HNWL update | [7 empty] | Pending due to despute MSN points
36 | ALAMIAN | GLH15 | MSN | MSN SYSTEM-System Cable routing plan | HSR-SOA-DRW-TELMSN-GLH15-1200003 | A | Under HNWL update | [7 empty] | Pending due to despute MSN points
37 | RAS ELHEKMA | GLM19 | WIFI | System Overall Architecture | HSR-SOA-DRW-TELWIFI-GLM19-1200001 | B | Approved from CJV |  | Released to Systra | WF-019462 |  | Approved with Comments
38 | RAS ELHEKMA | GLM19 | WIFI | System Equipment Layout | HSR-SOA-DRW-TELWIFI-GLM19-1200002 | B | Approved from CJV |  | Released to Systra | WF-019462 |  | Approved with Comments
39 | RAS ELHEKMA | GLM19 | WIFI | System Cable routing plan | HSR-SOA-DRW-TELWIFI-GLM19-1200003 | B | Approved from CJV |  | Released to Systra | WF-019462 |  | Approved with Comments
40 | RAS ELHEKMA | GLM19 | WIFI | Railway Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLM19-1200002 | B | Approved from CJV |  | Released to Systra | WF-019462 |  | Approved with Comments
41 | RAS ELHEKMA | GLM19 | WIFI | Cable Shedule | HSR-SOA-DES-TELWIFI-GLM19-1200004 | A | Approved from CJV |  | Released to Systra | WF-019340 |  | Approved with Comments
42 | RAS ELHEKMA | GLM19 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLM19-1200001 | B | Approved from CJV |  | Released to Systra | WF-019823 | 2026-03-02 | Approved with Comments | 2026-04-03
43 | RAS ELHEKMA | GLM19 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLM19-1200002 | B | Approved from CJV |  | Released to Systra | WF-019823 | 2026-03-02 | Approved with Comments | 2026-04-03
44 | RAS ELHEKMA | GLM19 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLM19-1200003 | B | Approved from CJV |  | Released to Systra | WF-019823 | 2026-03-02 | Approved with Comments | 2026-04-03
45 | RAS ELHEKMA | GLM19 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLM19-1200004 | A | Approved from CJV |  | Released to Systra | WF-019540 | 2026-01-02 | Approved with Comments | 2026-04-03
46 | RAS ELHEKMA | GLM19 | MSN | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMSN-GLM19-1200001 | A | Under HNWL update |  | Under SMO Review | WF- 019801 |  |  |  |  | Pending due to despute MSN points
47 | RAS ELHEKMA | GLM19 | MSN | System Equipment Layout | HSR-SOA-DRW-TELMSN-GLM19-1200002 | A | Under HNWL update |  | Under SMO Review | WF- 019801 |  |  |  |  | Pending due to despute MSN points
48 | RAS ELHEKMA | GLM19 | MSN | System Cable routing plan | HSR-SOA-DRW-TELMSN-GLM19-1200003 | A | Under HNWL update |  | Under SMO Review | WF- 019801 |  |  |  |  | Pending due to despute MSN points
49 | WADI NATROUN | GLE10 | WIFI | System Overall Architecture | HSR-SOA-DRW-TELWIFI-GLE10-1200001 | A | Approved from CJV |  | Released to Systra | WF- 019614 | 2026-03-02 | Approved with Comments | 2026-03-02
50 | WADI NATROUN | GLE10 | WIFI | System Equipment Layout | HSR-SOA-DRW-TELWIFI-GLE10-1200002 | A | Approved from CJV |  | Released to Systra | WF- 019614 | 2026-03-02 | Approved with Comments | 2026-03-02
51 | WADI NATROUN | GLE10 | WIFI | System Cable routing plan | HSR-SOA-DRW-TELWIFI-GLE10-1200003 | A | Approved from CJV |  | Released to Systra | WF- 019614 | 2026-03-02 | Approved with Comments | 2026-03-02
52 | WADI NATROUN | GLE10 | WIFI | Railway Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLE10-1200002 | A | Approved from CJV |  | Released to Systra | WF- 019614 | 2026-03-02 | Approved with Comments | 2026-03-02
53 | WADI NATROUN | GLE10 | WIFI | Cable Shedule | HSR-SOA-DES-TELWIFI-GLE10-1200004 | A | Approved from CJV |  | Released to Systra | WF-019597 | 29/1/2026 | Approved with Comments | 29/1/2026
54 | WADI NATROUN | GLE10 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLE10-1200001 | A | Approved from CJV |  | Released to Systra | WF-018884 | 14/1/2026 | Approved with Comments | 23-2-2026
55 | WADI NATROUN | GLE10 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLE10-1200002 | A | Approved from CJV |  | Released to Systra | WF-018884 | 14/1/2026 | Approved with Comments | 23-2-2026
56 | WADI NATROUN | GLE10 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLE10-1200003 | A | Approved from CJV |  | Released to Systra | WF-018884 | 14/1/2026 | Approved with Comments | 23-2-2026
57 | WADI NATROUN | GLE10 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLE10-1200004 | A | Approved from CJV |  | Released to Systra | WF-018883 | 23/1/2026 | Approved with Comments | 23-2-2026
58 | WADI NATROUN | GLE10 | MSN | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMSN-GLE10-1200001 | A | Under HNWL update | [7 empty] | Pending on AFCl "Omnia"-SYE PSS/Network Approval"Ali Haidar"
59 | WADI NATROUN | GLE10 | MSN | System Equipment Layout | HSR-SOA-DRW-TELMSN-GLE10-1200002 | A | Under HNWL update | [7 empty] | Pending on AFCl "Omnia"-SYE PSS/Network Approval"Ali Haidar"
60 | WADI NATROUN | GLE10 | MSN | System Cable routing plan | HSR-SOA-DRW-TELMSN-GLE10-1200003 | A | Under HNWL update | [7 empty] | Pending on AFCl "Omnia"-SYE PSS/Network Approval"Ali Haidar"
61 | OCTOBER GARDEN | GLC06 | WIFI | Railway WIFI System - Cable Schedule | HSR-SOA-DES-TELWIFI-GLC06-1200004 | A | Approved from CJV |  | Released to Systra | WF-018886 |  | Approved with Comments
62 | OCTOBER GARDEN | GLC06 | WIFI | Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLC06-1200005 | A | Approved from CJV |  | Released to Systra | WF-018887 | 15/1/2026 | Approved with Comments
63 | OCTOBER GARDEN | GLC06 | WIFI | WIFI System - Overall Architecture (SLD) | HSR-SOA-DRW-TELWIFI-GLC06-1200001 | B | Approved from CJV |  | Released to Systra | WF-018887 | 15/1/2026 | Approved with Comments
64 | OCTOBER GARDEN | GLC06 | WIFI | WIFI System - Equipment Layout – (Ground Floor | HSR-SOA-DRW-TELWIFI-GLC06-1200002 | B | Approved from CJV |  | Released to Systra | WF-018887 | 15/1/2026 | Approved with Comments
65 | OCTOBER GARDEN | GLC06 | WIFI | WIFI System - Cable routing plan (Ground Floor) | HSR-SOA-DRW-TELWIFI-GLC06-1200003 | A | Approved from CJV |  | Released to Systra | WF-018887 | 15/1/2026 | Approved with Comments
66 | OCTOBER GARDEN | GLC06 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLC06-1200001 | A | Approved from CJV |  | Released to Systra | WF-019161 | 29/1/2026 | Approved with Comments | 2026-02-03
67 | OCTOBER GARDEN | GLC06 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLC06-1200002 | A | Approved from CJV |  | Released to Systra | WF-019161 | 29/1/2026 | Approved with Comments | 2026-02-03
68 | OCTOBER GARDEN | GLC06 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLC06-1200003 | A | Approved from CJV |  | Released to Systra | WF-019161 | 29/1/2026 | Approved with Comments | 2026-02-03
69 | OCTOBER GARDEN | GLC06 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLC06-1200004 | A | Approved from CJV |  | Released to Systra | WF-019159 | 28/1/2026 | Approved with Comments | 2026-02-03
70 | OCTOBER GARDEN | GLC06 | MSN | MSN SYSTEM-System Overall Architecture | HSR-SOA-DRW-TELMSN-GLC06-1200001 | A | Under HNWL update | [5 empty] | 17/2/2026 | 17/2/2027
71 | OCTOBER GARDEN | GLC06 | MSN | MSN SYSTEM-System Equipment Layout | HSR-SOA-DRW-TELMSN-GLC06-1200002 | A | Under HNWL update | [5 empty] | 17/2/2026
72 | OCTOBER GARDEN | GLC06 | MSN | MSN SYSTEM-System Cable routing plan | HSR-SOA-DRW-TELMSN-GLC06-1200003 | A | Under HNWL update | [5 empty] | 17/2/2026
73 | CAIRO | GLB04 | WIFI | System Overall Architecture | HSR-SOA-DRW-TELWIFI-GLB04-1200001 | C | Approved from CJV |  | Released to Systra | WF-019762 | 2026-03-02 | Approved with Comments | 2026-03-02
74 | CAIRO | GLB04 | WIFI | System Equipment Layout | HSR-SOA-DRW-TELWIFI-GLB04-1200002 | C | Approved from CJV |  | Released to Systra | WF-019762 | 2026-03-02 | Approved with Comments | 2026-03-02
75 | CAIRO | GLB04 | WIFI | System Cable routing plan | HSR-SOA-DRW-TELWIFI-GLB04-1200003 | B | Approved from CJV |  | Released to Systra | WF-019762 | 2026-03-02 | Approved with Comments | 2026-03-02
76 | CAIRO | GLB04 | WIFI | Railway Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLB04-1200002 | B | Approved from CJV |  | Released to Systra | WF-019762 | 2026-03-02 | Approved with Comments | 2026-03-02
77 | CAIRO | GLB04 | WIFI | Cable Shedule | HSR-SOA-DES-TELWIFI-GLB04-1200004 | A | Approved from CJV |  | Released to Systra | WF-019464 | 2026-01-02 | Approved with Comments | 2026-01-02
78 | CAIRO | GLB04 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLB04-1200001 | B | Approved from CJV |  | Released to Systra | WF-019465 | 2026-01-02 | Approved with Comments | 2026-02-03 | 2026-02-04
79 | CAIRO | GLB04 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLB04-1200002 | B | Approved from CJV |  | Released to Systra | WF-019465 | 2026-01-02 | Approved with Comments | 2026-02-03
80 | CAIRO | GLB04 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLB04-1200003 | B | Approved from CJV |  | Released to Systra | WF-019465 | 2026-01-02 | Approved with Comments | 2026-02-03
81 | CAIRO | GLB04 | OATS | Cable Shedule | HSR-SYS-RCS-SOA-GL-001940 | A | Approved from CJV |  | Released to Systra | WF-019466 | 2026-01-02 | Approved with Comments | 2026-02-03
82 | CAIRO | GLB04 | MSN | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMSN-GLB04-1200001 | A | Under HNWL update |  | Under SMO Review | WF-015549 |  |  |  |  | Originator finalization and Closing justification
83 | CAIRO | GLB04 | MSN | System Equipment Layout | HSR-SOA-DRW-TELMSN-GLB04-1200002 | A | Under HNWL update |  | Under SMO Review | WF-015549 |  |  |  |  | Originator finalization and Closing justification
84 | CAIRO | GLB04 | MSN | System Cable routing plan | HSR-SOA-DRW-TELMSN-GLB04-1200003 | A | Under HNWL update |  | Under SMO Review | WF-015549 |  |  |  |  | Originator finalization and Closing justification
85 | GIZA | GLB05 | WIFI | System Overall Architecture | HSR-SOA-DRW-TELWIFI-GLB05-1200001 | A | Approved from CJV |  | Released to Systra | WF-019341 | 28/1/2026 | Approved with comments | 2026-12-02 | 2026-12-03
86 | GIZA | GLB05 | WIFI | System Equipment Layout | HSR-SOA-DRW-TELWIFI-GLB05-1200002 | A | Approved from CJV |  | Released to Systra | WF-019341 | 28/1/2026 | Approved with comments | 2026-12-02
87 | GIZA | GLB05 | WIFI | System Cable routing plan | HSR-SOA-DRW-TELWIFI-GLB05-1200003 | A | Approved from CJV |  | Released to Systra | WF-019341 | 28/1/2026 | Approved with comments | 2026-12-02
88 | GIZA | GLB05 | WIFI | Railway Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLB05-1200002 | A | Approved from CJV |  | Released to Systra | WF-019341 | 28/1/2026 | Approved with comments | 2026-12-02
89 | GIZA | GLB05 | WIFI | Cable Shedule | HSR-SOA-DES-TELWIFI-GLB05-1200004 | A | Approved from CJV |  | Released to Systra | WF-019342 | 29/1/2026 | Approved with comments | 2026-12-02
90 | GIZA | GLB05 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLB05-1200001 | A | Approved from CJV |  | Released to Systra | WF-019478 | 2026-01-02 | Approved with comments | 2026-04-03
91 | GIZA | GLB05 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLB05-1200002 | A | Approved from CJV |  | Released to Systra | WF-019478 | 2026-01-02 | Approved with comments | 2026-04-03
92 | GIZA | GLB05 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLB05-1200003 | A | Approved from CJV |  | Released to Systra | WF-019478 | 2026-01-02 | Approved with comments | 2026-04-03
93 | GIZA | GLB05 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLB05-1200004 | A | Approved from CJV |  | Released to Systra | WF-019472 | 2026-01-02 | Approved with comments | 2026-04-03
94 | GIZA | GLB05 | MSN | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMSN-GLB05-1200001 | A | Under HNWL update | [7 empty] | Pending due to despute MSN points
95 | GIZA | GLB05 | MSN | System Equipment Layout | HSR-SOA-DRW-TELMSN-GLB05-1200002 | A | Under HNWL update | [7 empty] | Pending due to despute MSN points
96 | GIZA | GLB05 | MSN | System Cable routing plan | HSR-SOA-DRW-TELMSN-GLB05-1200003 | A | Under HNWL update | [7 empty] | Pending due to despute MSN points
97 | SIDI ABDELRAHMAN | GLI16 | WIFI | System Overall Architecture | HSR-SOA-DRW-TELWIFI-GLI16-1200001 | B | Approved from CJV |  | Released to Systra | WF-019734 | 2026-03-02 | Approved with comments | 15/2/2026
98 | SIDI ABDELRAHMAN | GLI16 | WIFI | System Equipment Layout | HSR-SOA-DRW-TELWIFI-GLI16-1200002 | B | Approved from CJV |  | Released to Systra | WF-019734 | 2026-03-02 | Approved with comments | 15/2/2026
99 | SIDI ABDELRAHMAN | GLI16 | WIFI | System Cable routing plan | HSR-SOA-DRW-TELWIFI-GLI16-1200003 | B | Approved from CJV |  | Released to Systra | WF-019734 | 2026-03-02 | Approved with comments | 15/2/2026
100 | SIDI ABDELRAHMAN | GLI16 | WIFI | Railway Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLI16-1200002 | B | Approved from CJV |  | Released to Systra | WF-019734 | 2026-03-02 | Approved with comments | 15/2/2026
101 | SIDI ABDELRAHMAN | GLI16 | WIFI | Cable Shedule | HSR-SOA-DES-TELWIFI-GLI16-1200004 | A | Approved from CJV |  | Released to Systra | WF-019733 | 2026-03-02 | Approved with comments | 15/2/2026
102 | SIDI ABDELRAHMAN | GLI16 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLI16-1200002 | A | Approved from CJV |  | Released to Systra | WF-019654 | 2026-03-02 | Approved with comments | 2026-09-03
103 | SIDI ABDELRAHMAN | GLI16 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLI16-1200003 | A | Approved from CJV |  | Released to Systra | WF-019654 | 2026-03-02 | Approved with comments | 2026-09-03
104 | SIDI ABDELRAHMAN | GLI16 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLI16-1200001 | A | Approved from CJV |  | Released to Systra | WF-019654 | 2026-03-02 | Approved with comments | 2026-09-03
105 | SIDI ABDELRAHMAN | GLI16 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLI16-1200004 | A | Approved from CJV |  | Released to Systra | WF-019655 | 2026-04-02 | Approved with comments | 2026-09-03
106 | SIDI ABDELRAHMAN | GLI16 | MSN | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMSN-GLI16-1200001 | A | Under HNWL update |  | Under SMO Review | WF- 020014 |  |  |  |  | Pending due to despute MSN points
107 | SIDI ABDELRAHMAN | GLI16 | MSN | System Equipment Layout | HSR-SOA-DRW-TELMSN-GLI16-1200002 | A | Under HNWL update |  | Under SMO Review | WF- 020014 |  |  |  |  | Pending due to despute MSN points
108 | SIDI ABDELRAHMAN | GLI16 | MSN | System Cable routing plan | HSR-SOA-DRW-TELMSN-GLI16-1200003 | A | Under HNWL update |  | Under SMO Review | WF- 020014 |  |  |  |  | Pending due to despute MSN points
109 | EL NOUBARYA | GLF11 | WIFI | System Overall Architecture | HSR-SOA-DRW-TELWIFI-GLF11-1200001 | B | Approved from CJV |  | Released to Systra | WF-019507 | 28/1/2026 | Approved with comments | 28/1/2026
110 | EL NOUBARYA | GLF11 | WIFI | System Equipment Layout | HSR-SOA-DRW-TELWIFI-GLF11-1200002 | B | Approved from CJV |  | Released to Systra | WF-019507 | 28/1/2026 | Approved with comments | 28/1/2026
111 | EL NOUBARYA | GLF11 | WIFI | System Cable routing plan | HSR-SOA-DRW-TELWIFI-GLF11-1200003 | B | Approved from CJV |  | Released to Systra | WF-019507 | 28/1/2026 | Approved with comments | 28/1/2026
112 | EL NOUBARYA | GLF11 | WIFI | Railway Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLF11-1200002 | B | Approved from CJV |  | Released to Systra | WF-019833 | 414978 | Approved with comments | 414978
113 | EL NOUBARYA | GLF11 | WIFI | Cable Shedule | HSR-SOA-DES-TELWIFI-GLB05-1200004 | A | Approved from CJV |  | Released to Systra | WF-019508 | 28/1/2026 | Approved with comments | 28/1/2026
114 | EL NOUBARYA | GLF11 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLF11-1200001 | A | Approved from CJV |  | Released to Systra | WF-019825 | 2026-04-02 | Approved with comments | 2026-04-03 | 2026-04-04
115 | EL NOUBARYA | GLF11 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLF11-1200002 | A | Approved from CJV |  | Released to Systra | WF-019825 | 2026-04-02 | Approved with comments | 2026-04-03
116 | EL NOUBARYA | GLF11 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLF11-1200003 | A | Approved from CJV |  | Released to Systra | WF-019825 | 2026-04-02 | Approved with comments | 2026-04-03
117 | EL NOUBARYA | GLF11 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLF11-1200004 | A | Approved from CJV |  | Released to Systra | WF-019510 | 2026-01-02 | Approved with comments | 2026-04-03
118 | EL NOUBARYA | GLF11 | MSN | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMSN-GLF11-1200001 | A | Under HNWL update |  | Under SMO Review | WF-019706 |  |  |  |  | Pending due to despute MSN points
119 | EL NOUBARYA | GLF11 | MSN | System Equipment Layout | HSR-SOA-DRW-TELMSN-GLF11-1200002 | A | Under HNWL update |  | Under SMO Review | WF-019706 |  |  |  |  | Pending due to despute MSN points
120 | EL NOUBARYA | GLF11 | MSN | System Cable routing plan | HSR-SOA-DRW-TELMSN-GLF11-1200003 | A | Under HNWL update |  | Under SMO Review | WF-019706 |  |  |  |  | Pending due to despute MSN points
121 | EL SADAT | GLE09 | WIFI | System Overall Architecture | HSR-SOA-DRW-TELWIFI-GLE09-1200001 | A | Approved from CJV |  | Released to Systra | WF-020005 |  | Approved with comments | 18-3-2026
122 | EL SADAT | GLE09 | WIFI | System Equipment Layout | HSR-SOA-DRW-TELWIFI-GLE09-1200002 | A | Approved from CJV |  | Released to Systra | WF-020005 |  | Approved with comments | 18-3-2026
123 | EL SADAT | GLE09 | WIFI | System Cable routing plan | HSR-SOA-DRW-TELWIFI-GLE09-1200003 | A | Approved from CJV |  | Released to Systra | WF-020005 |  | Approved with comments | 18-3-2026
124 | EL SADAT | GLE09 | WIFI | Railway Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLE09-1200002 | A | Approved from CJV |  | Released to Systra | WF-020005 |  | Approved with comments | 18-3-2026
125 | EL SADAT | GLE09 | WIFI | Cable Shedule | HSR-SOA-DES-TELWIFI-GLE09-1200004 | A | Approved from CJV |  | Released to Systra | WF-020006 |  | Approved with comments | 18-3-2026
126 | EL SADAT | GLE09 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLE09-1200001 | A | Approved from CJV |  | Released to Systra | WF- 020007 |  | Approved with comments | 18-3-2026
127 | EL SADAT | GLE09 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLE09-1200002 | A | Approved from CJV |  | Released to Systra | WF- 020007 |  | Approved with comments | 18-3-2026
128 | EL SADAT | GLE09 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLE09-1200003 | A | Approved from CJV |  | Released to Systra | WF- 020007 |  | Approved with comments | 18-3-2026
129 | EL SADAT | GLE09 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLE09-1200004 | A | Approved from CJV |  | Released to Systra | WF- 020009 |  | Approved with comments | 18-3-2026
130 | EL SADAT | GLE09 | MSN | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMSN-GLE09-1200001 | A | Approved from CJV |  | Under SMO Review | WF-020294 |  |  |  |  | Pending due to despute MSN points
131 | EL SADAT | GLE09 | MSN | System Equipment Layout | HSR-SOA-DRW-TELMSN-GLE09-1200002 | A | Under HNWL update |  | Under SMO Review | WF-020294 |  |  |  |  | Pending due to despute MSN points
132 | EL SADAT | GLE09 | MSN | System Cable routing plan | HSR-SOA-DRW-TELMSN-GLE09-1200002 | A | Under HNWL update |  | Under SMO Review | WF-020294 |  |  |  |  | Pending due to despute MSN points
133 | El Ain ElSOKHNA | GLA01 | WIFI | System Overall Architecture | HSR-SOA-DRW-TELWIFI-GLA01-1200001 | A | Under Safety Review
134 | El Ain ElSOKHNA | GLA01 | WIFI | System Equipment Layout | HSR-SOA-DRW-TELWIFI-GLA01-1200002 | A | Under Safety Review
135 | El Ain ElSOKHNA | GLA01 | WIFI | System Cable routing plan | HSR-SOA-DRW-TELWIFI-GLA01-1200003 | A | Under Safety Review
136 | El Ain ElSOKHNA | GLA01 | WIFI | Railway Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLA01-1200002 | A | Under Safety Review
137 | El Ain ElSOKHNA | GLA01 | WIFI | Cable Shedule | HSR-SOA-DES-TELWIFI-GLA01-1200004 | A | Under Safety Review
138 | El Ain ElSOKHNA | GLA01 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLA01-1200001 | A | Approved from CJV |  | Under SMO Review | WF-024574
139 | El Ain ElSOKHNA | GLA01 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLA01-1200002 | A | Approved from CJV |  | Under SMO Review | WF-024574
140 | El Ain ElSOKHNA | GLA01 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLA01-1200003 | A | Approved from CJV |  | Under SMO Review | WF-024574
141 | El Ain ElSOKHNA | GLA01 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLA01-1200004 | A | Approved from CJV |  | Under SMO Review | WF-024575
142 | El Ain ElSOKHNA | GLA01 | MSN | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMSN-GLA01-1200001 | A | Under HNWL update
143 | El Ain ElSOKHNA | GLA01 | MSN | System Equipment Layout | HSR-SOA-DRW-TELMSN-GLA01-1200002 | A | Under HNWL update
144 | El Ain ElSOKHNA | GLA01 | MSN | System Cable routing plan | HSR-SOA-DRW-TELMSN-GLA01-1200002 | A | Under HNWL update
145 | 6TH OF OCTOBER | GLD07 | WIFI | System Overall Architecture | HSR-SOA-DRW-TELWIFI-GLD07-1200001 | A | Approved from CJV |  | Released to Systra | WF-020382 |  | Approved with comments | 2026-06-02
146 | 6TH OF OCTOBER | GLD07 | WIFI | System Equipment Layout | HSR-SOA-DRW-TELWIFI-GLD07-1200002 | A | Approved from CJV |  | Released to Systra | WF-020382 |  | Approved with comments | 2026-06-03
147 | 6TH OF OCTOBER | GLD07 | WIFI | System Cable routing plan | HSR-SOA-DRW-TELWIFI-GLD07-1200003 | A | Approved from CJV |  | Released to Systra | WF-020382 |  | Approved with comments | 2026-06-04
148 | 6TH OF OCTOBER | GLD07 | WIFI | Railway Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLD07-1200002 | A | Approved from CJV |  | Released to Systra | WF-020382 |  | Approved with comments | 2026-06-05
149 | 6TH OF OCTOBER | GLD07 | WIFI | Cable Shedule | HSR-SOA-DES-TELWIFI-GLD07-1200004 | A | Approved from CJV |  | Released to Systra | WF-020383 |  | Approved with comments | 2026-06-06
150 | 6TH OF OCTOBER | GLD07 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLD07-1200001 | A | Approved from CJV |  | Released to Systra | WF-020316 |  | Rejected | 2026-05-05
151 | 6TH OF OCTOBER | GLD07 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLD07-1200002 | A | Approved from CJV |  | Released to Systra | WF-020316 |  | Rejected | 2026-05-05
152 | 6TH OF OCTOBER | GLD07 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLD07-1200003 | A | Approved from CJV |  | Released to Systra | WF-020316 |  | Rejected | 2026-05-05
153 | 6TH OF OCTOBER | GLD07 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLD07-1200004 | A | Approved from CJV |  | Released to Systra | WF-020317 |  | Rejected | 2026-05-05
154 | 6TH OF OCTOBER | GLD07 | MSN | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMSN-GLD07-1200001 | A | Under HNWL update | [5 empty] | 2026-03-11
155 | 6TH OF OCTOBER | GLD07 | MSN | System Equipment Layout | HSR-SOA-DRW-TELMSN-GLD07-1200002 | A | Under HNWL update | [5 empty] | 2026-03-11
156 | 6TH OF OCTOBER | GLD07 | MSN | System Cable routing plan | HSR-SOA-DRW-TELMSN-GLD07-1200002 | A | Under HNWL update | [5 empty] | 2026-03-11
157 | SPHINX | GLE08 | WIFI | System Overall Architecture | HSR-SOA-DRW-TELWIFI-GLE08-1200001 | B | Approved from CJV |  | Released to Systra | WF-020492 |  | Approved with comments | 2026-04-21
158 | SPHINX | GLE08 | WIFI | System Equipment Layout | HSR-SOA-DRW-TELWIFI-GLE08-1200002 | B | Approved from CJV |  | Released to Systra | WF-020492 |  | Approved with comments | 2026-04-21
159 | SPHINX | GLE08 | WIFI | System Cable routing plan | HSR-SOA-DRW-TELWIFI-GLE08-1200003 | B | Approved from CJV |  | Released to Systra | WF-020492 |  | Approved with comments | 2026-04-21
160 | SPHINX | GLE08 | WIFI | Railway Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLE08-1200002 | B | Approved from CJV |  | Released to Systra | WF-020492 |  | Approved with comments | 2026-04-21
161 | SPHINX | GLE08 | WIFI | Cable Shedule | HSR-SOA-DES-TELWIFI-GLE08-1200004 | A | Approved from CJV |  | Released to Systra | WF-020493 |  | Approved with comments | 2026-04-21
162 | SPHINX | GLE08 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLE08-1200001 | A | Approved from CJV |  | Released to Systra | WF-020336 |  | Approved with comments | 2026-04-15
163 | SPHINX | GLE08 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLE08-1200002 | A | Approved from CJV |  | Released to Systra | WF-020336 |  | Approved with comments | 2026-04-15
164 | SPHINX | GLE08 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLE08-1200003 | A | Approved from CJV |  | Released to Systra | WF-020336 |  | Approved with comments | 2026-04-15
165 | SPHINX | GLE08 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLE08-1200004 | A | Approved from CJV |  | Released to Systra | WF-020338 |  | Approved with comments | 2026-04-15
166 | SPHINX | GLE08 | MSN | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMSN-GLE08-1200001 | A | Under HNWL update |  | Under SMO Review | WF-020712
167 | SPHINX | GLE08 | MSN | System Equipment Layout | HSR-SOA-DRW-TELMSN-GLE08-1200002 | A | Under HNWL update |  | Under SMO Review | WF-020712
168 | SPHINX | GLE08 | MSN | System Cable routing plan | HSR-SOA-DRW-TELMSN-GLE08-1200002 | A | Under HNWL update |  | Under SMO Review | WF-020712
169 | ALEXANDRIA |  | WIFI | System Overall Architecture
170 | ALEXANDRIA |  | WIFI | System Equipment Layout
171 | ALEXANDRIA |  | WIFI | System Cable routing plan
172 | ALEXANDRIA |  | WIFI | Railway Wi-Fi – Heat Map Specifications
173 | ALEXANDRIA |  | WIFI | Cable Shedule
174 | ALEXANDRIA |  | OATS | System Overall Architecture
175 | ALEXANDRIA |  | OATS | System Equipment Layout
176 | ALEXANDRIA |  | OATS | System Cable routing plan
177 | ALEXANDRIA |  | OATS | Cable Shedule
178 | ALEXANDRIA |  | MSN | System Overall Architecture (SLD)
179 | ALEXANDRIA |  | MSN | System Equipment Layout
180 | ALEXANDRIA |  | MSN | System Cable routing plan
181 | BORG ELARAB | GLG13 | WIFI | System Overall Architecture | HSR-SOA-DRW-TELWIFI-GLG13-1200001 | A | Approved from CJV |  | Released to Systra | WF-020955 | 2026-07-03 | Approved with comments | 2026-06-02
182 | BORG ELARAB | GLG13 | WIFI | System Equipment Layout | HSR-SOA-DRW-TELWIFI-GLG13-1200002 | A | Approved from CJV |  | Released to Systra | WF-020955 | 2026-07-03 | Approved with comments | 2026-06-02
183 | BORG ELARAB | GLG13 | WIFI | System Cable routing plan | HSR-SOA-DRW-TELWIFI-GLG13-1200003 | A | Approved from CJV |  | Released to Systra | WF-020955 | 2026-07-03 | Approved with comments | 2026-06-02
184 | BORG ELARAB | GLG13 | WIFI | Railway Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLG13-1200002 | A | Approved from CJV |  | Released to Systra | WF-020955 | 2026-07-03 | Approved with comments | 2026-06-02
185 | BORG ELARAB | GLG13 | WIFI | Cable Shedule | HSR-SOA-DES-TELWIFI-GLG13-1200004 | A | Approved from CJV |  | Released to Systra | WF-020956 | 2026-07-03 | Approved with comments | 2026-06-02
186 | BORG ELARAB | GLG13 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLG13-1200001 | A | Approved from CJV |  | Released to Systra | WF-020957 | 2026-07-03 | Under Systra Review
187 | BORG ELARAB | GLG13 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLG13-1200002 | A | Approved from CJV |  | Released to Systra | WF-020957 | 2026-07-03 | Under Systra Review
188 | BORG ELARAB | GLG13 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLG13-1200003 | A | Approved from CJV |  | Released to Systra | WF-020957 | 2026-07-03 | Under Systra Review
189 | BORG ELARAB | GLG13 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLG13-1200004 | A | Approved from CJV |  | Released to Systra | WF-020958 | 2026-07-03 | Under Systra Review
190 | BORG ELARAB | GLG13 | MSN | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMSN-GLG13-1200001 | A | Under HNWL update
191 | BORG ELARAB | GLG13 | MSN | System Equipment Layout | HSR-SOA-DRW-TELMSN-GLG13-1200002 | A | Under HNWL update
192 | BORG ELARAB | GLG13 | MSN | System Cable routing plan | HSR-SOA-DRW-TELMSN-GLG13-1200003 | A | Under HNWL update
193 | EL HAMMAM | GLG14 | WIFI | System Overall Architecture | HSR-SOA-DRW-TELWIFI-GLG14-1200001 | A | Approved from CJV |  | Released to Systra | WF-021466 |  | Approved with comments | 2026-06-02
194 | EL HAMMAM | GLG14 | WIFI | System Equipment Layout | HSR-SOA-DRW-TELWIFI-GLG14-1200002 | A | Approved from CJV |  | Released to Systra | WF-021466 |  | Approved with comments | 2026-06-02
195 | EL HAMMAM | GLG14 | WIFI | System Cable routing plan | HSR-SOA-DRW-TELWIFI-GLG14-1200003 | A | Approved from CJV |  | Released to Systra | WF-021466 |  | Approved with comments | 2026-06-02
196 | EL HAMMAM | GLG14 | WIFI | Railway Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLG14-1200002 | A | Approved from CJV |  | Released to Systra | WF-021466 |  | Approved with comments | 2026-06-02
197 | EL HAMMAM | GLG14 | WIFI | Cable Shedule | HSR-SOA-DES-TELWIFI-GLG14-1200004 | A | Approved from CJV |  | Released to Systra | WF-021651 |  | Approved with comments | 2026-06-02
198 | EL HAMMAM | GLG14 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLG14-1200001 | A | Approved from CJV |  | Released to Systra | WF-021237 | 17/3/2026 | Approved with comments | 2026-06-08
199 | EL HAMMAM | GLG14 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLG14-1200002 | A | Approved from CJV |  | Released to Systra | WF-021237 | 17/3/2026 | Approved with comments | 2026-06-08
200 | EL HAMMAM | GLG14 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLG14-1200003 | A | Approved from CJV |  | Released to Systra | WF-021237 | 17/3/2026 | Approved with comments | 2026-06-08
201 | EL HAMMAM | GLG14 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLG14-1200004 | A | Approved from CJV |  | Released to Systra | WF-021238 | 17/3/2026 | Approved with comments | 2026-06-08
202 | EL HAMMAM | GLG14 | MSN | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMSN-GLG14-1200001 | A | Under HNWL update
203 | EL HAMMAM | GLG14 | MSN | System Equipment Layout | HSR-SOA-DRW-TELMSN-GLG14-1200002 | A | Under HNWL update
204 | EL HAMMAM | GLG14 | MSN | System Cable routing plan | HSR-SOA-DRW-TELMSN-GLG14-1200003 | A | Under HNWL update
205 | EL DABAA | GLI17 | WIFI | System Overall Architecture | HSR-SOA-DRW-TELWIFI-GLI17-1200001 | B | Approved from CJV |  | Released to Systra | WF-020703 | 19/3/2026 | Approved with comments | 2026-06-02
206 | EL DABAA | GLI17 | WIFI | System Equipment Layout | HSR-SOA-DRW-TELWIFI-GLI17-1200002 | B | Approved from CJV |  | Released to Systra | WF-020703 | 19/3/2026 | Approved with comments | 2026-06-02
207 | EL DABAA | GLI17 | WIFI | System Cable routing plan | HSR-SOA-DRW-TELWIFI-GLI17-1200003 | B | Approved from CJV |  | Released to Systra | WF-020703 | 19/3/2026 | Approved with comments | 2026-06-02
208 | EL DABAA | GLI17 | WIFI | Railway Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLI17-1200002 | B | Approved from CJV |  | Released to Systra | WF-020703 | 19/3/2026 | Approved with comments | 2026-06-02
209 | EL DABAA | GLI17 | WIFI | Cable Shedule | HSR-SOA-DES-TELWIFI-GLI17-1200004 | A | Approved from CJV |  | Released to Systra | WF-020704 | 19/3/2026 | Approved with comments | 2026-06-02
210 | EL DABAA | GLI17 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLI17-1200001 | A | Approved from CJV |  | Released to Systra | WF-020643 | 2026-09-03 | Approved with comments | 2026-05-14
211 | EL DABAA | GLI17 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLI17-1200002 | A | Approved from CJV |  | Released to Systra | WF-020643 | 2026-09-03 | Approved with comments | 2026-05-14
212 | EL DABAA | GLI17 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLI17-1200003 | A | Approved from CJV |  | Released to Systra | WF-020643 | 2026-09-03 | Approved with comments | 2026-05-14
213 | EL DABAA | GLI17 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLI17-1200004 | A | Approved from CJV |  | Released to Systra | WF-020645 | 2026-09-03 | Approved with comments | 2026-05-14
214 | EL DABAA | GLI17 | MSN | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMSN-GLI17-1200001 | A | Under HNWL update | 2026-03-02
215 | EL DABAA | GLI17 | MSN | System Equipment Layout | HSR-SOA-DRW-TELMSN-GLI17-1200002 | A | Under HNWL update | 2026-03-02
216 | EL DABAA | GLI17 | MSN | System Cable routing plan | HSR-SOA-DRW-TELMSN-GLI17-1200003 | A | Under HNWL update | 2026-03-02
217 | AlAMRIA |  | WIFI | System Overall Architecture
218 | AlAMRIA |  | WIFI | System Equipment Layout
219 | AlAMRIA |  | WIFI | System Cable routing plan
220 | AlAMRIA |  | WIFI | Railway Wi-Fi – Heat Map Specifications
221 | AlAMRIA |  | WIFI | Cable Shedule
222 | AlAMRIA |  | OATS | System Overall Architecture
223 | AlAMRIA |  | OATS | System Equipment Layout
224 | AlAMRIA |  | OATS | System Cable routing plan
225 | AlAMRIA |  | OATS | Cable Shedule
226 | AlAMRIA |  | MSN | System Overall Architecture (SLD)
227 | AlAMRIA |  | MSN | System Equipment Layout
228 | AlAMRIA |  | MSN | System Cable routing plan
241 | MARSA MATROUH | GLM21 | WIFI | System Overall Architecture | HSR-SOA-DRW-TELWIFI-GLM21-1200001 | A | Approved from CJV |  | Released to systra | WF-021463 | 20/4/2026 | Approved with Comments
242 | MARSA MATROUH | GLM21 | WIFI | System Equipment Layout | HSR-SOA-DRW-TELWIFI-GLM21-1200002 | A | Approved from CJV |  | Released to systra | WF-021463 | 20/4/2026 | Approved with Comments
243 | MARSA MATROUH | GLM21 | WIFI | System Cable routing plan | HSR-SOA-DRW-TELWIFI-GLM21-1200003 | A | Approved from CJV |  | Released to systra | WF-021463 | 20/4/2026 | Approved with Comments
244 | MARSA MATROUH | GLM21 | WIFI | Railway Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLM21-1200002 | A | Approved from CJV |  | Released to systra | WF-021463 | 20/4/2026 | Approved with Comments
245 | MARSA MATROUH | GLM21 | WIFI | Cable Shedule | HSR-SOA-DES-TELWIFI-GLM21-1200004 | A | Approved from CJV |  | Released to systra | WF-021650 | 22/4/2026 | Approved with Comments
246 | MARSA MATROUH | GLM21 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLM21-1200001 | A | Approved from CJV |  | Released to systra | WF-021358 | 20/4/2026 | Approved with Comments
247 | MARSA MATROUH | GLM21 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLM21-1200002 | A | Approved from CJV |  | Released to systra | WF-021358 | 20/4/2026 | Approved with Comments
248 | MARSA MATROUH | GLM21 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLM21-1200003 | A | Approved from CJV |  | Released to systra | WF-021358 | 20/4/2026 | Approved with Comments
249 | MARSA MATROUH | GLM21 | OATS | Cable Shedule | HSR-SOA-DES-TELACS-GLM21-1200002 | A | Approved from CJV |  | Released to systra | WF-021357 | 22/4/2026 | Approved with Comments
250 | MARSA MATROUH | GLM21 | MSN | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMSN-GLM21-1200001 | A | Under HNWL update
251 | MARSA MATROUH | GLM21 | MSN | System Equipment Layout | HSR-SOA-DRW-TELMSN-GLM21-1200002 | A | Under HNWL update
252 | MARSA MATROUH | GLM21 | MSN | System Cable routing plan | HSR-SOA-DRW-TELMSN-GLM21-1200003 | A | Under HNWL update
253 | Army Stadium | GLN12 | WIFI | System Overall Architecture | HSR-SOA-DRW-TELWIFI-GLN12-1200001 | A | Approved from CJV |  | Released to systra | WF-022297 | 2026-03-05 | Approved with comments | 2026-06-02
254 | Army Stadium | GLN12 | WIFI | System Equipment Layout | HSR-SOA-DRW-TELWIFI-GLN12-1200001 | A | Approved from CJV |  | Released to systra | WF-022297 | 2026-03-05 | Approved with comments | 2026-06-02
255 | Army Stadium | GLN12 | WIFI | System Cable routing plan | HSR-SOA-DRW-TELWIFI-GLN12-1200001 | A | Approved from CJV |  | Released to systra | WF-022297 | 2026-03-05 | Approved with comments | 2026-06-02
256 | Army Stadium | GLN12 | WIFI | Railway Wi-Fi – Heat Map Specifications | HSR-SOA-DES-TELWIFI-GLN12-1200001 | A | Approved from CJV |  | Released to systra | WF-022297 | 2026-03-05 | Approved with comments | 2026-06-02
257 | Army Stadium | GLN12 | WIFI | Cable Shedule | HSR-SOA-DES-TELWIFI-GLN12-1200003 | A | Approved from CJV |  | Released to systra | WF-022298 | 2026-03-05 | Approved with comments | 2026-06-02
258 | Army Stadium | GLN12 | OATS | System Overall Architecture | HSR-SOA-DRW-TELOATS-GLN12-1200001 | A | Approved from CJV |  | Released to systra | WF-021877 | 2026-06-05 | Approved with comments | 2026-06-02
259 | Army Stadium | GLN12 | OATS | System Equipment Layout | HSR-SOA-DRW-TELOATS-GLN12-1200001 | A | Approved from CJV |  | Released to systra | WF-021877 | 2026-06-05 | Approved with comments | 2026-06-02
260 | Army Stadium | GLN12 | OATS | System Cable routing plan | HSR-SOA-DRW-TELOATS-GLN12-1200001 | A | Approved from CJV |  | Released to systra | WF-021877 | 2026-06-05 | Approved with comments | 2026-06-02
261 | Army Stadium | GLN12 | OATS | Cable Shedule | HSR-SOA-DES-TELOATS-GLN12-1200003 | A | Approved from CJV |  | Released to systra | WF-021879 | 2026-06-05 | Approved with comments | 2026-06-02
262 | Army Stadium | GLN12 | MSN | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMSN-GLN12-1200001 | A | Under HNWL update
263 | Army Stadium | GLN12 | MSN | System Equipment Layout | HSR-SOA-DRW-TELMSN-GLN12-1200002 | A | Under HNWL update
264 | Army Stadium | GLN12 | MSN | System Cable routing plan | HSR-SOA-DRW-TELMSN-GLN12-1200003 | A | Under HNWL update
Documents Status
[16 empty] | Total Number of Documents | 252
[16 empty] | Total Number of submitted from HNWLdoumcnts | 228
[16 empty] | Total Number of not submitted from HNWL documents | 24
[16 empty] | Under HNWL update | 53
[16 empty] | Under CJV Review | 0
[16 empty] | Under Safety Review | 5
[16 empty] | Under SMO Review | 25
[16 empty] | Released to Systra | 162
[16 empty] | Under Systra Review | 4
[16 empty] | Approved with Comments | 154
[16 empty] | Rejected | 4

## ICT DD (Depot)
Cutoff Date 03-09-2026
[6 empty] | Internal Review |  | SMO Review |  |  | Systra Review
Building NAME | Building Ref. | TEL Sub-Systems | Document Title | Document No. | Rev. | Status With Honeywell | Status Date | Document through WF Status | WF no. | Date | Status with Systra | Status Date | REASONS OF RETURN | Comment
OCS - Main Switching HUB 1 |  | OATS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF- 019519 |  | Approved with Comments
OCS - Main Switching HUB 1 |  | OATS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF- 019519 |  | Approved with Comments
OCS - Main Switching HUB 1 |  | OATS | Cable Schedule |  | A | [5 empty] | Approved with Comments
OCS - Main Switching HUB 1 |  | OATS | Cable Routing |  | A | Approved from CJV |  | Released to Systra | WF- 019519 |  | Approved with Comments
OCS - Main Switching HUB 1 |  | MSN | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-021909 |  | Approved with Comments
OCS - Main Switching HUB 1 |  | MSN | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-021909 |  | Approved with Comments
OCS - Main Switching HUB 1 |  | MSN | System Cable routing plan |  | A | Approved from CJV |  | Released to Systra | WF-021909 |  | Approved with Comments
OCS Section Switching HUB 2 |  | OATS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-020666 |  | Approved with Comments
OCS Section Switching HUB 2 |  | OATS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-020666 |  | Approved with Comments
OCS Section Switching HUB 2 |  | OATS | Cable Schedule |  | A | Approved from CJV |  | Released to Systra | WF-019237 |  | Approved with Comments
OCS Section Switching HUB 2 |  | OATS | Cable Routing |  | A | Approved from CJV |  | Released to Systra | WF-020666 |  | Approved with Comments
OCS Section Switching HUB 2 |  | MSN | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-021916 |  | Approved with Comments
OCS Section Switching HUB 2 |  | MSN | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-021916 |  | Approved with Comments
OCS Section Switching HUB 2 |  | MSN | System Cable routing plan |  | A | Approved from CJV |  | Released to Systra | WF-021916 |  | Approved with Comments
MWB Building |  | OATS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-023548 |  | Approved with Comments
MWB Building |  | OATS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-023548 |  | Approved with Comments
MWB Building |  | OATS | Cable Schedule |  | A | Approved from CJV |  | Released to Systra | WF-023548 |  | Approved with Comments
MWB Building |  | OATS | Cable Routing |  | A | Approved from CJV |  | Released to Systra | WF-023549 |  | Approved with Comments
MWB Building |  | MSN | Equipment Layout Drawing |  | A | Approved from CJV |  | Under SMO review | WF-021922
MWB Building |  | MSN | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Under SMO review | WF-021922
MWB Building |  | MSN | System Cable routing plan |  | A | Approved from CJV |  | Under SMO review | WF-021922
WPMS Building |  | OATS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-020495 |  | Approved with Comments
WPMS Building |  | OATS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-020495 |  | Approved with Comments
WPMS Building |  | OATS | Cable Schedule |  | A | Approved from CJV |  | Released to Systra | WF-019188 |  | Approved with Comments
WPMS Building |  | OATS | Cable Routing |  | A | Approved from CJV |  | Released to Systra | WF-020495 |  | Approved with Comments
WPMS Building |  | MSN | Equipment Layout Drawing |  | A | Approved from CJV |  | Under SMO review | WF-021923
WPMS Building |  | MSN | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Under SMO review | WF-021923
WPMS Building |  | MSN | System Cable routing plan |  | A | Approved from CJV |  | Under SMO review | WF-021923
Stabling Yard 1 |  | Wifi | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-019485 |  | Approved with Comments
Stabling Yard 1 |  | Wifi | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-019485 |  | Approved with Comments
Stabling Yard 1 |  | Wifi | Cable Schedule |  | A | Approved from CJV |  | Released to Systra | WF-019482 |  | Approved with Comments
Stabling Yard 1 |  | Wifi | Cable Routing |  | A | Approved from CJV |  | Released to Systra | WF-019485 |  | Approved with Comments
Stabling Yard 1 |  | Wifi | WIFI Heatmap |  | A | Approved from CJV |  | Released to Systra | WF-019485 |  | Approved with Comments
Stabling Yard 1 |  | OATS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-023575 |  | Rejected
Stabling Yard 1 |  | OATS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-023575 |  | Rejected
Stabling Yard 1 |  | OATS | Cable Schedule |  | A | Approved from CJV |  | Released to Systra | WF-023575 |  | Rejected
Stabling Yard 1 |  | OATS | Cable Routing |  | A | Approved from CJV |  | Released to Systra | WF-023576 |  | Approved with Comments
Stabling Yard 1 |  | MSN | Equipment Layout Drawing |  | A | Approved from CJV |  | Under SMO review | WF-022108 |  | Approved with Comments
Stabling Yard 1 |  | MSN | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Under SMO review | WF-022108 |  | Approved with Comments
Stabling Yard 1 |  | MSN | System Cable routing plan |  | A | Approved from CJV |  | Under SMO review | WF-022108 |  | Approved with Comments
Stabling Yard 2 |  | Wifi | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-020773 |  | Approved with Comments
Stabling Yard 2 |  | Wifi | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-020773 |  | Approved with Comments
Stabling Yard 2 |  | Wifi | Cable Schedule |  | A | Approved from CJV |  | Released to Systra | WF-020774 |  | Approved with Comments
Stabling Yard 2 |  | Wifi | Cable Routing |  | A | Approved from CJV |  | Released to Systra | WF-020773 |  | Approved with Comments
Stabling Yard 2 |  | Wifi | WIFI Heatmap |  | A | Approved from CJV |  | Released to Systra | WF-020773 |  | Approved with Comments
Stabling Yard 2 |  | OATS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-023572 |  | Under Systra Review
Stabling Yard 2 |  | OATS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-023572 |  | Under Systra Review
Stabling Yard 2 |  | OATS | Cable Schedule |  | A | Approved from CJV |  | Released to Systra | WF-023572 |  | Under Systra Review
Stabling Yard 2 |  | OATS | Cable Routing |  | A | Approved from CJV |  | Released to Systra | WF-023573 |  | Under Systra Review
Stabling Yard 2 |  | MSN | Equipment Layout Drawing |  | A | Approved from CJV |  | Under SMO review | WF-021197 | 2026-04-03
Stabling Yard 2 |  | MSN | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Under SMO review | WF-021197 | 2026-04-03
Stabling Yard 2 |  | MSN | System Cable routing plan |  | A | Approved from CJV |  | Under SMO review | WF-021197 | 2026-04-03
Automatic Train Washing Plant |  | OATS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-021060 |  | Approved with Comments
Automatic Train Washing Plant |  | OATS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-021060 |  | Approved with Comments
Automatic Train Washing Plant |  | OATS | Cable Schedule |  | A | Approved from CJV |  | Released to Systra | WF-021063 |  | Approved with Comments
Automatic Train Washing Plant |  | OATS | Cable Routing |  | A | Approved from CJV |  | Released to Systra | WF-021060 |  | Approved with Comments
Automatic Train Washing Plant |  | MSN | Equipment Layout Drawing |  | A | Approved from CJV |  | Under SMO review | WF-021088 | 2026-04-03
Automatic Train Washing Plant |  | MSN | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Under SMO review | WF-021088 | 2026-04-03
Automatic Train Washing Plant |  | MSN | System Cable routing plan |  | A | Approved from CJV |  | Under SMO review | WF-021088 | 2026-04-03
Fresh Water Refiling Building |  | OATS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-021099 |  | Approved with Comments
Fresh Water Refiling Building |  | OATS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-021099 |  | Approved with Comments
Fresh Water Refiling Building |  | OATS | Cable Schedule |  | A | Approved from CJV |  | Released to Systra | WF-021101 |  | Approved with Comments
Fresh Water Refiling Building |  | OATS | Cable Routing |  | A | Approved from CJV |  | Released to Systra | WF-021099 |  | Approved with Comments
Fresh Water Refiling Building |  | MSN | Equipment Layout Drawing |  | A | Approved from CJV |  | Under SMO review | WF-021131 | 2026-04-04
Fresh Water Refiling Building |  | MSN | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Under SMO review | WF-021131 | 2026-04-04
Fresh Water Refiling Building |  | MSN | System Cable routing plan |  | A | Approved from CJV |  | Under SMO review | WF-021131 | 2026-04-04
REL Workshop Building |  | OATS | Equipment Layout Drawing |  | A | Under HNWL updated
REL Workshop Building |  | OATS | System Overall Architecture (SLD) |  | A | Under HNWL updated
REL Workshop Building |  | OATS | Cable Schedule |  | A | Under HNWL updated
REL Workshop Building |  | OATS | Cable Routing |  | A | Under HNWL updated
REL Workshop Building |  | MSN | Equipment Layout Drawing |  | A | Approved from CJV |  | Under SMO review | WF-021132
REL Workshop Building |  | MSN | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Under SMO review | WF-021132
REL Workshop Building |  | MSN | System Cable routing plan |  | A | Approved from CJV |  | Under SMO review | WF-021132
Documents Status
[15 empty] | Total Number of Documents | 117
[15 empty] | Total Number of submitted from HNWL doumcnts | 72
[15 empty] | Total Number of not submitted from HNWL documents | 45
[15 empty] | Under HNWL updated | 4
[15 empty] | Under CJV Review | 0
[15 empty] | Under Safety Review | 0
[15 empty] | Under SMO Review | 21
[15 empty] | Released to Systra | 47
[15 empty] | Under Systra Review | 4
[15 empty] | Approved with Comments | 44
[15 empty] | Rejected | 3

## ICT DD - Service Point
Cutoff 03-09-2026
[6 empty] | Internal Review |  | SMO Review |  |  | Systra Review
Building NAME | Building Ref. | TEL Sub-Systems | Document Title | Document No. | Rev. | Status With Honeywell | Status Date | Document through WF Status | WF no. | Date | Status with Systra | Status Date | REASONS OF RETURN | Comment
NC SP - Fresh Water Building | OATS | Equipment Layout Drawing |  |  | A | Approved from CJV |  | Released to Systra | WF-024138 |  | Under Systra Review
NC SP - Fresh Water Building | OATS | System Overall Architecture (SLD) |  |  | A | Approved from CJV |  | Released to Systra | WF-024138 |  | Under Systra Review
NC SP - Fresh Water Building | OATS | Cable Schedule |  |  | A | Approved from CJV |  | Released to Systra | WF-024138 |  | Under Systra Review
NC SP - Fresh Water Building | OATS | Cable Routing |  |  | A | Approved from CJV |  | Released to Systra | WF-024140 |  | Under Systra Review
NC SP - Fresh Water Building | MSN | Equipment Layout Drawing |  |  | A | Under HNWL updated
NC SP - Fresh Water Building | MSN | System Overall Architecture (SLD) |  |  | A | Under HNWL updated
NC SP - Fresh Water Building | MSN | System Cable routing plan |  |  | A | Under HNWL updated
NC & MM SP - Stabling Yard Building | Wifi | Equipment Layout Drawing |  |  | A | Approved from CJV |  | Released to Systra | WF-024145 |  | Under Systra Review
NC & MM SP - Stabling Yard Building | Wifi | System Overall Architecture (SLD) |  |  | A | Approved from CJV |  | Released to Systra | WF-024145 |  | Under Systra Review
NC & MM SP - Stabling Yard Building | Wifi | Cable Schedule |  |  | A | Approved from CJV |  | Released to Systra | WF-024145 |  | Under Systra Review
NC & MM SP - Stabling Yard Building | Wifi | Cable Routing |  |  | A | Approved from CJV |  | Released to Systra | WF-024145 |  | Under Systra Review
NC & MM SP - Stabling Yard Building | Wifi | WIFI Heatmap |  |  | A | Approved from CJV |  | Released to Systra | WF-024146 |  | Under Systra Review
NC & MM SP - Stabling Yard Building | OATS | Equipment Layout Drawing |  |  | A | Under Safety Review |  | Released to Systra | WF-024392 |  | Under Systra Review
NC & MM SP - Stabling Yard Building | OATS | System Overall Architecture (SLD) |  |  | A | Under Safety Review |  | Released to Systra | WF-024392 |  | Under Systra Review
NC & MM SP - Stabling Yard Building | OATS | Cable Schedule |  |  | A | Under Safety Review |  | Released to Systra | WF-024392 |  | Under Systra Review
NC & MM SP - Stabling Yard Building | OATS | Cable Routing |  |  | A | Under Safety Review |  | Released to Systra | WF-024393 |  | Under Systra Review
NC & MM SP - Stabling Yard Building | MSN | Equipment Layout Drawing |  |  | A | Approved from CJV |  | Under SMO Review | WF-021712
NC & MM SP - Stabling Yard Building | MSN | System Overall Architecture (SLD) |  |  | A | Approved from CJV |  | Under SMO Review | WF-021712
NC & MM SP - Stabling Yard Building | MSN | System Cable routing plan |  |  | A | Approved from CJV |  | Under SMO Review | WF-021712
NC SP - High Pressure Curtain Wash Building | OATS | Equipment Layout Drawing |  |  | A | Approved from CJV |  | Under SMO Review | WF-024460
NC SP - High Pressure Curtain Wash Building | OATS | System Overall Architecture (SLD) |  |  | A | Approved from CJV |  | Under SMO Review | WF-024460
NC SP - High Pressure Curtain Wash Building | OATS | Cable Schedule |  |  | A | Approved from CJV |  | Under SMO Review | WF-024460
NC SP - High Pressure Curtain Wash Building | OATS | Cable Routing |  |  | A | Approved from CJV |  | Under SMO Review | WF-024461
NC SP - High Pressure Curtain Wash Building | MSN | Equipment Layout Drawing |  |  | A | Under HNWL updated
NC SP - High Pressure Curtain Wash Building | MSN | System Overall Architecture (SLD) |  |  | A | Under HNWL updated
NC SP - High Pressure Curtain Wash Building | MSN | System Cable routing plan |  |  | A | Under HNWL updated
Borg El-Arab SP - Stabling Yard Building | Wifi | Equipment Layout Drawing |  |  | A | Approved from CJV |  | Released to Systra | WF-024022 |  | Under Systra Review
Borg El-Arab SP - Stabling Yard Building | Wifi | System Overall Architecture (SLD) |  |  | A | Approved from CJV |  | Released to Systra | WF-024022 |  | Under Systra Review
Borg El-Arab SP - Stabling Yard Building | Wifi | Cable Schedule |  |  | A | Approved from CJV |  | Released to Systra | WF-024022 |  | Under Systra Review
Borg El-Arab SP - Stabling Yard Building | Wifi | Cable Routing |  |  | A | Approved from CJV |  | Released to Systra | WF-024022 |  | Under Systra Review
Borg El-Arab SP - Stabling Yard Building | Wifi | WIFI Heatmap |  |  | A | Approved from CJV |  | Released to Systra | WF-024023 |  | Under Systra Review
Borg El-Arab SP - Stabling Yard Building | OATS | Equipment Layout Drawing |  |  | A | Approved from CJV |  | Released to Systra | WF-024155 |  | Under Systra Review
Borg El-Arab SP - Stabling Yard Building | OATS | System Overall Architecture (SLD) |  |  | A | Approved from CJV |  | Released to Systra | WF-024155 |  | Under Systra Review
Borg El-Arab SP - Stabling Yard Building | OATS | Cable Schedule |  |  | A | Approved from CJV |  | Released to Systra | WF-024155 |  | Under Systra Review
Borg El-Arab SP - Stabling Yard Building | OATS | Cable Routing |  |  | A | Approved from CJV |  | Released to Systra | WF-024156 |  | Under Systra Review
Borg El-Arab SP - Stabling Yard Building | MSN | Equipment Layout Drawing |  |  | A | Under HNWL updated
Borg El-Arab SP - Stabling Yard Building | MSN | System Overall Architecture (SLD) |  |  | A | Under HNWL updated
Borg El-Arab SP - Stabling Yard Building | MSN | System Cable routing plan |  |  | A | Under HNWL updated
Borg El-Arab SP - WPMS | OATS | Equipment Layout Drawing |  |  | A | Approved from CJV |  | Released to systra | WF-023802 |  | Under Systra Review
Borg El-Arab SP - WPMS | OATS | System Overall Architecture (SLD) |  |  | A | Approved from CJV |  | Released to systra | WF-023802 |  | Under Systra Review
Borg El-Arab SP - WPMS | OATS | Cable Schedule |  |  | A | Approved from CJV |  | Released to systra | WF-023802 |  | Under Systra Review
Borg El-Arab SP - WPMS | OATS | Cable Routing |  |  | A | Approved from CJV |  | Released to systra | WF-023803 |  | Under Systra Review
Borg El-Arab SP - WPMS | MSN | Equipment Layout Drawing |  |  | A | Under HNWL updated
Borg El-Arab SP - WPMS | MSN | System Overall Architecture (SLD) |  |  | A | Under HNWL updated
Borg El-Arab SP - WPMS | MSN | System Cable routing plan |  |  | A | Under HNWL updated
NC SP - OCS switching hub | OATS | Equipment Layout Drawing |  |  | A
NC SP - OCS switching hub | OATS | System Overall Architecture (SLD) |  |  | A
NC SP - OCS switching hub | OATS | Cable Schedule |  |  | A
NC SP - OCS switching hub | OATS | Cable Routing |  |  | A
NC SP - OCS switching hub | MSN | Equipment Layout Drawing |  |  | A | Under HNWL updated
NC SP - OCS switching hub | MSN | System Overall Architecture (SLD) |  |  | A | Under HNWL updated
NC SP - OCS switching hub | MSN | System Cable routing plan |  |  | A | Under HNWL updated
Documents Status
[15 empty] | Total Number of Documents | 52
[15 empty] | Total Number of submitted from HNWL doumcnts | 48
[15 empty] | Total Number of not submitted from HNWL documents | 4
[15 empty] | Under HNWL updated | 15
[15 empty] | Under CJV Review | 0
[15 empty] | Under Safety Review | 4
[15 empty] | Under SMO Review | 7
[15 empty] | Released to Systra | 26
[15 empty] | Under Systra Review | 26
[15 empty] | Approved with Comments | 0
[15 empty] | Rejected | 0

## ELV DD (Stations)
Cutoff 02-09-2026
[7 empty] | Internal Review |  | SMO Review |  |  | Systra Review
NO. | STATION NAME | Station Ref. | TEL Sub-Systems | Document Title | Document No. | Rev. | Status With Honeywell | Status Date | Document through WF Status | WF no. | Date | Status with Systra | Status Date | Comment
1 | NEW CAPITAL | GLB02 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLB02-1200002 | D | Approved from CJV |  | Released to Systra | WF - 18636 | 2026-01-18 | Approved with Comments
2 | NEW CAPITAL | GLB02 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLB02-1200001 | D | Approved from CJV |  | Released to Systra | WF - 18636 | 2026-01-18 | Approved with Comments
3 | NEW CAPITAL | GLB02 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLB02-1200003 | C | Approved from CJV |  | Released to Systra | WF - 18636 | 2026-01-18 | Approved with Comments
4 | NEW CAPITAL | GLB02 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLB02-1200002 | A | Approved from CJV |  | Released to Systra | WF - 18628 | 2026-01-29 | Approved with Comments
5 | NEW CAPITAL | GLB02 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLB02-1200002 | B | Approved from CJV |  | Released to Systra | 24805 |  | Under Systra Review
6 | NEW CAPITAL | GLB02 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLB02-1200001 | B | Approved from CJV |  | Released to Systra | 24805 |  | Under Systra Review
7 | NEW CAPITAL | GLB02 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLB02-1200003 | B | Approved from CJV |  | Released to Systra | 24805 |  | Under Systra Review
8 | NEW CAPITAL | GLB02 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLB02-1200002 | B | Approved from CJV |  | Released to Systra | 24805 |  | Under Systra Review
9 | NEW CAPITAL | GLB02 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLB02-1200003 | A | Approved from CJV |  | Under SMO Review | 25030
| NEW CAPITAL | GLB02 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLB02-1200004 | A | Approved from CJV |  | Released to Systra | 22602 |  | Approved with Comments
10 | NEW CAPITAL | GLB02 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLB02-1200002 | B | Approved from CJV |  | Released to Systra | WF - 18748 | 2026-01-29 | Approved with Comments
11 | NEW CAPITAL | GLB02 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLB02-1200001 | B | Approved from CJV |  | Released to Systra | WF - 18748 | 2026-01-29 | Approved with Comments
12 | NEW CAPITAL | GLB02 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLB02-1200003 | B | Approved from CJV |  | Released to Systra | WF - 18748 | 2026-01-29 | Approved with Comments
13 | NEW CAPITAL | GLB02 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLB02-1200004 | A | Approved from CJV |  | Released to Systra | WF - 18749 | 2026-01-29 | Approved with Comments
14 | NEW CAPITAL | GLB02 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLB02-1200002 | B | Approved from CJV |  | Released to Systra | WF-018383 | 2025-11-14 | Approved with Comments
15 | NEW CAPITAL | GLB02 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLB02-1200001 | B | Approved from CJV |  | Released to Systra | WF-018383 | 2025-11-14 | Approved with Comments
16 | NEW CAPITAL | GLB02 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLB02-1200003 | B | Approved from CJV |  | Released to Systra | WF-018383 | 2025-11-14 | Approved with Comments
17 | NEW CAPITAL | GLB02 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLB02-1200003 | A | Approved from CJV |  | Released to Systra | 24769 | 2025-11-14 | Under Systra Review
18 | NEW CAPITAL | GLB02 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLB02-1200004 | A | Approved from CJV |  | Released to Systra | 21612 | 2025-11-14 | Approved with Comments
19 | NEW CAPITAL | GLB02 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLB02-1200001 | A | Approved from CJV |  | Released to Systra | WF-023343 |  | Approved with Comments
20 | NEW CAPITAL | GLB02 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLB02-1200002 | A | Approved from CJV |  | Released to Systra | WF-023343 |  | Approved with Comments
21 | NEW CAPITAL | GLB02 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLB02-1200003 | A | Approved from CJV |  | Released to Systra | WF-023343 |  | Approved with Comments
22 | NEW CAPITAL | GLB02 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLB02-1200002 | A | Approved from CJV |  | Released to Systra | WF-023345 |  | Approved with Comments
23 | NEW CAPITAL | GLB02 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLB02-1200003 | A | Approved from CJV |  | Released to Systra | WF-023346 |  | Approved with Comments
24 | NEW CAPITAL | GLB02 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLB02-1200001 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
25 | NEW CAPITAL | GLB02 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLB02-1200002 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
26 | NEW CAPITAL | GLB02 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLB02-1200003 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
27 | NEW CAPITAL | GLB02 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLB02-1200002 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
28 | NEW CAPITAL | GLB02 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLB02-1200003 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
29 | Ahmed Omar Hashem | GLB03 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLB03-1200002 | C | Approved from CJV |  | Released to Systra | WF - 18525 | 2025-12-28 | Approved with Comments | 2026-01-19
30 | Ahmed Omar Hashem | GLB03 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLB03-1200001 | C | Approved from CJV |  | Released to Systra | WF - 18525 | 2025-12-28 | Approved with Comments | 2026-01-19
31 | Ahmed Omar Hashem | GLB03 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLB03-1200003 | B | Approved from CJV |  | Released to Systra | WF - 18525 | 2025-12-28 | Approved with Comments | 2026-01-19
32 | Ahmed Omar Hashem | GLB03 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLB03-1200002 | A | Approved from CJV |  | Released to Systra | WF - 18523 | 2026-01-29 | Approved with Comments | 2026-01-29
33 | Ahmed Omar Hashem | GLB03 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLB03-1200002 | A | Approved from CJV | 2026-01-04 | Released to Systra | 24790 |  | Under Systra Review
34 | Ahmed Omar Hashem | GLB03 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLB03-1200001 | A | Approved from CJV | 2026-01-04 | Released to Systra | 24790 |  | Under Systra Review
35 | Ahmed Omar Hashem | GLB03 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLB03-1200003 | A | Approved from CJV | 2026-01-04 | Released to Systra | 24790 |  | Under Systra Review
36 | Ahmed Omar Hashem | GLB03 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLB03-1200002 | A | Approved from CJV | 2026-01-04 | Released to Systra | 24790 |  | Under Systra Review
37 | Ahmed Omar Hashem | GLB03 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLB03-1200003 | A | Approved from CJV | 2026-01-04 | Released to Systra | 24792 |  | Under Systra Review
| Ahmed Omar Hashem | GLB03 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLB03-1200004 | A | Approved from CJV |  | Under SMO Review | WF-025288
38 | Ahmed Omar Hashem | GLB03 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLB03-1200002 | A | Approved from CJV |  | Released to Systra | WF-015668 |  | Approved with Comments | 2026-02-01
39 | Ahmed Omar Hashem | GLB03 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLB03-1200001 | A | Approved from CJV |  | Released to Systra | WF-015668 |  | Approved with Comments | 2026-02-01
40 | Ahmed Omar Hashem | GLB03 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLB03-1200003 | A | Approved from CJV |  | Released to Systra | WF-015668 |  | Approved with Comments | 2026-02-01
41 | Ahmed Omar Hashem | GLB03 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLB03-1200004 | A | Approved from CJV |  | Released to Systra | WF-018560 |  | Approved with Comments
42 | Ahmed Omar Hashem | GLB03 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLB03-1200002 | B | Approved from CJV |  | Released to Systra | 21994 |  | Approved with Comments
43 | Ahmed Omar Hashem | GLB03 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLB03-1200001 | B | Approved from CJV |  | Released to Systra | 21994 |  | Approved with Comments
44 | Ahmed Omar Hashem | GLB03 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLB03-1200003 | B | Approved from CJV |  | Released to Systra | 21994 |  | Approved with Comments
45 | Ahmed Omar Hashem | GLB03 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLB03-1200003 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
46 | Ahmed Omar Hashem | GLB03 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLB03-1200004 | A | Approved from CJV |  | Released to Systra | 21997 |  | Approved with Comments
47 | Ahmed Omar Hashem | GLB03 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLB03-1200001 | A | Under HNWL update | 2026-01-25
48 | Ahmed Omar Hashem | GLB03 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLB03-1200002 | A | Under HNWL update | 2026-01-25
49 | Ahmed Omar Hashem | GLB03 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLB03-1200003 | A | Under HNWL update | 2026-01-25
50 | Ahmed Omar Hashem | GLB03 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLB03-1200002 | A | Under HNWL update | 2026-01-25
51 | Ahmed Omar Hashem | GLB03 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLB03-1200003 | A
52 | Ahmed Omar Hashem | GLB03 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLB03-1200001 | A | Approved from CJV |  | Released to Systra | 21554 | 2026-04-01 | Approved with Comments
53 | Ahmed Omar Hashem | GLB03 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLB03-1200002 | A | Approved from CJV |  | Released to Systra | 21554 | 2026-04-01 | Approved with Comments
54 | Ahmed Omar Hashem | GLB03 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLB03-1200003 | A | Approved from CJV |  | Released to Systra | 21554 | 2026-04-01 | Approved with Comments
55 | Ahmed Omar Hashem | GLB03 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLB03-1200002 | A | Approved from CJV |  | Released to Systra | 21554 | 2026-04-01 | Approved with Comments
56 | Ahmed Omar Hashem | GLB03 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLB03-1200003 | A | Approved from CJV |  | Released to Systra | 21555 | 2026-04-01 | Approved with Comments
57 | ALAMIAN | GLH15 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLH15-1200002 | C | Approved from CJV |  | Released to Systra | WF - 18521 | 2026-01-07 | Approved with Comments | 2026-01-20
58 | ALAMIAN | GLH15 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLH15-1200001 | C | Approved from CJV |  | Released to Systra | WF - 18521 | 2026-01-07 | Approved with Comments | 2026-01-20
59 | ALAMIAN | GLH15 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLH15-1200003 | C | Approved from CJV |  | Released to Systra | WF - 18521 | 2026-01-07 | Approved with Comments | 2026-01-20
60 | ALAMIAN | GLH15 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLH15-1200002 | A | Approved from CJV |  | Released to Systra | WF - 18516 | 2026-01-29 | Approved with Comments | 2026-01-29
61 | ALAMIAN | GLH15 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLH15-1200002 | B | Approved from CJV |  | Released to Systra | WF-023827 |  | Under Systra Review
62 | ALAMIAN | GLH15 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLH15-1200001 | B | Approved from CJV |  | Released to Systra | WF-023827 |  | Under Systra Review
63 | ALAMIAN | GLH15 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLH15-1200003 | B | Approved from CJV |  | Released to Systra | WF-023827 |  | Under Systra Review
64 | ALAMIAN | GLH15 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLH15-1200002 | B | Approved from CJV |  | Released to Systra | WF-023827 |  | Under Systra Review
65 | ALAMIAN | GLH15 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLH15-1200003 | B | Approved from CJV |  | Released to Systra | WF-023828 |  | Under Systra Review
| ALAMIAN | GLH15 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLH15-1200004 | A | Approved from CJV |  | Released to Systra | WF-022921 |  | Approved with Comments
66 | ALAMIAN | GLH15 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLH15-1200002 | B | Approved from CJV |  | Released to Systra | WF - 18652 | 2026-01-29 | Approved with Comments
67 | ALAMIAN | GLH15 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLH15-1200001 | B | Approved from CJV |  | Released to Systra | WF - 18652 | 2026-01-29 | Approved with Comments
68 | ALAMIAN | GLH15 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLH15-1200003 | B | Approved from CJV |  | Released to Systra | WF - 18652 | 2026-01-29 | Approved with Comments
69 | ALAMIAN | GLH15 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLH15-1200004 | B | Approved from CJV |  | Released to Systra | WF - 18648 | 2026-01-29 | Approved with Comments
70 | ALAMIAN | GLH15 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLH15-1200002 | B | Approved from CJV |  | Released to Systra | WF-018654 | 2026-01-29 | Approved with Comments
71 | ALAMIAN | GLH15 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLH15-1200001 | B | Approved from CJV |  | Released to Systra | WF-018654 | 2026-01-29 | Approved with Comments
72 | ALAMIAN | GLH15 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLH15-1200003 | B | Approved from CJV |  | Released to Systra | WF-018654 | 2026-01-29 | Approved with Comments
73 | ALAMIAN | GLH15 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLH15-1200003 | A | Approved from CJV |  | Released to Systra | WF-018653 |  | Rejected
74 | ALAMIAN | GLH15 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLH15-1200004 | A | Approved from CJV | 2026-01-25 | Released to Systra | WF-023199 |  | Under Systra Review
75 | ALAMIAN | GLH15 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLH15-1200001 | A | Under HNWL update | 2026-01-25
76 | ALAMIAN | GLH15 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLH15-1200002 | A | Under HNWL update | 2026-01-25
77 | ALAMIAN | GLH15 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLH15-1200003 | A | Under HNWL update | 2026-01-25
78 | ALAMIAN | GLH15 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLH15-1200002 | A | Under HNWL update | 2026-01-25
79 | ALAMIAN | GLH15 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLH15-1200003 | A
80 | ALAMIAN | GLH15 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLH15-1200001 | A | Approved from CJV | 2026-02-25 | Released to Systra | 24462 |  | Under Systra Review
81 | ALAMIAN | GLH15 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLH15-1200002 | A | Approved from CJV | 2026-02-25 | Released to Systra | 24462 |  | Under Systra Review
82 | ALAMIAN | GLH15 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLH15-1200003 | A | Approved from CJV | 2026-02-25 | Released to Systra | 24462 |  | Under Systra Review
83 | ALAMIAN | GLH15 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLH15-1200002 | A | Approved from CJV | 2026-02-25 | Released to Systra | 24462 |  | Under Systra Review
84 | ALAMIAN | GLH15 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLH15-1200003 | A | Approved from CJV | 2026-02-25 | Released to Systra | 24464 |  | Under Systra Review
85 | RAS ELHEKMA | GLM19 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLM19-1200002 | C | Approved from CJV |  | Released to Systra | WF - 19198 | 2026-01-29 | Approved with Comments
86 | RAS ELHEKMA | GLM19 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLM19-1200001 | C | Approved from CJV |  | Released to Systra | WF - 19198 | 2026-01-29 | Approved with Comments
87 | RAS ELHEKMA | GLM19 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLM19-1200003 | C | Approved from CJV |  | Released to Systra | WF - 19198 | 2026-01-29 | Approved with Comments
88 | RAS ELHEKMA | GLM19 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLM19-1200002 | A | Approved from CJV |  | Released to Systra | WF - 19194 | 2026-01-29 | Approved with Comments
89 | RAS ELHEKMA | GLM19 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLM19-1200002 | A | Approved from CJV |  | Released to Systra |  | 2026-02-25 | Under Systra Review
90 | RAS ELHEKMA | GLM19 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLM19-1200001 | A | Approved from CJV |  | Released to Systra |  | 2026-02-25 | Under Systra Review
91 | RAS ELHEKMA | GLM19 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLM19-1200003 | A | Approved from CJV |  | Released to Systra |  | 2026-02-25 | Under Systra Review
92 | RAS ELHEKMA | GLM19 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLM19-1200002 | A | Approved from CJV |  | Released to Systra |  | 2026-02-25 | Under Systra Review
93 | RAS ELHEKMA | GLM19 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLM19-1200003 | A | Approved from CJV |  | Released to Systra |  | 2026-02-25 | Under Systra Review
| RAS ELHEKMA | GLM19 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLM19-1200004 | A | Approved from CJV |  | Released to Systra | 22927 |  | Under Systra Review
94 | RAS ELHEKMA | GLM19 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLM19-1200002 | B | Approved from CJV |  | Released to Systra | WF-019216 | 2026-02-01 | Approved with Comments
95 | RAS ELHEKMA | GLM19 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLM19-1200001 | B | Approved from CJV |  | Released to Systra | WF-019216 | 2026-02-01 | Approved with Comments
96 | RAS ELHEKMA | GLM19 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLM19-1200003 | B | Approved from CJV |  | Released to Systra | WF-019216 | 2026-02-01 | Approved with Comments
97 | RAS ELHEKMA | GLM19 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLM19-1200004 | A | Approved from CJV |  | Released to Systra | WF-019291 | 2026-01-29 | Approved with Comments
98 | RAS ELHEKMA | GLM19 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLM19-1200002 | B | Approved from CJV |  | Released to Systra | WF- 019789 | 2026-01-22 | Approved with Comments
99 | RAS ELHEKMA | GLM19 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLM19-1200001 | B | Approved from CJV |  | Released to Systra | WF- 019789 | 2026-01-22 | Approved with Comments
100 | RAS ELHEKMA | GLM19 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLM19-1200003 | B | Approved from CJV |  | Released to Systra | WF- 019789 | 2026-01-22 | Approved with Comments
101 | RAS ELHEKMA | GLM19 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLM19-1200003 | A | Approved from CJV |  | Released to Systra | WF- 019790 | 2026-01-22 | Rejected
102 | RAS ELHEKMA | GLM19 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLM19-1200004 | A | Approved from CJV |  | Released to Systra | 20238 |  | Under Systra Review
103 | RAS ELHEKMA | GLM19 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLM19-1200001 | A | Under HNWL update | 2026-02-10
104 | RAS ELHEKMA | GLM19 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLM19-1200002 | A | Under HNWL update | 2026-02-10
105 | RAS ELHEKMA | GLM19 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLM19-1200003 | A | Under HNWL update | 2026-02-10
106 | RAS ELHEKMA | GLM19 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLM19-1200002 | A | Under HNWL update | 2026-02-10
107 | RAS ELHEKMA | GLM19 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLM19-1200003 | A | Under HNWL update | 2026-02-10
108 | RAS ELHEKMA | GLM19 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLM19-1200001 | A | Approved from CJV | 2026-03-24 | Released to Systra |  |  | Approved with Comments
109 | RAS ELHEKMA | GLM19 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLM19-1200002 | A | Approved from CJV | 2026-03-24 | Released to Systra |  |  | Approved with Comments
110 | RAS ELHEKMA | GLM19 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLM19-1200003 | A | Approved from CJV | 2026-03-24 | Released to Systra |  |  | Approved with Comments
111 | RAS ELHEKMA | GLM19 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLM19-1200002 | A | Approved from CJV | 2026-03-24 | Released to Systra |  |  | Approved with Comments
112 | RAS ELHEKMA | GLM19 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLM19-1200003 | A | Approved from CJV | 2026-03-24 | Released to Systra |  |  | Approved with Comments
113 | WADI NATROUN | GLE10 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLE10-1200002 | A | Approved from CJV |  | Released to Systra | WF-019079 | 2026-01-18 | Approved with Comments | 2026-01-21
114 | WADI NATROUN | GLE10 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLE10-1200001 | A | Approved from CJV |  | Released to Systra | WF-019079 | 2026-01-18 | Approved with Comments | 2026-01-21
115 | WADI NATROUN | GLE10 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLE10-1200003 | A | Approved from CJV |  | Released to Systra | WF-019079 | 2026-01-18 | Approved with Comments | 2026-01-21
116 | WADI NATROUN | GLE10 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLE10-1200002 | A | Approved from CJV |  | Released to Systra | WF-019078 | 2026-01-29 | Approved with Comments | 2026-01-29
117 | WADI NATROUN | GLE10 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLE10-1200002 | B | Approved from CJV |  | Released to Systra | WF-023938 |  | Under Systra Review
118 | WADI NATROUN | GLE10 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLE10-1200001 | B | Approved from CJV |  | Released to Systra | WF-023938 |  | Under Systra Review
119 | WADI NATROUN | GLE10 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLE10-1200003 | B | Approved from CJV |  | Released to Systra | WF-023938 |  | Under Systra Review
120 | WADI NATROUN | GLE10 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLE10-1200002 | B | Approved from CJV |  | Released to Systra | WF-023938 |  | Under Systra Review
121 | WADI NATROUN | GLE10 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLE10-1200003 | B | Approved from CJV |  | Released to Systra | WF-023349 |  | Approved with Comments
| WADI NATROUN | GLE10 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLE10-1200004 | A | Approved from CJV |  | Released to Systra | 22519 |  | Approved with Comments
122 | WADI NATROUN | GLE10 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLE10-1200002 | A | Approved from CJV |  | Released to Systra | WF - 19110 | 2026-02-01 | Approved with Comments
123 | WADI NATROUN | GLE10 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLE10-1200001 | A | Approved from CJV |  | Released to Systra | WF - 19110 | 2026-02-01 | Approved with Comments
124 | WADI NATROUN | GLE10 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLE10-1200003 | A | Approved from CJV |  | Released to Systra | WF - 19110 | 2026-02-01 | Approved with Comments
125 | WADI NATROUN | GLE10 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLE10-1200004 | A | Approved from CJV |  | Released to Systra | WF - 19107 | 2026-01-28 | Approved with Comments
126 | WADI NATROUN | GLE10 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLE10-1200002 | A | Approved from CJV |  | Released to Systra | WF-019244 | 2026-02-08 | Approved with Comments
127 | WADI NATROUN | GLE10 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLE10-1200001 | A | Approved from CJV |  | Released to Systra | WF-019244 | 2026-02-08 | Approved with Comments
128 | WADI NATROUN | GLE10 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLE10-1200003 | A | Approved from CJV |  | Released to Systra | WF-019244 | 2026-02-08 | Approved with Comments
129 | WADI NATROUN | GLE10 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLE10-1200003 | A | Approved from CJV |  | Released to Systra | WF-019242 |  | Rejected
130 | WADI NATROUN | GLE10 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLE10-1200004 | A | Approved from CJV |  | Released to Systra | WF-021478 |  | Rejected
131 | WADI NATROUN | GLE10 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLE10-1200001 | A | Under HNWL update | 2026-02-10
132 | WADI NATROUN | GLE10 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLE10-1200002 | A | Under HNWL update | 2026-02-10
133 | WADI NATROUN | GLE10 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLE10-1200003 | A | Under HNWL update | 2026-02-10
134 | WADI NATROUN | GLE10 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLE10-1200002 | A | Under HNWL update | 2026-02-10
135 | WADI NATROUN | GLE10 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLE10-1200003 | A | Under HNWL update | 2026-02-10
136 | WADI NATROUN | GLE10 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLE10-1200001 | A | Approved from CJV |  | Released to Systra | 24395 |  | Under Systra Review
137 | WADI NATROUN | GLE10 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLE10-1200002 | A | Approved from CJV |  | Released to Systra | 24395 |  | Under Systra Review
138 | WADI NATROUN | GLE10 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLE10-1200003 | A | Approved from CJV |  | Released to Systra | 24395 |  | Under Systra Review
139 | WADI NATROUN | GLE10 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLE10-1200002 | A | Approved from CJV |  | Released to Systra | 24395 |  | Under Systra Review
140 | WADI NATROUN | GLE10 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLE10-1200003 | A | Approved from CJV |  | Released to Systra | 24396 |  | Under Systra Review
141 | OCTOBER GARDEN | GLC06 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLC06-1200002 | B | Approved from CJV |  | Released to Systra | WF - 18759 | 2026-01-29 | Approved with Comments
142 | OCTOBER GARDEN | GLC06 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLC06-1200001 | B | Approved from CJV |  | Released to Systra | WF - 18759 | 2026-01-29 | Approved with Comments
143 | OCTOBER GARDEN | GLC06 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLC06-1200003 | A | Approved from CJV |  | Released to Systra | WF - 18759 | 2026-01-29 | Approved with Comments
144 | OCTOBER GARDEN | GLC06 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLC06-1200002 | A | Approved from CJV |  | Released to Systra | WF - 18756 | 2026-01-29 | Approved with Comments
145 | OCTOBER GARDEN | GLC06 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLC06-1200002 | A | Approved from CJV | 2026-02-02 | Released to Systra | 24983 |  | Under Systra Review
146 | OCTOBER GARDEN | GLC06 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLC06-1200001 | A | Approved from CJV | 2026-02-02 | Released to Systra | 24983 |  | Under Systra Review
147 | OCTOBER GARDEN | GLC06 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLC06-1200003 | A | Approved from CJV | 2026-02-02 | Released to Systra | 24983 |  | Under Systra Review
148 | OCTOBER GARDEN | GLC06 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLC06-1200002 | A | Approved from CJV | 2026-02-02 | Released to Systra | 24983 |  | Under Systra Review
149 | OCTOBER GARDEN | GLC06 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLC06-1200003 | A | Approved from CJV | 2026-02-02 | Under SMO Review | WF-024986
| OCTOBER GARDEN | GLC06 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLC06-1200004 | A | Under CJV review
150 | OCTOBER GARDEN | GLC06 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLC06-1200002 | A | Approved from CJV |  | Released to Systra | WF - 18754 | 2026-01-29 | Approved with Comments
151 | OCTOBER GARDEN | GLC06 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLC06-1200001 | A | Approved from CJV |  | Released to Systra | WF - 18754 | 2026-01-29 | Approved with Comments
152 | OCTOBER GARDEN | GLC06 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLC06-1200003 | A | Approved from CJV |  | Released to Systra | WF - 18754 | 2026-01-29 | Approved with Comments
153 | OCTOBER GARDEN | GLC06 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLC06-1200004 | A | Approved from CJV |  | Released to Systra | WF - 18750 | 2026-01-29 | Approved with Comments
154 | OCTOBER GARDEN | GLC06 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLC06-1200002 | A | Approved from CJV |  | Released to Systra | WF-018241 | 2026-01-29 | Approved with Comments
155 | OCTOBER GARDEN | GLC06 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLC06-1200001 | A | Approved from CJV |  | Released to Systra | WF-018241 | 2026-01-29 | Approved with Comments
156 | OCTOBER GARDEN | GLC06 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLC06-1200003 | A | Approved from CJV |  | Released to Systra | WF-018241 | 2026-01-29 | Approved with Comments
157 | OCTOBER GARDEN | GLC06 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLC06-1200003 | A | Approved from CJV |  | Released to Systra | WF-018242 |  | Rejected
158 | OCTOBER GARDEN | GLC06 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLC06-1200004 | A | Approved from CJV |  | Released to Systra | WF-018243 | 2026-02-08 | Rejected
159 | OCTOBER GARDEN | GLC06 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLC06-1200001 | B | Approved from CJV |  | Released to Systra |  |  | Approved with Comments
160 | OCTOBER GARDEN | GLC06 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLC06-1200002 | B | Approved from CJV |  | Released to Systra |  |  | Approved with Comments
161 | OCTOBER GARDEN | GLC06 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLC06-1200003 | B | Approved from CJV |  | Released to Systra |  |  | Approved with Comments
162 | OCTOBER GARDEN | GLC06 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLC06-1200002 | B | Approved from CJV |  | Released to Systra |  |  | Approved with Comments
163 | OCTOBER GARDEN | GLC06 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLC06-1200003 | B | Approved from CJV |  | Released to Systra |  |  | Approved with Comments
164 | OCTOBER GARDEN | GLC06 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLC06-1200001 | A | Approved from CJV |  | Released to Systra | 23928 |  | Under Systra Review
165 | OCTOBER GARDEN | GLC06 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLC06-1200002 | A | Approved from CJV |  | Released to Systra | 23928 |  | Under Systra Review
166 | OCTOBER GARDEN | GLC06 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLC06-1200003 | A | Approved from CJV |  | Released to Systra | 23928 |  | Under Systra Review
167 | OCTOBER GARDEN | GLC06 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLC06-1200002 | A | Approved from CJV |  | Released to Systra | 23928 |  | Under Systra Review
168 | OCTOBER GARDEN | GLC06 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLC06-1200003 | A | Approved from CJV |  | Released to Systra | 23929 |  | Approved with Comments
169 | CAIRO | GLB04 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLB04-1200002 | C | Approved from CJV |  | Released to Systra | WF - 19327 | 2026-01-29 | Approved with Comments
170 | CAIRO | GLB04 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLB04-1200001 | C | Approved from CJV |  | Released to Systra | WF - 19327 | 2026-01-29 | Approved with Comments
171 | CAIRO | GLB04 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLB04-1200003 | C | Approved from CJV |  | Released to Systra | WF - 19327 | 2026-01-29 | Approved with Comments
172 | CAIRO | GLB04 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLB04-1200002 | A | Approved from CJV |  | Released to Systra | WF - 19322 | 2026-01-29 | Approved with Comments
173 | CAIRO | GLB04 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLB04-1200002 | A | Under HNWL update | 2026-01-04
174 | CAIRO | GLB04 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLB04-1200001 | A | Under HNWL update | 2026-01-04
175 | CAIRO | GLB04 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLB04-1200003 | A | Under HNWL update | 2026-01-04
176 | CAIRO | GLB04 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLB04-1200002 | A | Under HNWL update | 2026-01-04
177 | CAIRO | GLB04 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLB04-1200003 | A | Under HNWL update | 2026-01-04
| CAIRO | GLB04 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLB04-1200004 | A
178 | CAIRO | GLB04 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLB04-1200002 | B | Approved from CJV |  | Released to Systra | WF - 19496 | 2026-02-08 | Approved with Comments
179 | CAIRO | GLB04 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLB04-1200001 | B | Approved from CJV |  | Released to Systra | WF - 19496 | 2026-02-08 | Approved with Comments
180 | CAIRO | GLB04 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLB04-1200003 | B | Approved from CJV |  | Released to Systra | WF - 19496 | 2026-02-08 | Approved with Comments
181 | CAIRO | GLB04 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLB04-1200004 | A | Approved from CJV |  | Released to Systra | WF - 19493 |  | Approved with Comments
182 | CAIRO | GLB04 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLB04-1200002 | C | Approved from CJV |  | Released to Systra | WF-023614 |  | Approved with Comments
183 | CAIRO | GLB04 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLB04-1200001 | C | Approved from CJV |  | Released to Systra | WF-023614 |  | Approved with Comments
184 | CAIRO | GLB04 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLB04-1200003 | B | Approved from CJV |  | Released to Systra | WF-023614 |  | Approved with Comments
185 | CAIRO | GLB04 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLB04-1200003 | A | Approved from CJV |  | Released to Systra | WF-019603 |  | Approved with Comments
186 | CAIRO | GLB04 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLB04-1200004 | A | Approved from CJV |  | Released to Systra | WF-021647 |  | Approved with Comments
187 | CAIRO | GLB04 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLB04-1200001 | A | Under HNWL update | 2026-02-10
188 | CAIRO | GLB04 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLB04-1200002 | A | Under HNWL update | 2026-02-10
189 | CAIRO | GLB04 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLB04-1200003 | A | Under HNWL update | 2026-02-10
190 | CAIRO | GLB04 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLB04-1200002 | A | Under HNWL update | 2026-02-10
191 | CAIRO | GLB04 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLB04-1200003 | A | Under HNWL update | 2026-02-10
192 | CAIRO | GLB04 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLB04-1200001 | B | Approved from CJV |  | Released to Systra | WF-023336 |  | Approved with Comments
193 | CAIRO | GLB04 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLB04-1200002 | B | Approved from CJV |  | Released to Systra | WF-023336 |  | Approved with Comments
194 | CAIRO | GLB04 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLB04-1200003 | B | Approved from CJV |  | Released to Systra | WF-023336 |  | Approved with Comments
195 | CAIRO | GLB04 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLB04-1200002 | B | Approved from CJV |  | Released to Systra | WF-023336 |  | Approved with Comments
196 | CAIRO | GLB04 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLB04-1200003 | B | Approved from CJV |  | Released to Systra | WF-023726 |  | Approved with Comments
197 | GIZA | GLB05 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLB04-1200002 | A | Approved from CJV |  | Released to Systra | WF - 19531 |  | Approved with Comments
198 | GIZA | GLB05 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLB05-1200001 | A | Approved from CJV |  | Released to Systra | WF - 19531 |  | Approved with Comments
199 | GIZA | GLB05 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLB05-1200003 | A | Approved from CJV |  | Released to Systra | WF - 19531 |  | Approved with Comments
200 | GIZA | GLB05 | MCS | Cable SChedule | HSR-SOA-DRW-TELMCS-GLB05-1200002 | A | Approved from CJV |  | Released to Systra | WF - 19532 |  | Approved with Comments
201 | GIZA | GLB05 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLB05-1200002 | A | Approved from CJV | 2026-01-04 | Released to Systra | WF-020928 | 2026-03-04 | Approved with Comments
202 | GIZA | GLB05 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLB05-1200001 | A | Approved from CJV | 2026-01-04 | Released to Systra | WF-020928 | 2026-03-04 | Approved with Comments
203 | GIZA | GLB05 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLB05-1200003 | A | Approved from CJV | 2026-01-04 | Released to Systra | WF-020928 | 2026-03-04 | Approved with Comments
204 | GIZA | GLB05 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLB05-1200002 | A | Approved from CJV | 2026-01-04 | Released to Systra | WF-020928 | 2026-03-04 | Approved with Comments
205 | GIZA | GLB05 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLB05-1200003 | A | Approved from CJV | 2026-01-04 | Released to Systra | WF-020930 | 2026-03-04 | Under Systra Review
| GIZA | GLB05 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLB05-1200004 | A |  |  | Released to Systra |  |  | Under Systra Review
206 | GIZA | GLB05 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLB05-1200002 | A | Approved from CJV |  | Released to Systra | WF - 19544 | 2026-02-08 | Approved with Comments
207 | GIZA | GLB05 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLB05-1200001 | A | Approved from CJV |  | Released to Systra | WF - 19544 | 2026-02-08 | Approved with Comments
208 | GIZA | GLB05 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLB05-1200003 | A | Approved from CJV |  | Released to Systra | WF - 19544 | 2026-02-08 | Approved with Comments
209 | GIZA | GLB05 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLB05-1200004 | A | Approved from CJV |  | Released to Systra | WF - 19545 | 2026-02-01 | Approved with Comments
210 | GIZA | GLB05 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLB05-1200002 | B | Approved from CJV |  | Released to Systra | WF-019695 | 2026-02-09 | Approved with Comments
211 | GIZA | GLB05 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLB05-1200001 | B | Approved from CJV |  | Released to Systra | WF-019695 | 2026-02-09 | Approved with Comments
212 | GIZA | GLB05 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLB05-1200003 | B | Approved from CJV |  | Released to Systra | WF-019695 | 2026-02-09 | Approved with Comments
213 | GIZA | GLB05 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLB05-1200003 | B | Approved from CJV |  | Under SMO Review | WF-025287
214 | GIZA | GLB05 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLB05-1200004 | A | Approved from CJV |  | Released to Systra | WF-019698 |  | Rejected
215 | GIZA | GLB05 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLB05-1200001 | A | Under HNWL update | 2026-02-10
216 | GIZA | GLB05 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLB05-1200002 | A | Under HNWL update | 2026-02-10
217 | GIZA | GLB05 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLB05-1200003 | A | Under HNWL update | 2026-02-10
218 | GIZA | GLB05 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLB05-1200002 | A | Under HNWL update | 2026-02-10
219 | GIZA | GLB05 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLB05-1200003 | A | Under HNWL update | 2026-02-10
220 | GIZA | GLB05 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLB05-1200001 | B | Approved from CJV |  | Released to Systra | WF-023335 |  | Under Systra Review
221 | GIZA | GLB05 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLB05-1200002 | B | Approved from CJV |  | Released to Systra | WF-023335 |  | Under Systra Review
222 | GIZA | GLB05 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLB05-1200003 | B | Approved from CJV |  | Released to Systra | WF-023335 |  | Under Systra Review
223 | GIZA | GLB05 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLB05-1200002 | B | Approved from CJV |  | Released to Systra | WF-023335 |  | Under Systra Review
224 | GIZA | GLB05 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLB05-1200003 | B | Approved from CJV |  | Released to Systra | WF-023347 |  | Approved with Comments
225 | SIDI ABDELRAHMAN | GLI16 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLI16-1200002 | C | Approved from CJV |  | Released to Systra | WF - 19619 | 2026-02-08 | Approved with Comments
226 | SIDI ABDELRAHMAN | GLI16 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLI16-1200001 | C | Approved from CJV |  | Released to Systra | WF - 19619 | 2026-02-08 | Approved with Comments
227 | SIDI ABDELRAHMAN | GLI16 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLI16-1200003 | C | Approved from CJV |  | Released to Systra | WF - 19619 | 2026-02-08 | Approved with Comments
228 | SIDI ABDELRAHMAN | GLI16 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLI16-1200002 | A | Approved from CJV |  | Released to Systra | WF - 19620 | 2026-02-08 | Approved with Comments | 2026-02-08
229 | SIDI ABDELRAHMAN | GLI16 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLI16-1200002 | B | Approved from CJV |  | Released to Systra | WF-023383 |  | Approved with Comments
230 | SIDI ABDELRAHMAN | GLI16 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLI16-1200001 | B | Approved from CJV |  | Released to Systra | WF-023383 |  | Approved with Comments
231 | SIDI ABDELRAHMAN | GLI16 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLI16-1200003 | B | Approved from CJV |  | Released to Systra | WF-023383 |  | Approved with Comments
232 | SIDI ABDELRAHMAN | GLI16 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLI16-1200002 | B | Approved from CJV |  | Released to Systra | WF-023383 |  | Approved with Comments
233 | SIDI ABDELRAHMAN | GLI16 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLI16-1200003 | B | Approved from CJV |  | Released to Systra | WF-023380 |  | Approved with Comments
| SIDI ABDELRAHMAN | GLI16 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLI16-1200004 | A | Approved from CJV |  | Released to Systra | WF-023034 |  | Approved with Comments
234 | SIDI ABDELRAHMAN | GLI16 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLI16-1200002 | B | Approved from CJV |  | Released to Systra | WF- 020051 |  | Approved with Comments
235 | SIDI ABDELRAHMAN | GLI16 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLI16-1200001 | B | Approved from CJV |  | Released to Systra | WF- 020051 |  | Approved with Comments
236 | SIDI ABDELRAHMAN | GLI16 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLI16-1200003 | B | Approved from CJV |  | Released to Systra | WF- 020051 |  | Approved with Comments
237 | SIDI ABDELRAHMAN | GLI16 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLI16-1200004 | A | Approved from CJV |  | Released to Systra | WF- 020052 |  | Approved with Comments
238 | SIDI ABDELRAHMAN | GLI16 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLI16-1200002 | B | Approved from CJV |  | Released to Systra | WF-019704 |  | Approved with Comments
239 | SIDI ABDELRAHMAN | GLI16 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLI16-1200001 | B | Approved from CJV |  | Released to Systra | WF-019704 |  | Approved with Comments
240 | SIDI ABDELRAHMAN | GLI16 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLI16-1200003 | B | Approved from CJV |  | Released to Systra | WF-019704 |  | Approved with Comments
241 | SIDI ABDELRAHMAN | GLI16 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLI16-1200003 | A | Approved from CJV |  | Released to Systra | 24576 |  | Under Systra Review
242 | SIDI ABDELRAHMAN | GLI16 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLI16-1200004 | B | Approved from CJV |  | Released to Systra | WF-023067 |  | Under Systra Review
243 | SIDI ABDELRAHMAN | GLI16 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLI16-1200001 | A | Under HNWL update | 2026-02-10
244 | SIDI ABDELRAHMAN | GLI16 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLI16-1200002 | A | Under HNWL update | 2026-02-10
245 | SIDI ABDELRAHMAN | GLI16 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLI16-1200003 | A | Under HNWL update | 2026-02-10
246 | SIDI ABDELRAHMAN | GLI16 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLI16-1200002 | A | Under HNWL update | 2026-02-10
247 | SIDI ABDELRAHMAN | GLI16 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLI16-1200003 | A | Under HNWL update | 2026-01-24
248 | SIDI ABDELRAHMAN | GLI16 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLI16-1200001 | A | Approved from CJV | 2026-03-24 | Released to Systra | WF-023713 |  | Under Systra Review
249 | SIDI ABDELRAHMAN | GLI16 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLI16-1200002 | A | Approved from CJV | 2026-03-24 | Released to Systra | WF-023713 |  | Under Systra Review
250 | SIDI ABDELRAHMAN | GLI16 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLI16-1200003 | A | Approved from CJV | 2026-03-24 | Released to Systra | WF-023713 |  | Under Systra Review
251 | SIDI ABDELRAHMAN | GLI16 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLI16-1200002 | A | Approved from CJV | 2026-03-24 | Released to Systra | WF-023713 |  | Under Systra Review
252 | SIDI ABDELRAHMAN | GLI16 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLI16-1200003 | A | Approved from CJV | 2026-03-24 | Released to Systra | WF-023730 |  | Approved with Comments
253 | EL NOUBARYA | GLF11 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLF11-1200002 | C | Approved from CJV |  | Released to Systra | WF - 19551 | 46061 | Approved with Comments
254 | EL NOUBARYA | GLF11 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLF11-1200001 | C | Approved from CJV |  | Released to Systra | WF - 19551 | 46061 | Approved with Comments
255 | EL NOUBARYA | GLF11 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLF11-1200003 | C | Approved from CJV |  | Released to Systra | WF - 19551 | 46061 | Approved with Comments
256 | EL NOUBARYA | GLF11 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLF11-1200002 | A | Approved from CJV |  | Released to Systra | WF - 19552 | 46056 | Approved with Comments | 46056
257 | EL NOUBARYA | GLF11 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLF11-1200002 | B | Approved from CJV |  | Released to Systra | WF-023195 |  | Approved with Comments
258 | EL NOUBARYA | GLF11 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLF11-1200001 | B | Approved from CJV |  | Released to Systra | WF-023195 |  | Approved with Comments
259 | EL NOUBARYA | GLF11 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLF11-1200003 | B | Approved from CJV |  | Released to Systra | WF-023195 |  | Approved with Comments
260 | EL NOUBARYA | GLF11 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLF11-1200002 | B | Approved from CJV |  | Released to Systra | WF-023195 |  | Under Systra Review
261 | EL NOUBARYA | GLF11 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLF11-1200003 | A
| EL NOUBARYA | GLF11 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLF11-1200004 | A | Approved from CJV |  | Released to Systra | 22518 |  | Approved with Comments
262 | EL NOUBARYA | GLF11 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLF11-1200002 | B | Approved from CJV |  | Released to Systra | WF-020118 |  | Approved with Comments
263 | EL NOUBARYA | GLF11 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLF11-1200001 | B | Approved from CJV |  | Released to Systra | WF-020118 |  | Approved with Comments
264 | EL NOUBARYA | GLF11 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLF11-1200003 | B | Approved from CJV |  | Released to Systra | WF-020118 |  | Approved with Comments
265 | EL NOUBARYA | GLF11 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLF11-1200004 | A | Approved from CJV |  | Released to Systra | WF-020146 |  | Approved with Comments
266 | EL NOUBARYA | GLF11 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLF11-1200002 | B | Approved from CJV |  | Released to Systra | WF- 020020 |  | Approved with Comments
267 | EL NOUBARYA | GLF11 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLF11-1200001 | B | Approved from CJV |  | Released to Systra | WF- 020020 |  | Approved with Comments
268 | EL NOUBARYA | GLF11 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLF11-1200003 | B | Approved from CJV |  | Released to Systra | WF- 020020 |  | Approved with Comments
269 | EL NOUBARYA | GLF11 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLF11-1200003 | A | Approved from CJV |  | Released to Systra | 22316 |  | Approved with Comments
270 | EL NOUBARYA | GLF11 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLF11-1200004 | A | Approved from CJV |  | Released to Systra | 22302 |  | Approved with Comments
271 | EL NOUBARYA | GLF11 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLF11-1200001 | A | Under HNWL update | 2026-02-10
272 | EL NOUBARYA | GLF11 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLF11-1200002 | A | Under HNWL update | 2026-02-10
273 | EL NOUBARYA | GLF11 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLF11-1200003 | A | Under HNWL update | 2026-02-10
274 | EL NOUBARYA | GLF11 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLF11-1200002 | A | Under HNWL update | 2026-02-10
275 | EL NOUBARYA | GLF11 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLF11-1200003 | A | Under HNWL update | 2026-02-10
276 | EL NOUBARYA | GLF11 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLF11-1200001 | B | Approved from CJV |  | Released to Systra | 24029 |  | Under Systra Review
277 | EL NOUBARYA | GLF11 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLF11-1200002 | B | Approved from CJV |  | Released to Systra | 24029 |  | Under Systra Review
278 | EL NOUBARYA | GLF11 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLF11-1200003 | B | Approved from CJV |  | Released to Systra | 24029 |  | Under Systra Review
279 | EL NOUBARYA | GLF11 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLF11-1200002 | B | Approved from CJV |  | Released to Systra | 24029 |  | Under Systra Review
280 | EL NOUBARYA | GLF11 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLF11-1200003 | B | Approved from CJV |  | Released to Systra | 24030 |  | Under Systra Review
281 | EL SADAT | GLE09 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLE09-1200002 | A | Approved from CJV |  | Released to Systra | WF-019994 |  | Approved with Comments
282 | EL SADAT | GLE09 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLE09-1200001 | A | Approved from CJV |  | Released to Systra | WF-019994 |  | Approved with Comments
283 | EL SADAT | GLE09 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLE09-1200003 | A | Approved from CJV |  | Released to Systra | WF-019994 |  | Approved with Comments
284 | EL SADAT | GLE09 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLE09-1200002 | A | Approved from CJV |  | Released to Systra | WF-019995 |  | Approved with Comments
285 | EL SADAT | GLE09 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLE09-1200002 | A | Under HNWL update | 2026-02-08
286 | EL SADAT | GLE09 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLE09-1200001 | A | Under HNWL update | 2026-02-08
287 | EL SADAT | GLE09 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLE09-1200003 | A | Under HNWL update | 2026-02-08
288 | EL SADAT | GLE09 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLE09-1200002 | A | Under HNWL update | 2026-02-08
289 | EL SADAT | GLE09 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLE09-1200003 | A | Under HNWL update | 2026-02-08
| EL SADAT | GLE09 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLE09-1200004 | A
290 | EL SADAT | GLE09 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLE09-1200002 | A | Approved from CJV |  | Released to Systra | WF-020198 |  | Rejected
291 | EL SADAT | GLE09 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLE09-1200001 | A | Approved from CJV |  | Released to Systra | WF-020198 |  | Rejected
292 | EL SADAT | GLE09 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLE09-1200003 | A | Approved from CJV |  | Released to Systra | WF-020198 |  | Rejected
293 | EL SADAT | GLE09 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLE09-1200004 | A | Approved from CJV |  | Released to Systra | WF-020199 |  | Rejected
294 | EL SADAT | GLE09 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLE09-1200002 | A | Approved from CJV |  | Released to Systra | WF- 020016 | 2026-02-10 | Approved with Comments
295 | EL SADAT | GLE09 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLE09-1200001 | A | Approved from CJV |  | Released to Systra | WF- 020016 | 2026-02-10 | Approved with Comments
296 | EL SADAT | GLE09 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLE09-1200003 | A | Approved from CJV |  | Released to Systra | WF- 020016 | 2026-02-10 | Approved with Comments
297 | EL SADAT | GLE09 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLE09-1200003 | A | Approved from CJV |  | Released to Systra | WF- 020017 | 2026-02-02 | Rejected
298 | EL SADAT | GLE09 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLE09-1200004 | B | Approved from CJV |  | Released to Systra | 21683 |  | Rejected
299 | EL SADAT | GLE09 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLE09-1200001 | A | Under HNWL update
300 | EL SADAT | GLE09 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLE09-1200002 | A | Under HNWL update
301 | EL SADAT | GLE09 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLE09-1200003 | A | Under HNWL update
302 | EL SADAT | GLE09 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLE09-1200002 | A | Under HNWL update
303 | EL SADAT | GLE09 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLE09-1200003 | A | Under HNWL update
304 | EL SADAT | GLE09 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLE09-1200001 | A | Approved from CJV | 2026-02-13 | Released to Systra | 20821 |  | Approved with Comments
305 | EL SADAT | GLE09 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLE09-1200002 | A | Approved from CJV | 2026-02-13 | Released to Systra | 20821 |  | Approved with Comments
306 | EL SADAT | GLE09 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLE09-1200003 | A | Approved from CJV | 2026-02-13 | Released to Systra | 20821 |  | Approved with Comments
307 | EL SADAT | GLE09 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLE09-1200002 | A | Approved from CJV | 2026-02-13 | Released to Systra | 20821 |  | Approved with Comments
308 | EL SADAT | GLE09 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLE09-1200003 | A | Approved from CJV | 2026-02-13 | Released to Systra | 20741 |  | Approved with Comments
309 | El Ain ElSOKHNA | GLA01 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLA01-1200002 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
310 | El Ain ElSOKHNA | GLA01 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLA01-1200001 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
311 | El Ain ElSOKHNA | GLA01 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLA01-1200003 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
312 | El Ain ElSOKHNA | GLA01 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLA01-1200002 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
313 | El Ain ElSOKHNA | GLA01 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLA01-1200002 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
314 | El Ain ElSOKHNA | GLA01 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLA01-1200001 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
315 | El Ain ElSOKHNA | GLA01 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLA01-1200003 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
316 | El Ain ElSOKHNA | GLA01 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLA01-1200002 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
317 | El Ain ElSOKHNA | GLA01 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLA01-1200003 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
| El Ain ElSOKHNA | GLA01 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLA01-1200004 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
318 | El Ain ElSOKHNA | GLA01 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLA01-1200002 | A | Approved from CJV |  | Released to Systra | 24466 |  | Under Systra Review
319 | El Ain ElSOKHNA | GLA01 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLA01-1200001 | A | Approved from CJV |  | Released to Systra | 24466 |  | Under Systra Review
320 | El Ain ElSOKHNA | GLA01 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLA01-1200003 | A | Approved from CJV |  | Released to Systra | 24466 |  | Under Systra Review
321 | El Ain ElSOKHNA | GLA01 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLA01-1200004 | A | Approved from CJV |  | Released to Systra | 24468 |  | Under Systra Review
322 | El Ain ElSOKHNA | GLA01 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLA01-1200002 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
323 | El Ain ElSOKHNA | GLA01 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLA01-1200001 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
324 | El Ain ElSOKHNA | GLA01 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLA01-1200003 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
325 | El Ain ElSOKHNA | GLA01 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLA01-1200003 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
326 | El Ain ElSOKHNA | GLA01 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLA01-1200004 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
327 | El Ain ElSOKHNA | GLA01 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLA01-1200001 | A | Under CJV review
328 | El Ain ElSOKHNA | GLA01 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLA01-1200002 | A | Under CJV review
329 | El Ain ElSOKHNA | GLA01 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLA01-1200003 | A | Under CJV review
330 | El Ain ElSOKHNA | GLA01 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLA01-1200002 | A | Under CJV review
331 | El Ain ElSOKHNA | GLA01 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLA01-1200003 | A | Under CJV review
332 | El Ain ElSOKHNA | GLA01 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLA01-1200001 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
333 | El Ain ElSOKHNA | GLA01 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLA01-1200002 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
334 | El Ain ElSOKHNA | GLA01 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLA01-1200003 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
335 | El Ain ElSOKHNA | GLA01 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLA01-1200002 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
336 | El Ain ElSOKHNA | GLA01 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLA01-1200003 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
337 | 6TH OF OCTOBER | GLD07 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLD07-1200002 | A | Approved from CJV | 2026-02-10 | Under SMO Review | WF-025158
338 | 6TH OF OCTOBER | GLD07 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLD07-1200001 | A | Approved from CJV | 2026-02-10 | Under SMO Review | WF-025158
339 | 6TH OF OCTOBER | GLD07 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLD07-1200003 | A | Approved from CJV | 2026-02-10 | Under SMO Review | WF-025158
340 | 6TH OF OCTOBER | GLD07 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLD07-1200002 | A | Approved from CJV | 2026-02-10 | Under SMO Review | WF-025160
341 | 6TH OF OCTOBER | GLD07 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLD07-1200002 |  | Under HNWL update
342 | 6TH OF OCTOBER | GLD07 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLD07-1200001 |  | Under HNWL update
343 | 6TH OF OCTOBER | GLD07 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLD07-1200003 |  | Under HNWL update
344 | 6TH OF OCTOBER | GLD07 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLD07-1200002 |  | Under HNWL update
345 | 6TH OF OCTOBER | GLD07 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLD07-1200003 |  | Under HNWL update
| 6TH OF OCTOBER | GLD07 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLD07-1200004 |  | Under HNWL update
346 | 6TH OF OCTOBER | GLD07 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLD07-1200002 | A | Under HNWL update | 2026-02-10
347 | 6TH OF OCTOBER | GLD07 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLD07-1200001 | A | Under HNWL update | 2026-02-10
348 | 6TH OF OCTOBER | GLD07 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLD07-1200003 | A | Under HNWL update | 2026-02-10
349 | 6TH OF OCTOBER | GLD07 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLD07-1200004 | A | Under HNWL update | 2026-02-10
350 | 6TH OF OCTOBER | GLD07 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLD07-1200002 | A | Under HNWL update | 2026-02-10
351 | 6TH OF OCTOBER | GLD07 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLD07-1200001 | A | Under HNWL update | 2026-02-10
352 | 6TH OF OCTOBER | GLD07 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLD07-1200003 | A | Under HNWL update | 2026-02-10
353 | 6TH OF OCTOBER | GLD07 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLD07-1200003 | A | Under HNWL update | 2026-02-10
354 | 6TH OF OCTOBER | GLD07 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLD07-1200004
355 | 6TH OF OCTOBER | GLD07 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLD07-1200001
356 | 6TH OF OCTOBER | GLD07 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLD07-1200002
357 | 6TH OF OCTOBER | GLD07 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLD07-1200003
358 | 6TH OF OCTOBER | GLD07 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLD07-1200002
359 | 6TH OF OCTOBER | GLD07 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLD07-1200003
360 | 6TH OF OCTOBER | GLD07 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLD07-1200001 | A | Under HNWL update | 2026-02-10 | [5 empty] | Waiting SYS workshop
361 | 6TH OF OCTOBER | GLD07 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLD07-1200002 | A | Under HNWL update | 2026-02-10 | [5 empty] | Waiting SYS workshop
362 | 6TH OF OCTOBER | GLD07 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLD07-1200003 | A | Under HNWL update | 2026-02-10 | [5 empty] | Waiting SYS workshop
363 | 6TH OF OCTOBER | GLD07 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLD07-1200002 | A | Under HNWL update | 2026-02-10 | [5 empty] | Waiting SYS workshop
364 | 6TH OF OCTOBER | GLD07 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLD07-1200003 | A | Under HNWL update | 2026-02-10 | [5 empty] | Waiting SYS workshop
365 | SPHINX | GLE08 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLE08-1200002 | B | Approved from CJV |  | Released to Systra | 21274 |  | Approved with Comments
366 | SPHINX | GLE08 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLE08-1200001 | B | Approved from CJV |  | Released to Systra | 21274 |  | Approved with Comments
367 | SPHINX | GLE08 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLE08-1200003 | B | Approved from CJV |  | Released to Systra | 21274 |  | Approved with Comments
368 | SPHINX | GLE08 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLE08-1200002 | A | Approved from CJV |  | Released to Systra | 21273 |  | Approved with Comments
369 | SPHINX | GLE08 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLE08-1200002 | A | Approved from CJV | 2026-02-17 | Released to Systra | 24072 |  | Under Systra Review
370 | SPHINX | GLE08 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLE08-1200001 | A | Approved from CJV | 2026-02-17 | Released to Systra | 24072 |  | Under Systra Review
371 | SPHINX | GLE08 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLE08-1200003 | A | Approved from CJV | 2026-02-17 | Released to Systra | 24072 |  | Under Systra Review
372 | SPHINX | GLE08 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLE08-1200002 | A | Approved from CJV | 2026-02-17 | Released to Systra | 24072 |  | Under Systra Review
373 | SPHINX | GLE08 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLE08-1200003 | A | Approved from CJV | 2026-02-17 | Released to Systra | 24072 |  | Under Systra Review
| SPHINX | GLE08 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLE08-1200004 | A
374 | SPHINX | GLE08 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLE08-1200002 | A | Approved from CJV |  | Released to Systra | 21276 |  | Approved with Comments
375 | SPHINX | GLE08 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLE08-1200001 | A | Approved from CJV |  | Released to Systra | 21276 |  | Approved with Comments
376 | SPHINX | GLE08 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLE08-1200003 | A | Approved from CJV |  | Released to Systra | 21276 |  | Approved with Comments
377 | SPHINX | GLE08 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLE08-1200004 | A | Approved from CJV |  | Released to Systra | 21277 |  | Approved with Comments
378 | SPHINX | GLE08 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLE08-1200002 | A | Approved from CJV |  | Released to Systra | 20451 |  | Under Systra Review
379 | SPHINX | GLE08 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLE08-1200001 | A | Approved from CJV |  | Released to Systra | 20451 |  | Under Systra Review
380 | SPHINX | GLE08 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLE08-1200003 | A | Approved from CJV |  | Released to Systra | 20451 |  | Under Systra Review
381 | SPHINX | GLE08 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLE08-1200003 | A | Approved from CJV |  | Released to Systra | 20452 |  | Rejected
382 | SPHINX | GLE08 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLE08-1200004 | A | Approved from CJV |  | Released to Systra | 20453 |  | Rejected
383 | SPHINX | GLE08 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLE08-1200001 | A | Approved from CJV |  | Released to Systra | 21589 |  | Rejected
384 | SPHINX | GLE08 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLE08-1200002 | A | Approved from CJV |  | Released to Systra | 21589 |  | Rejected
385 | SPHINX | GLE08 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLE08-1200003 | A | Approved from CJV |  | Released to Systra | 21589 |  | Rejected
386 | SPHINX | GLE08 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLE08-1200002 | A | Approved from CJV |  | Released to Systra | 21590 |  | Rejected
387 | SPHINX | GLE08 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLE08-1200003 | A | Approved from CJV |  | Released to Systra | 21591 |  | Rejected
388 | SPHINX | GLE08 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLE08-1200001 | B | Approved from CJV | 2026-03-24 | Released to Systra | 24060 |  | Approved with Comments
389 | SPHINX | GLE08 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLE08-1200002 | B | Approved from CJV | 2026-03-24 | Released to Systra | 24060 |  | Approved with Comments
390 | SPHINX | GLE08 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLE08-1200003 | B | Approved from CJV | 2026-03-24 | Released to Systra | 24060 |  | Approved with Comments
391 | SPHINX | GLE08 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLE08-1200002 | B | Approved from CJV | 2026-03-24 | Released to Systra | 24060 |  | Approved with Comments
392 | SPHINX | GLE08 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLE08-1200003 | B | Approved from CJV | 2026-03-24 | Released to Systra | 24061 |  | Under Systra Review
393 | ALEXANDRIA |  | MCS | Equipment Layout Drawing | [6 empty] | 2026-03-24
394 | ALEXANDRIA |  | MCS | System Overall Architecture (SLD)
395 | ALEXANDRIA |  | MCS | Cable Routing drawing
396 | ALEXANDRIA |  | MCS | Cable SChedule
397 | ALEXANDRIA |  | PAS | Equipment Layout Drawing
398 | ALEXANDRIA |  | PAS | System Overall Architecture (SLD)
399 | ALEXANDRIA |  | PAS | Cable Routing drawing
400 | ALEXANDRIA |  | PAS | Acoustic Report
401 | ALEXANDRIA |  | PAS | Cable schedule
| ALEXANDRIA |  | PAS | Rack Layout
402 | ALEXANDRIA |  | PIS | Equipment Layout Drawing
403 | ALEXANDRIA |  | PIS | System Overall Architecture (SLD)
404 | ALEXANDRIA |  | PIS | Cable Routing drawing
405 | ALEXANDRIA |  | PIS | Cable SChedule
406 | ALEXANDRIA |  | ACS | Equipment Layout Drawing
407 | ALEXANDRIA |  | ACS | System Overall Architecture (SLD)
408 | ALEXANDRIA |  | ACS | Cable Routing drawing
409 | ALEXANDRIA |  | ACS | Cable SChedule
410 | ALEXANDRIA |  | ACS | Panel Arrangement
411 | ALEXANDRIA |  | UPS | Equipment Layout Drawing
412 | ALEXANDRIA |  | UPS | System Overall Architecture (SLD)
413 | ALEXANDRIA |  | UPS | Cable Routing drawing
414 | ALEXANDRIA |  | UPS | Cable SChedule
415 | ALEXANDRIA |  | UPS | Distribution Board loads schedule
416 | ALEXANDRIA |  | CCTV | System Overall Architecture (SLD)
417 | ALEXANDRIA |  | CCTV | System Equipment Layout
418 | ALEXANDRIA |  | CCTV | System Cable routing plan
419 | ALEXANDRIA |  | CCTV | Coverage Report / Field of View
420 | ALEXANDRIA |  | CCTV | Cable Schedule
421 | BORG ELARAB | GLG13 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLG13-1200002 | A | Approved from CJV |  | Released to Systra | 21453 |  | Approved with Comments
422 | BORG ELARAB | GLG13 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLG13-1200001 | A | Approved from CJV |  | Released to Systra | 21453 |  | Approved with Comments
423 | BORG ELARAB | GLG13 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLG13-1200003 | A | Approved from CJV |  | Released to Systra | 21453 |  | Approved with Comments
424 | BORG ELARAB | GLG13 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLG13-1200002 | A | Approved from CJV |  | Released to Systra | 21682 |  | Approved with Comments
425 | BORG ELARAB | GLG13 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLG13-1200002 | B | Approved from CJV |  | Released to Systra | WF-023700 |  | Approved with Comments
426 | BORG ELARAB | GLG13 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLG13-1200001 | B | Approved from CJV |  | Released to Systra | WF-023700 |  | Approved with Comments
427 | BORG ELARAB | GLG13 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLG13-1200003 | B | Approved from CJV |  | Released to Systra | WF-023700 |  | Approved with Comments
428 | BORG ELARAB | GLG13 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLG13-1200002 | B | Approved from CJV |  | Released to Systra | WF-023700 |  | Approved with Comments
429 | BORG ELARAB | GLG13 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLG13-1200003 | B | Approved from CJV |  | Released to Systra | WF-023703 |  | Approved with Comments
| BORG ELARAB | GLG13 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLG13-1200004 | A | Approved from CJV |  | Released to Systra | 22496 |  | Approved with Comments
430 | BORG ELARAB | GLG13 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLG13-1200002 | A | Approved from CJV |  | Released to Systra | 21551 |  | Approved with Comments
431 | BORG ELARAB | GLG13 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLG13-1200001 | A | Approved from CJV |  | Released to Systra | 21551 |  | Approved with Comments
432 | BORG ELARAB | GLG13 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLG13-1200003 | A | Approved from CJV |  | Released to Systra | 21551 |  | Approved with Comments
433 | BORG ELARAB | GLG13 | PIS | Cable SChedule | HSR-SOA-DES-TELPIS-GLG13-1200002 | A | Approved from CJV |  | Released to Systra | WF-021626 |  | Approved with Comments
434 | BORG ELARAB | GLG13 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLG13-1200002 | A | Approved from CJV |  | Released to Systra | 21392 |  | Approved with Comments
435 | BORG ELARAB | GLG13 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLG13-1200001 | A | Approved from CJV |  | Released to Systra | 21392 |  | Approved with Comments
436 | BORG ELARAB | GLG13 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLG13-1200003 | A | Approved from CJV |  | Released to Systra | 21392 |  | Approved with Comments
437 | BORG ELARAB | GLG13 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLG13-1200003 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
438 | BORG ELARAB | GLG13 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLG13-1200004 | A | Approved from CJV |  | Released to Systra | 24337 |  | Under Systra Review
439 | BORG ELARAB | GLG13 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLG13-1200001 | A | Under HNWL update | 2026-03-11
440 | BORG ELARAB | GLG13 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLG13-1200002 | A | Under HNWL update | 2026-03-11
441 | BORG ELARAB | GLG13 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLG13-1200003 | A | Under HNWL update | 2026-03-11
442 | BORG ELARAB | GLG13 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLG13-1200002 | A | Under HNWL update | 2026-03-11
443 | BORG ELARAB | GLG13 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLG13-1200003 | A | Under HNWL update | 2026-03-11
444 | BORG ELARAB | GLG13 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLG13-1200001 | A | Approved from CJV |  | Released to Systra | 24439 |  | Under Systra Review
445 | BORG ELARAB | GLG13 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLG13-1200002 | A | Approved from CJV |  | Released to Systra | 24439 |  | Under Systra Review
446 | BORG ELARAB | GLG13 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLG13-1200003 | A | Approved from CJV |  | Released to Systra | 24439 |  | Under Systra Review
447 | BORG ELARAB | GLG13 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLG13-1200002 | A | Approved from CJV |  | Released to Systra | 24439 |  | Under Systra Review
448 | BORG ELARAB | GLG13 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLG13-1200003 | A | Approved from CJV |  | Released to Systra | 24440 |  | Under Systra Review
449 | EL HAMMAM | GLG14 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLG14-1200002 |  | Approved from CJV |  | Released to Systra | 20999 |  | Approved with Comments
450 | EL HAMMAM | GLG14 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLG14-1200001 |  | Approved from CJV |  | Released to Systra | 20999 |  | Approved with Comments
451 | EL HAMMAM | GLG14 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLG14-1200003 |  | Approved from CJV |  | Released to Systra | 20999 |  | Approved with Comments
452 | EL HAMMAM | GLG14 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLG14-1200002 |  | Approved from CJV |  | Released to Systra | 21000 |  | Approved with Comments
453 | EL HAMMAM | GLG14 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLG14-1200002 |  | Approved from CJV |  | Released to Systra | 24066 |  | Under Systra Review
454 | EL HAMMAM | GLG14 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLG14-1200001 |  | Approved from CJV |  | Released to Systra | 24066 |  | Under Systra Review
455 | EL HAMMAM | GLG14 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLG14-1200003 |  | Approved from CJV |  | Released to Systra | 24066 |  | Under Systra Review
456 | EL HAMMAM | GLG14 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLG14-1200002 |  | Approved from CJV |  | Released to Systra | 24066 |  | Under Systra Review
457 | EL HAMMAM | GLG14 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLG14-1200003 |  | Approved from CJV |  | Released to Systra | 24064 |  | Under Systra Review
| EL HAMMAM | GLG14 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLG14-1200004 | A | Approved from CJV |  | Released to Systra | 22517 |  | Approved with Comments
458 | EL HAMMAM | GLG14 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLG14-1200002 |  | Approved from CJV |  | Released to Systra | 21445 |  | Approved with Comments
459 | EL HAMMAM | GLG14 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLG14-1200001 |  | Approved from CJV |  | Released to Systra | 21445 |  | Approved with Comments
460 | EL HAMMAM | GLG14 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLG14-1200003 |  | Approved from CJV |  | Released to Systra | 21445 |  | Approved with Comments
461 | EL HAMMAM | GLG14 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLG14-1200004 |  | Approved from CJV |  | Released to Systra | 21680 |  | Approved with Comments
462 | EL HAMMAM | GLG14 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLG14-1200002 |  | Approved from CJV |  | Released to Systra | 21441 |  | Approved with Comments
463 | EL HAMMAM | GLG14 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLG14-1200001 |  | Approved from CJV |  | Released to Systra | 21441 |  | Approved with Comments
464 | EL HAMMAM | GLG14 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLG14-1200003 |  | Approved from CJV |  | Released to Systra | 21441 |  | Approved with Comments
465 | EL HAMMAM | GLG14 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLG14-1200003 |  | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
466 | EL HAMMAM | GLG14 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLG14-1200004 |  | Approved from CJV |  | Released to Systra | 24962 |  | Under Systra Review
467 | EL HAMMAM | GLG14 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLG14-1200001 | A | Under HNWL update | 2026-03-26
468 | EL HAMMAM | GLG14 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLG14-1200002 | A | Under HNWL update | 2026-03-26
469 | EL HAMMAM | GLG14 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLG14-1200003 | A | Under HNWL update | 2026-03-26
470 | EL HAMMAM | GLG14 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLG14-1200002 | A | Under HNWL update | 2026-03-26
471 | EL HAMMAM | GLG14 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLG14-1200003 | A | Under HNWL update | 2026-03-26
472 | EL HAMMAM | GLG14 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLG14-1200001 | B | Approved from CJV | 2026-03-24 | Released to Systra | 24092 |  | Under Systra Review
473 | EL HAMMAM | GLG14 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLG14-1200002 | B | Approved from CJV | 2026-03-24 | Released to Systra | 24092 |  | Under Systra Review
474 | EL HAMMAM | GLG14 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLG14-1200003 | B | Approved from CJV | 2026-03-24 | Released to Systra | 24092 |  | Under Systra Review
475 | EL HAMMAM | GLG14 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLG14-1200002 | B | Approved from CJV | 2026-03-24 | Released to Systra | 24092 |  | Under Systra Review
476 | EL HAMMAM | GLG14 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLG14-1200003 | B | Approved from CJV | 2026-03-24 | Released to Systra | 24094 |  | Under Systra Review
477 | EL DABAA | GLI17 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLI17-1200002 | B | Approved from CJV |  | Released to Systra | WF-023146 | 2025-08-26 | Approved with Comments
478 | EL DABAA | GLI17 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLI17-1200001 | B | Approved from CJV |  | Released to Systra | WF-023146 | 2025-08-26 | Approved with Comments
479 | EL DABAA | GLI17 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLI17-1200003 | B | Approved from CJV |  | Released to Systra | WF-023146 | 2025-08-26 | Approved with Comments
480 | EL DABAA | GLI17 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLI17-1200002 | B | Approved from CJV |  | Released to Systra | WF-023147 |  | Approved with Comments
481 | EL DABAA | GLI17 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLI17-1200002 | A | Approved from CJV | 2026-02-25 | Released to Systra | WF-024068 |  | Under Systra Review
482 | EL DABAA | GLI17 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLI17-1200001 | A | Approved from CJV | 2026-02-25 | Released to Systra | WF-024068 |  | Under Systra Review
483 | EL DABAA | GLI17 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLI17-1200003 | A | Approved from CJV | 2026-02-25 | Released to Systra | WF-024068 |  | Under Systra Review
484 | EL DABAA | GLI17 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLI17-1200002 | A | Approved from CJV | 2026-02-25 | Released to Systra | WF-024068 |  | Under Systra Review
485 | EL DABAA | GLI17 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLI17-1200003 | A | Approved from CJV | 2026-02-25 | Released to Systra | WF-024069 |  | Under Systra Review
| EL DABAA | GLI17 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLI17-1200004 | A | Approved from CJV |  | Released to Systra | WF-023032 |  | Approved with Comments
486 | EL DABAA | GLI17 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLI17-1200002 | B | Approved from CJV |  | Released to Systra | 20607 | 2025-09-18 | Approved with Comments
487 | EL DABAA | GLI17 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLI17-1200001 | B | Approved from CJV |  | Released to Systra | 20607 | 2025-09-18 | Approved with Comments
488 | EL DABAA | GLI17 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLI17-1200003 | B | Approved from CJV |  | Released to Systra | 20607 | 2025-09-18 | Approved with Comments
489 | EL DABAA | GLI17 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLI17-1200004 | A | Approved from CJV |  | Released to Systra | 20608 |  | Approved with Comments
490 | EL DABAA | GLI17 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLI17-1200002 | A | Approved from CJV |  | Released to Systra | WF-020612 |  | Approved with Comments
491 | EL DABAA | GLI17 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLI17-1200001 | A | Approved from CJV |  | Released to Systra | WF-020612 |  | Approved with Comments
492 | EL DABAA | GLI17 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLI17-1200003 | A | Approved from CJV |  | Released to Systra | WF-020612 |  | Approved with Comments
493 | EL DABAA | GLI17 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLI17-1200003 | A | Approved from CJV |  | Released to Systra | WF-020613 |  | Rejected
494 | EL DABAA | GLI17 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLI17-1200004 | A | Under HNWL update |  | Returned from SMO | WF-020614
495 | EL DABAA | GLI17 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLI17-1200001 | A | Under HNWL update | 2026-03-09
496 | EL DABAA | GLI17 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLI17-1200002 | A | Under HNWL update | 2026-03-09
497 | EL DABAA | GLI17 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLI17-1200003 | A | Under HNWL update | 2026-03-09
498 | EL DABAA | GLI17 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLI17-1200002 | A | Under HNWL update | 2026-03-09
499 | EL DABAA | GLI17 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLI17-1200003 | A | Under HNWL update | 2026-03-09
500 | EL DABAA | GLI17 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLI17-1200001 | A | Approved from CJV | 2026-02-25 | Released to Systra | 24322 |  | Under Systra Review
501 | EL DABAA | GLI17 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLI17-1200002 | A | Approved from CJV | 2026-02-25 | Released to Systra | 24322 |  | Under Systra Review
502 | EL DABAA | GLI17 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLI17-1200003 | A | Approved from CJV | 2026-02-25 | Released to Systra | 24322 |  | Under Systra Review
503 | EL DABAA | GLI17 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLI17-1200002 | A | Approved from CJV | 2026-02-25 | Released to Systra | 24322 |  | Under Systra Review
504 | EL DABAA | GLI17 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLI17-1200003 | A | Approved from CJV | 2026-02-25 | Released to Systra | 24323 |  | Under Systra Review
505 | AlAMRIA |  | MCS | Equipment Layout Drawing
506 | AlAMRIA |  | MCS | System Overall Architecture (SLD)
507 | AlAMRIA |  | MCS | Cable Routing drawing
508 | AlAMRIA |  | MCS | Cable SChedule
509 | AlAMRIA |  | PAS | Equipment Layout Drawing
510 | AlAMRIA |  | PAS | System Overall Architecture (SLD)
511 | AlAMRIA |  | PAS | Cable Routing drawing
512 | AlAMRIA |  | PAS | Acoustic Report
513 | AlAMRIA |  | PAS | Cable schedule
| AlAMRIA |  | PAS | Rack Layout
514 | AlAMRIA |  | PIS | Equipment Layout Drawing
515 | AlAMRIA |  | PIS | System Overall Architecture (SLD)
516 | AlAMRIA |  | PIS | Cable Routing drawing
517 | AlAMRIA |  | PIS | Cable SChedule
518 | AlAMRIA |  | ACS | Equipment Layout Drawing
519 | AlAMRIA |  | ACS | System Overall Architecture (SLD)
520 | AlAMRIA |  | ACS | Cable Routing drawing
521 | AlAMRIA |  | ACS | Cable SChedule
522 | AlAMRIA |  | ACS | Panel Arrangement
523 | AlAMRIA |  | UPS | Equipment Layout Drawing
524 | AlAMRIA |  | UPS | System Overall Architecture (SLD)
525 | AlAMRIA |  | UPS | Cable Routing drawing
526 | AlAMRIA |  | UPS | Cable SChedule
527 | AlAMRIA |  | UPS | Distribution Board loads schedule
528 | AlAMRIA |  | CCTV | System Overall Architecture (SLD)
529 | AlAMRIA |  | CCTV | System Equipment Layout
530 | AlAMRIA |  | CCTV | System Cable routing plan
531 | AlAMRIA |  | CCTV | Coverage Report / Field of View
532 | AlAMRIA |  | CCTV | Cable Schedule
533 | MARSA MATROUH | GLM21 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLM21-1200002 |  | Approved from CJV |  | Released to Systra | 21154 |  | Under Systra Review
534 | MARSA MATROUH | GLM21 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLM21-1200001 |  | Approved from CJV |  | Released to Systra | 21154 |  | Under Systra Review
535 | MARSA MATROUH | GLM21 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLM21-1200003 |  | Approved from CJV |  | Released to Systra | 21154 |  | Under Systra Review
536 | MARSA MATROUH | GLM21 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLM21-1200002 |  | Approved from CJV |  | Released to Systra | 21153 |  | Under Systra Review
537 | MARSA MATROUH | GLM21 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLM21-1200002 |  | Approved from CJV |  | Released to Systra | 21450 |  | Approved with Comments
538 | MARSA MATROUH | GLM21 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLM21-1200001 |  | Approved from CJV |  | Released to Systra | 21450 |  | Approved with Comments
539 | MARSA MATROUH | GLM21 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLM21-1200003 |  | Approved from CJV |  | Released to Systra | 21450 |  | Approved with Comments
540 | MARSA MATROUH | GLM21 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLM21-1200002 |  | Approved from CJV |  | Released to Systra | 21450 |  | Approved with Comments
541 | MARSA MATROUH | GLM21 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLM21-1200003 |  | Approved from CJV |  | Released to Systra | 21458 |  | Approved with Comments
| MARSA MATROUH | GLM21 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLM21-1200004 | A | Approved from CJV |  | Released to Systra | 22927 |  | Approved with Comments
542 | MARSA MATROUH | GLM21 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLM21-1200002 |  | Approved from CJV |  | Released to Systra | WF-021266 |  | Under Systra Review
543 | MARSA MATROUH | GLM21 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLM21-1200001 |  | Approved from CJV |  | Released to Systra | WF-021266 |  | Under Systra Review
544 | MARSA MATROUH | GLM21 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLM21-1200003 |  | Approved from CJV |  | Released to Systra | WF-021266 |  | Under Systra Review
545 | MARSA MATROUH | GLM21 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLM21-1200004 |  | Approved from CJV |  | Released to Systra | 21263 |  | Under Systra Review
546 | MARSA MATROUH | GLM21 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLM21-1200002 |  | Approved from CJV |  | Released to Systra | 21387 |  | Approved with Comments
547 | MARSA MATROUH | GLM21 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLM21-1200001 |  | Approved from CJV |  | Released to Systra | 21387 |  | Approved with Comments
548 | MARSA MATROUH | GLM21 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLM21-1200003 |  | Approved from CJV |  | Released to Systra | 21387 |  | Approved with Comments
549 | MARSA MATROUH | GLM21 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLM21-1200003 |  | Approved from CJV |  | Released to Systra | WF-023337 |  | Under Systra Review
550 | MARSA MATROUH | GLM21 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLM21-1200004 | B | Approved from CJV |  | Released to Systra | WF-024158 |  | Under Systra Review
551 | MARSA MATROUH | GLM21 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLM21-1200001 | A | Under HNWL update | 2026-03-29
552 | MARSA MATROUH | GLM21 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLM21-1200002 | A | Under HNWL update | 2026-03-29
553 | MARSA MATROUH | GLM21 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLM21-1200003 | A | Under HNWL update | 2026-03-29
554 | MARSA MATROUH | GLM21 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLM21-1200002 | A | Under HNWL update | 2026-03-29
555 | MARSA MATROUH | GLM21 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLM21-1200003 | A | Under HNWL update | 2026-03-29
556 | MARSA MATROUH | GLM21 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLM21-1200001 | A | Approved from CJV | 2026-03-24 | Released to Systra | WF-021431 |  | Approved with Comments
557 | MARSA MATROUH | GLM21 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLM21-1200002 | A | Approved from CJV | 2026-03-24 | Released to Systra | WF-021431 |  | Approved with Comments
558 | MARSA MATROUH | GLM21 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLM21-1200003 | A | Approved from CJV | 2026-03-24 | Released to Systra | WF-021431 |  | Approved with Comments
559 | MARSA MATROUH | GLM21 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLM21-1200002 | A | Approved from CJV | 2026-03-24 | Released to Systra | WF-021431 |  | Approved with Comments
560 | MARSA MATROUH | GLM21 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLM21-1200003 | A | Approved from CJV | 2026-03-24 | Released to Systra | WF-021432 |  | Approved with Comments
561 | Army Staduim Station | GLN12 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLN12-1200002 | A | Approved from CJV |  | Released to Systra | 21718 |  | Approved with Comments
562 | Army Staduim Station | GLN12 | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLN12-1200001 | A | Approved from CJV |  | Released to Systra | 21718 |  | Approved with Comments
563 | Army Staduim Station | GLN12 | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLN12-1200003 | A | Approved from CJV |  | Released to Systra | 21718 |  | Approved with Comments
564 | Army Staduim Station | GLN12 | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLN12-1200002 | A | Approved from CJV |  | Released to Systra | 21719 |  | Approved with Comments
565 | Army Staduim Station | GLN12 | PAS | Equipment Layout Drawing | HSR-SOA-DRW-TELPAS-GLN12-1200002 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
566 | Army Staduim Station | GLN12 | PAS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPAS-GLN12-1200001 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
567 | Army Staduim Station | GLN12 | PAS | Cable Routing drawing | HSR-SOA-DRW-TELPAS-GLN12-1200003 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
568 | Army Staduim Station | GLN12 | PAS | Acoustic Report | HSR-SOA-DES-TELPAS-GLN12-1200002 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
569 | Army Staduim Station | GLN12 | PAS | Cable schedule | HSR-SOA-DES-TELPAS-GLN12-1200003 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
| Army Staduim Station | GLN12 | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLN12-1200004 | A | Approved from CJV |  | Released to Systra | WF-022928 |  | Approved with Comments
570 | Army Staduim Station | GLN12 | PIS | Equipment Layout Drawing | HSR-SOA-DRW-TELPIS-GLN12-1200002 | A | Approved from CJV | 2026-04-20 | Released to Systra | 21970 |  | Approved with Comments
571 | Army Staduim Station | GLN12 | PIS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELPIS-GLN12-1200001 | A | Approved from CJV | 2026-04-20 | Released to Systra | 21970 |  | Approved with Comments
572 | Army Staduim Station | GLN12 | PIS | Cable Routing drawing | HSR-SOA-DRW-TELPIS-GLN12-1200003 | A | Approved from CJV | 2026-04-20 | Released to Systra | 21970 |  | Approved with Comments
573 | Army Staduim Station | GLN12 | PIS | Cable SChedule | HSR-SOA-DRW-TELPIS-GLN12-1200004 | A | Approved from CJV | 2026-04-20 | Released to Systra | 21971 |  | Approved with Comments
574 | Army Staduim Station | GLN12 | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLN12-1200002 | A | Approved from CJV |  | Released to Systra | WF-022094 |  | Approved with Comments
575 | Army Staduim Station | GLN12 | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLN12-1200001 | A | Approved from CJV |  | Released to Systra | WF-022094 |  | Approved with Comments
576 | Army Staduim Station | GLN12 | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLN12-1200003 | A | Approved from CJV |  | Released to Systra | WF-022094 |  | Approved with Comments
577 | Army Staduim Station | GLN12 | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLN12-1200003 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
578 | Army Staduim Station | GLN12 | ACS | Panel Arrangement | HSR-SOA-DRW-TELACS-GLN12-1200004 | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
579 | Army Staduim Station | GLN12 | UPS | Equipment Layout Drawing | HSR-SOA-DRW-TELUPS-GLN12-1200001 | A | Under HNWL update | 2026-04-06
580 | Army Staduim Station | GLN12 | UPS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELUPS-GLN12-1200002 | A | Under HNWL update | 2026-04-06
581 | Army Staduim Station | GLN12 | UPS | Cable Routing drawing | HSR-SOA-DRW-TELUPS-GLN12-1200003 | A | Under HNWL update | 2026-04-06
582 | Army Staduim Station | GLN12 | UPS | Cable SChedule | HSR-SOA-DES-TELUPS-GLN12-1200002 | A | Under HNWL update | 2026-04-06
583 | Army Staduim Station | GLN12 | UPS | Distribution Board loads schedule | HSR-SOA-DES-TELUPS-GLN12-1200003 | A | Under HNWL update | 2026-04-06
584 | Army Staduim Station | GLN12 | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLN12-1200001 | A | Approved from CJV | 2026-04-09 | Released to Systra |  |  | Under Systra Review
585 | Army Staduim Station | GLN12 | CCTV | System Equipment Layout | HSR-SOA-DRW-TELCCTV-GLN12-1200002 | A | Approved from CJV | 2026-04-09 | Released to Systra |  |  | Under Systra Review
586 | Army Staduim Station | GLN12 | CCTV | System Cable routing plan | HSR-SOA-DRW-TELCCTV-GLN12-1200003 | A | Approved from CJV | 2026-04-09 | Released to Systra |  |  | Under Systra Review
587 | Army Staduim Station | GLN12 | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLN12-1200002 | A | Approved from CJV | 2026-04-09 | Released to Systra |  |  | Under Systra Review
588 | Army Staduim Station | GLN12 | CCTV | Cable Schedule | HSR-SOA-DES-TELCCTV-GLN12-1200003 | A | Approved from CJV | 2026-04-09 | Released to Systra |  |  | Under Systra Review
Documents Status
[15 empty] | Total Number of Documents | 609
[15 empty] | Total Number of submitted from HNWLdoumcnts | 538
[15 empty] | Total Number of not submitted from HNWL documents | 71
[15 empty] | Under HNWL update | 98
[15 empty] | Under CJV Review | 6
[15 empty] | Under Safety Review | 0
[15 empty] | Under SMO Review | 8
[15 empty] | Released to Systra | 427
[15 empty] | Under Systra Review | 153
[15 empty] | Approved with Comments | 253
[15 empty] | Rejected | 21

## ELV DD (Depot)
Cutoff date 02-09-2026
[5 empty] | Internal Review |  | SMO Review |  |  | Systra Review
Building NAME | TEL Sub-Systems | Document Title | Document No. | Rev. | Status With Honeywell | Status Date | Document through WF Status | WF no. | Date | Status with Systra | Status Date | REASONS OF RETURN | Comment
MANUAL WASH | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLCDEPWB-1200002 | B | Approved from CJV |  | Released to Systra | WF-21744 |  | Approved With Comments
MANUAL WASH | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLCDEPWB-1200001 | B | Approved from CJV |  | Released to Systra | WF-21744 |  | Approved With Comments
MANUAL WASH | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLCDEPWB-1200003 | B | Approved from CJV |  | Released to Systra | WF-21744 |  | Approved With Comments
MANUAL WASH | MCS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | 18597 |  | Approved With Comments
MANUAL WASH | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLCDEPWB-1200001 | A | Approved from CJV |  | Released to Systra | WF-018659 |  | Approved With Comments | 2026-03-10
MANUAL WASH | ACS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-018659 |  | Approved With Comments | 2026-03-10
MANUAL WASH | ACS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | WF-018659 |  | Approved With Comments | 2026-03-10
MANUAL WASH | ACS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | WF-018657 |  | Approved With Comments | 2026-03-10
MANUAL WASH | ACS | Panel Arrangement and Wiring Details |  | A | Approved from CJV |  | Released to Systra |  |  | Approved With Comments
MANUAL WASH | CCTV | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 21960 |  | Approved With Comments
MANUAL WASH | CCTV | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 21960 |  | Approved With Comments
MANUAL WASH | CCTV | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 21960 |  | Approved With Comments
MANUAL WASH | CCTV | FOV |  | A | Approved from CJV |  | Released to Systra | 21960 |  | Approved With Comments
MANUAL WASH | CCTV | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | 21962 |  | Approved With Comments
WPMS | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLCDEPWP-1200002 | A | Approved from CJV |  | Released to Systra | 22003 |  | Approved With Comments
WPMS | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLCDEPWP-1200001 | A | Approved from CJV |  | Released to Systra | 22003 |  | Approved With Comments
WPMS | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLCDEPWP-1200003 | A | Approved from CJV |  | Released to Systra | 22003 |  | Approved With Comments
WPMS | MCS | Cable SChedule |  | A | Approved from CJV |  | Under SMO Review | 22004 |  | Approved With Comments
WPMS | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLCDEPWP-1200002 | A | Approved from CJV |  | Released to Systra | WF-018356 |  | Approved with Comments
WPMS | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLCDEPWP-1200001 | A | Approved from CJV |  | Released to Systra | WF-018356 |  | Approved with Comments
WPMS | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLCDEPWP-1200003 | A | Approved from CJV |  | Released to Systra | WF-018356 |  | Approved with Comments
WPMS | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLCDEPWP-1200002 | A | Approved from CJV |  | Released to Systra | WF-018357 |  | Approved with Comments
WPMS | ACS | Panel Arrangement and Wiring Details | HSR-SOA-DRW-TELACS-GLCDEPWP-1200004 | A | Approved from CJV |  | Released to Systra | WF-023266 |  | Rejected
WPMS | CCTV | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra |  |  | Approved with Comments
WPMS | CCTV | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra |  |  | Approved with Comments
WPMS | CCTV | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra |  |  | Approved with Comments
WPMS | CCTV | FOV |  | A | Approved from CJV |  | Released to Systra |  |  | Approved with Comments
WPMS | CCTV | Cable SChedule |  | A | Approved from CJV |  | Released to Systra |  |  | Under Systra Review
MAIN OCS SWITCHING HUB | MCS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-018603 |  | Approved with Comments
MAIN OCS SWITCHING HUB | MCS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-018603 |  | Approved with Comments
MAIN OCS SWITCHING HUB | MCS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | WF-018603 |  | Approved with Comments
MAIN OCS SWITCHING HUB | MCS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | WF-018601 |  | Approved with Comments
MAIN OCS SWITCHING HUB | ACS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-018675 |  | Approved with Comments
MAIN OCS SWITCHING HUB | ACS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-018675 |  | Approved with Comments
MAIN OCS SWITCHING HUB | ACS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | WF-018675 |  | Approved with Comments
MAIN OCS SWITCHING HUB | ACS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | WF-018673 |  | Approved with Comments
MAIN OCS SWITCHING HUB | ACS | Panel Arrangement and Wiring Details |  | A | Approved from CJV |  | Released to Systra | 21998 |  | Rejected
MAIN OCS SWITCHING HUB | CCTV | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-022149 |  | Approved with Comments
MAIN OCS SWITCHING HUB | CCTV | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-022149 |  | Approved with Comments
MAIN OCS SWITCHING HUB | CCTV | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | WF-022149 |  | Approved with Comments
MAIN OCS SWITCHING HUB | CCTV | FOV |  | A | Approved from CJV |  | Released to Systra | WF-022149 |  | Approved with Comments
MAIN OCS SWITCHING HUB | CCTV | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | WF-022150 |  | Approved with Comments
OCS SECTIONING HUB | MCS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-019014 |  | Approved with Comments
OCS SECTIONING HUB | MCS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-019014 |  | Approved with Comments
OCS SECTIONING HUB | MCS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | WF-019014 |  | Approved with Comments
OCS SECTIONING HUB | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLCDEPOCS2-1200001 | A | Approved from CJV |  | Released to Systra | WF-019015 |  | Approved with Comments
OCS SECTIONING HUB | ACS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-019220 |  | Approved with Comments
OCS SECTIONING HUB | ACS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-019220 |  | Approved with Comments
OCS SECTIONING HUB | ACS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | WF-019220 |  | Approved with Comments
OCS SECTIONING HUB | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLCDEPOCS2-1200001 | A | Approved from CJV |  | Released to Systra | WF-019218 |  | Approved with Comments
OCS SECTIONING HUB | ACS | Panel Arrangement and Wiring Details |  | A | Approved from CJV |  | Released to Systra | WF-019219 |  | Rejected
OCS SECTIONING HUB | CCTV | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 21979 |  | Approved with Comments
OCS SECTIONING HUB | CCTV | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 21979 |  | Approved with Comments
OCS SECTIONING HUB | CCTV | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 21979 |  | Approved with Comments
OCS SECTIONING HUB | CCTV | FOV |  | A | Approved from CJV |  | Released to Systra | 21979 |  | Approved with Comments
OCS SECTIONING HUB | CCTV | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | 21980 |  | Approved with Comments
STABLING YARD 1 | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLCDEPSY1-1200001 | A | Approved from CJV |  | Released to Systra | WF- 019817 |  | Approved with Comments
STABLING YARD 1 | MCS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF- 019817 |  | Approved with Comments
STABLING YARD 1 | MCS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | WF- 019817 |  | Approved with Comments
STABLING YARD 1 | MCS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | WF- 019816 |  | Approved with Comments
STABLING YARD 1 | CCTV | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 22177 |  | Approved with Comments
STABLING YARD 1 | CCTV | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 22177 |  | Approved with Comments
STABLING YARD 1 | CCTV | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 22177 |  | Approved with Comments
STABLING YARD 1 | CCTV | FOV |  | A | Approved from CJV |  | Released to Systra | 22177 |  | Approved with Comments
STABLING YARD 1 | CCTV | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | 22178 |  | Approved with Comments
STABLING YARD 1 | PAS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 20977 |  | Rejected
STABLING YARD 1 | PAS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 20977 |  | Rejected
STABLING YARD 1 | PAS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 20977 |  | Rejected
STABLING YARD 1 | PAS | acoustec report |  | A | Approved from CJV |  | Released to Systra | 20977 |  | Rejected
STABLING YARD 1 | PAS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | 20978 |  | Rejected
STABLING YARD 1 | UPS | Equipment Layout Drawing |  | A | Under HNWL update | 2026-03-10
STABLING YARD 1 | UPS | System Overall Architecture (SLD) |  | A | Under HNWL update | 2026-03-11
STABLING YARD 1 | UPS | Cable Routing drawing |  | A | Under HNWL update | 2026-03-12
STABLING YARD 1 | UPS | Cable SChedule |  | A | Under HNWL update | 2026-03-13
STABLING YARD 1 | UPS | PANEL BOARD |  | A | Under HNWL update | 2026-03-14
STABLING YARD 2 | MCS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF- 020040 |  | Approved with comments
STABLING YARD 2 | MCS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF- 020040 |  | Approved with comments
STABLING YARD 2 | MCS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | WF- 020040 |  | Approved with comments
STABLING YARD 2 | MCS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | WF- 020057 |  | Approved with comments
STABLING YARD 2 | CCTV | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-021963 |  | Approved with comments
STABLING YARD 2 | CCTV | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-021963 |  | Approved with comments
STABLING YARD 2 | CCTV | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | WF-021963 |  | Approved with comments
STABLING YARD 2 | CCTV | FOV |  | A | Approved from CJV |  | Released to Systra | WF-021963 |  | Approved with comments
STABLING YARD 2 | CCTV | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | WF-021964 |  | Approved with comments
STABLING YARD 2 | PAS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 21474 |  | Rejected
STABLING YARD 2 | PAS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 21474 |  | Rejected
STABLING YARD 2 | PAS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 21474 |  | Rejected
STABLING YARD 2 | PAS | acoustec report |  | A | Approved from CJV |  | Released to Systra | 21474 |  | Rejected
STABLING YARD 2 | PAS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | 21652 |  | Rejected
REL WORKSHOP | MCS | Equipment Layout Drawing |  | A | Approved from CJV | 2026-02-19 | Released to Systra | WF-020531 |  | Approved with comments
REL WORKSHOP | MCS | System Overall Architecture (SLD) |  | A | Approved from CJV | 2026-02-19 | Released to Systra | WF-020531 |  | Approved with comments
REL WORKSHOP | MCS | Cable Routing drawing |  | A | Approved from CJV | 2026-02-19 | Released to Systra | WF-020531 |  | Approved with comments
REL WORKSHOP | MCS | Cable SChedule |  | A | Approved from CJV | 2026-02-19 | Released to Systra | WF-020532 |  | Approved with comments
REL WORKSHOP | CCTV | Equipment Layout Drawing |  | A | Approved from CJV | 2026-02-19 | Released to Systra | 24299 |  | Under Systra Review
REL WORKSHOP | CCTV | System Overall Architecture (SLD) |  | A | Approved from CJV | 2026-02-19 | Released to Systra | 24299 |  | Under Systra Review
REL WORKSHOP | CCTV | Cable Routing drawing |  | A | Approved from CJV | 2026-02-19 | Released to Systra | 24299 |  | Under Systra Review
REL WORKSHOP | CCTV | FOV |  | A | Approved from CJV | 2026-02-19 | Released to Systra | 24299 |  | Under Systra Review
REL WORKSHOP | CCTV | Cable SChedule |  | A | Approved from CJV | 2026-02-19 | Released to Systra | 24301 |  | Under Systra Review
REL WORKSHOP | PAS | Equipment Layout Drawing |  | A | Approved from CJV | 2026-03-04 | Released to Systra | WF-020890 |  | Under Systra Review
REL WORKSHOP | PAS | System Overall Architecture (SLD) |  | A | Approved from CJV | 2026-03-04 | Released to Systra | WF-020890 |  | Under Systra Review
REL WORKSHOP | PAS | Cable Routing drawing |  | A | Approved from CJV | 2026-03-04 | Released to Systra | WF-020890 |  | Under Systra Review
REL WORKSHOP | PAS | acoustec report |  | A | Approved from CJV | 2026-03-04 | Released to Systra | WF-020890 |  | Under Systra Review
REL WORKSHOP | PAS | Cable SChedule |  | A | Approved from CJV | 2026-03-04 | Released to Systra | WF-020892 |  | Under Systra Review
REL WORKSHOP | PAS | Rack Layout | HSR-SOA-DRW-TELPAS-GLCDEPRELW-1200004 | A | Approved from CJV |  | Released to Systra | WF-023145 |  | Under Systra Review
REL WORKSHOP | UPS | Equipment Layout Drawing |  | A | Under HNWL update | 2026-03-29
REL WORKSHOP | UPS | System Overall Architecture (SLD) |  | A | Under HNWL update | 2026-03-29
REL WORKSHOP | UPS | Cable Routing drawing |  | A | Under HNWL update | 2026-03-29
REL WORKSHOP | UPS | Cable SChedule |  | A | Under HNWL update | 2026-03-29
REL WORKSHOP | UPS | PANEL BOARD |  | A | Under HNWL update | 2026-03-29
REL WORKSHOP | ACS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 24251 |  | Under Systra Review
REL WORKSHOP | ACS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 24251 |  | Under Systra Review
REL WORKSHOP | ACS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 24251 |  | Under Systra Review
REL WORKSHOP | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLCDEPOCS2-1200001 | A | Approved from CJV |  | Released to Systra | 21603 |  | Rejected
REL WORKSHOP | ACS | Panel Arrangement and Wiring Details | HSR-SOA-DRW-TELACS-GLCDEPRELW-1200004 | B | Approved from CJV |  | Released to Systra | WF-023752 |  | Under Systra Review
Automatic Train Wash Building | MCS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 20962 |  | Approved with Comments
Automatic Train Wash Building | MCS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 20962 |  | Approved with Comments
Automatic Train Wash Building | MCS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 20962 |  | Approved with Comments
Automatic Train Wash Building | MCS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | 20964 |  | Approved with Comments
Automatic Train Wash Building | CCTV | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-022066 |  | Approved with Comments
Automatic Train Wash Building | CCTV | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-022066 |  | Approved with Comments
Automatic Train Wash Building | CCTV | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | WF-022066 |  | Approved with Comments
Automatic Train Wash Building | CCTV | FOV |  | A | Approved from CJV |  | Released to Systra | WF-022066 |  | Approved with Comments
Automatic Train Wash Building | CCTV | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | WF-022067 |  | Rejected
Automatic Train Wash Building | UPS | Equipment Layout Drawing |  | A | Under HNWL update | 2026-03-02
Automatic Train Wash Building | UPS | System Overall Architecture (SLD) |  | A | Under HNWL update | 2026-03-02
Automatic Train Wash Building | UPS | Cable Routing drawing |  | A | Under HNWL update | 2026-03-02
Automatic Train Wash Building | UPS | Cable SChedule |  | A | Under HNWL update | 2026-03-02
Automatic Train Wash Building | UPS | PANEL BOARD |  | A | Under HNWL update | 2026-03-02
Automatic Train Wash Building | ACS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 22207 |  | Under Systra Review
Automatic Train Wash Building | ACS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 22207 |  | Under Systra Review
Automatic Train Wash Building | ACS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 22207 |  | Under Systra Review
Automatic Train Wash Building | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLCDEPOCS2-1200001 | A | Approved from CJV |  | Released to Systra | 22209 |  | Under Systra Review
Automatic Train Wash Building | ACS | Panel Arrangement and Wiring Details |  | A | Approved from CJV |  | Released to Systra | 22210 |  | Under Systra Review
Fresh water Building | MCS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 20697 |  | Approved with Comments
Fresh water Building | MCS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 20697 |  | Approved with Comments
Fresh water Building | MCS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 20697 |  | Approved with Comments
Fresh water Building | MCS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | 20698 |  | Approved with Comments
Fresh water Building | CCTV | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 21281 |  | Approved with Comments
Fresh water Building | CCTV | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 21281 |  | Approved with Comments
Fresh water Building | CCTV | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 21281 |  | Approved with Comments
Fresh water Building | CCTV | FOV |  | A | Approved from CJV |  | Released to Systra | 21281 |  | Approved with Comments
Fresh water Building | CCTV | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | 22008 |  | Approved with Comments
Fresh water Building | UPS | Equipment Layout Drawing |  | A | Under HNWL update | 2026-03-10
Fresh water Building | UPS | System Overall Architecture (SLD) |  | A | Under HNWL update | 2026-03-10
Fresh water Building | UPS | Cable Routing drawing |  | A | Under HNWL update | 2026-03-10
Fresh water Building | UPS | Cable SChedule |  | A | Under HNWL update | 2026-03-10
Fresh water Building | UPS | PANEL BOARD |  | A | Under HNWL update | 2026-03-10
Fresh water Building | ACS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 21593 |  | Approved with Comments
Fresh water Building | ACS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 21593 |  | Approved with Comments
Fresh water Building | ACS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 21593 |  | Approved with Comments
Fresh water Building | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLCDEPOCS2-1200001 | A | Approved from CJV |  | Released to Systra | 21594 |  | Approved with Comments
Fresh water Building | ACS | Panel Arrangement and Wiring Details |  | A | Approved from CJV |  | Released to Systra | 21595 |  | Rejected
Admin Building | MCS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 23935 |  | Rejected
Admin Building | MCS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 23935 |  | Rejected |  |  |  | Documents Status
Admin Building | MCS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 23935 |  | Rejected |  |  |  | Total Number of Documents | 303
Admin Building | MCS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | 23935 |  | Rejected |  |  |  | Total Number of submitted from HNWLdoumcnts | 166
Admin Building | ACS | Equipment Layout Drawing |  | A | Approved from CJV |  | Under SMO Review | WF-023959 | [5 empty] | Total Number of not submitted from HNWL documents | 137
Admin Building | ACS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Under SMO Review | WF-023959 | [5 empty] | Under HNWL update | 20
Admin Building | ACS | Cable Routing drawing |  | A | Approved from CJV |  | Under SMO Review | WF-023959 | [5 empty] | Under CJV Review | 0
Admin Building | ACS | Cable SChedule |  | A | Approved from CJV |  | Under SMO Review | WF-023961 | [5 empty] | Under Safety Review | 0
Admin Building | ACS | Panel Arrangement and Wiring Details |  | A | Approved from CJV |  | Under SMO Review | WF-023960 | [5 empty] | Under SMO Review | 11
Admin Building | CCTV | Equipment Layout Drawing |  | A | Approved from CJV |  | Under SMO Review | WF-023967 | [5 empty] | Released to Systra | 135
Admin Building | CCTV | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Under SMO Review | WF-023967 | [5 empty] | Under Systra Review | 21
Admin Building | CCTV | Cable Routing drawing |  | A | Approved from CJV |  | Under SMO Review | WF-023967 | [5 empty] | Approved with Comments | 95
Admin Building | CCTV | FOV |  | A | Approved from CJV |  | Under SMO Review | WF-023967 | [5 empty] | Rejected | 20
Admin Building | CCTV | Cable SChedule |  | A | Approved from CJV |  | Under SMO Review | WF-023969

## ELV DD - Service Point
Cutoff Date 02/09/2026
[7 empty] | Internal Review |  | SMO Review |  |  | Systra Review
Location Name | Building NAME | Building Ref. | TEL Sub-Systems | Document Title | Document No. | Rev. | Status With Honeywell | Status Date | Document through WF Status | WF no. | Date | Status with Systra | Status Date | REASONS OF RETURN | Comment
New Capital SP | FRESH WATER BUILDING |  | MCS | Equipment Layout Drawing | HSR-SOA-DRW-TELMCS-GLBSPT1FS-1200002 | A | Approved from CJV |  | Released to Systra | 21192 |  | Under Systra Review
New Capital SP | FRESH WATER BUILDING |  | MCS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELMCS-GLBSPT1FS-1200001 | A | Approved from CJV |  | Released to Systra | 21192 |  | Under Systra Review
New Capital SP | FRESH WATER BUILDING |  | MCS | Cable Routing drawing | HSR-SOA-DRW-TELMCS-GLBSPT1FS-1200003 | A | Approved from CJV |  | Released to Systra | 21192 |  | Under Systra Review
New Capital SP | FRESH WATER BUILDING |  | MCS | Cable SChedule | HSR-SOA-DES-TELMCS-GLBSPT1FS-1200001 | A | Approved from CJV |  | Released to Systra | 22009 |  | Approved with Comments
New Capital SP | FRESH WATER BUILDING |  | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLBSPT1FS-1200002 | A | Approved from CJV |  | Released to Systra | 21401 |  | Approved with Comments
New Capital SP | FRESH WATER BUILDING |  | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLBSPT1FS-1200001 | A | Approved from CJV |  | Released to Systra | 21401 |  | Approved with Comments
New Capital SP | FRESH WATER BUILDING |  | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLBSPT1FS-1200003 | A | Approved from CJV |  | Released to Systra | 21401 |  | Approved with Comments
New Capital SP | FRESH WATER BUILDING |  | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLBSPT1FS-1200001 | A | Approved from CJV |  | Released to Systra | 21399 |  | Approved with Comments
New Capital SP | FRESH WATER BUILDING |  | ACS | Panel Arrangement and Wiring Details | HSR-SOA-DRW-TELACS-GLBSPT1FS-1200004 | B | Approved from CJV |  | Released to Systra | WF-023260 |  | Under Systra Review
New Capital SP | FRESH WATER BUILDING |  | UPS | Equipment Layout Drawing |  | A | Under HNWL update | 2026-03-10
New Capital SP | FRESH WATER BUILDING |  | UPS | System Overall Architecture (SLD) |  | A | Under HNWL update | 2026-03-10
New Capital SP | FRESH WATER BUILDING |  | UPS | Cable Routing drawing |  | A | Under HNWL update | 2026-03-10
New Capital SP | FRESH WATER BUILDING |  | UPS | Cable SChedule |  | A | Under HNWL update | 2026-03-10
New Capital SP | FRESH WATER BUILDING |  | UPS | PANEL BOARD |  | A | Under HNWL update | 2026-03-10
New Capital SP | FRESH WATER BUILDING |  | CCTV | Equipment Layout Drawing | HSR-SOA-DRW-TELCCTV-GLBSPT1FS-1200002 | A | Approved from CJV |  | Released to Systra | 21564 |  | Approved with Comments
New Capital SP | FRESH WATER BUILDING |  | CCTV | System Overall Architecture (SLD) | HSR-SOA-DRW-TELCCTV-GLBSPT1FS-1200001 | A | Approved from CJV |  | Released to Systra | 21564 |  | Approved with Comments
New Capital SP | FRESH WATER BUILDING |  | CCTV | Cable Routing drawing | HSR-SOA-DRW-TELCCTV-GLBSPT1FS-1200003 | A | Approved from CJV |  | Released to Systra | 21564 |  | Approved with Comments
New Capital SP | FRESH WATER BUILDING |  | CCTV | Coverage Report / Field of View | HSR-SOA-DES-TELCCTV-GLBSPT1FS-1200001 | A | Approved from CJV |  | Released to Systra | 21564 |  | Approved with Comments
New Capital SP | FRESH WATER BUILDING |  | CCTV | cable schedule | HSR-SOA-DES-TELCCTV-GLBSPT1FS-1200002 | A | Approved from CJV |  | Released to Systra | 21566 |  | Approved with Comments
New Capital SP | HP TRAIN WASH BUILDING |  | MCS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 21150 |  | Approved with Comments
New Capital SP | HP TRAIN WASH BUILDING |  | MCS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 21150 |  | Approved with Comments
New Capital SP | HP TRAIN WASH BUILDING |  | MCS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 21150 |  | Approved with Comments
New Capital SP | HP TRAIN WASH BUILDING |  | MCS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | 21151 |  | Approved with Comments
New Capital SP | HP TRAIN WASH BUILDING |  | ACS | Equipment Layout Drawing | HSR-SOA-DRW-TELACS-GLBSPT1WC-1200002 | A | Approved from CJV |  | Released to Systra | 21269 |  | Under Systra Review
New Capital SP | HP TRAIN WASH BUILDING |  | ACS | System Overall Architecture (SLD) | HSR-SOA-DRW-TELACS-GLBSPT1WC-1200001 | A | Approved from CJV |  | Released to Systra | 21269 |  | Under Systra Review
New Capital SP | HP TRAIN WASH BUILDING |  | ACS | Cable Routing drawing | HSR-SOA-DRW-TELACS-GLBSPT1WC-1200003 | A | Approved from CJV |  | Released to Systra | 21269 |  | Under Systra Review
New Capital SP | HP TRAIN WASH BUILDING |  | ACS | Cable SChedule | HSR-SOA-DES-TELACS-GLBSPT1WC-1200001 | A | Approved from CJV |  | Released to Systra | 21270 |  | Under Systra Review
New Capital SP | HP TRAIN WASH BUILDING |  | ACS | Panel Arrangement and Wiring Details |  | A | Approved from CJV |  | Released to Systra | 21271 |  | Under Systra Review
New Capital SP | HP TRAIN WASH BUILDING |  | UPS | Equipment Layout Drawing |  | A
New Capital SP | HP TRAIN WASH BUILDING |  | UPS | System Overall Architecture (SLD) |  | A
New Capital SP | HP TRAIN WASH BUILDING |  | UPS | Cable Routing drawing |  | A
New Capital SP | HP TRAIN WASH BUILDING |  | UPS | Cable SChedule |  | A
New Capital SP | HP TRAIN WASH BUILDING |  | UPS | PANEL BOARD |  | A
New Capital SP | HP TRAIN WASH BUILDING |  | CCTV | Equipment Layout Drawing |  | B | Approved from CJV |  | Released to Systra | 24291 |  | Under Systra Review
New Capital SP | HP TRAIN WASH BUILDING |  | CCTV | System Overall Architecture (SLD) |  | B | Approved from CJV |  | Released to Systra | 24291 |  | Under Systra Review
New Capital SP | HP TRAIN WASH BUILDING |  | CCTV | Cable Routing drawing |  | B | Approved from CJV |  | Released to Systra | 24291 |  | Under Systra Review
New Capital SP | HP TRAIN WASH BUILDING |  | CCTV | Coverage Report / Field of View |  | B | Approved from CJV |  | Released to Systra | 24291 |  | Under Systra Review
New Capital SP | HP TRAIN WASH BUILDING |  | CCTV | cable schedule |  | B | Approved from CJV |  | Released to Systra | 24293 |  | Under Systra Review
New Capital SP | STABLING YARD |  | MCS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 21685 |  | Approved with Comments
New Capital SP | STABLING YARD |  | MCS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 21685 |  | Approved with Comments
New Capital SP | STABLING YARD |  | MCS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 21685 |  | Approved with Comments
New Capital SP | STABLING YARD |  | MCS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | 21686 |  | Approved with Comments
New Capital SP | STABLING YARD |  | ACS | Equipment Layout Drawing |  | A
New Capital SP | STABLING YARD |  | ACS | System Overall Architecture (SLD) |  | A
New Capital SP | STABLING YARD |  | ACS | Cable Routing drawing |  | A
New Capital SP | STABLING YARD |  | ACS | Cable SChedule |  | A
New Capital SP | STABLING YARD |  | ACS | Panel Arrangement and Wiring Details |  | A
New Capital SP | STABLING YARD |  | UPS | Equipment Layout Drawing |  | A | Under HNWL update | 2026-03-09
New Capital SP | STABLING YARD |  | UPS | System Overall Architecture (SLD) |  | A | Under HNWL update | 2026-03-09
New Capital SP | STABLING YARD |  | UPS | Cable Routing drawing |  | A | Under HNWL update | 2026-03-09
New Capital SP | STABLING YARD |  | UPS | Cable SChedule |  | A | Under HNWL update | 2026-03-09
New Capital SP | STABLING YARD |  | UPS | PANEL BOARD |  | A | Under HNWL update | 2026-03-09
New Capital SP | STABLING YARD |  | CCTV | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 21991 |  | Approved with Comments
New Capital SP | STABLING YARD |  | CCTV | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 21991 |  | Approved with Comments
New Capital SP | STABLING YARD |  | CCTV | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 21991 |  | Approved with Comments
New Capital SP | STABLING YARD |  | CCTV | Coverage Report / Field of View |  | A | Approved from CJV |  | Released to Systra | 21991 |  | Approved with Comments
New Capital SP | STABLING YARD |  | CCTV | cable schedule |  | A | Approved from CJV |  | Released to Systra | 21992 |  | Approved with Comments
New Capital SP | STABLING YARD |  | PAS | Equipment Layout Drawing |  | A
New Capital SP | STABLING YARD |  | PAS | System Overall Architecture (SLD) |  | A
New Capital SP | STABLING YARD |  | PAS | Cable Routing drawing |  | A
New Capital SP | STABLING YARD |  | PAS | acoustec report |  | A
New Capital SP | STABLING YARD |  | PAS | Cable SChedule |  | A
New Capital SP | WPMS |  | MCS | Equipment Layout Drawing |  | A
New Capital SP | WPMS |  | MCS | System Overall Architecture (SLD) |  | A
New Capital SP | WPMS |  | MCS | Cable Routing drawing |  | A
New Capital SP | WPMS |  | MCS | Cable SChedule |  | A
New Capital SP | WPMS |  | ACS | Equipment Layout Drawing |  | A
New Capital SP | WPMS |  | ACS | System Overall Architecture (SLD) |  | A
New Capital SP | WPMS |  | ACS | Cable Routing drawing |  | A
New Capital SP | WPMS |  | ACS | Cable SChedule |  | A
New Capital SP | WPMS |  | ACS | Panel Arrangement and Wiring Details |  | A
New Capital SP | WPMS |  | UPS | Equipment Layout Drawing |  | A
New Capital SP | WPMS |  | UPS | System Overall Architecture (SLD) |  | A
New Capital SP | WPMS |  | UPS | Cable Routing drawing |  | A
New Capital SP | WPMS |  | UPS | Cable SChedule |  | A
New Capital SP | WPMS |  | UPS | PANEL BOARD |  | A
New Capital SP | WPMS |  | CCTV | Equipment Layout Drawing |  | A
New Capital SP | WPMS |  | CCTV | System Overall Architecture (SLD) |  | A
New Capital SP | WPMS |  | CCTV | Cable Routing drawing |  | A
New Capital SP | WPMS |  | CCTV | Coverage Report / Field of View |  | A
New Capital SP | WPMS |  | CCTV | cable schedule |  | A
Borg El Arab SP | FRESH WATER BUILDING |  | MCS | Equipment Layout Drawing |  | A | Approved from CJV |  | Under SMO Review
Borg El Arab SP | FRESH WATER BUILDING |  | MCS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Under SMO Review
Borg El Arab SP | FRESH WATER BUILDING |  | MCS | Cable Routing drawing |  | A | Approved from CJV |  | Under SMO Review
Borg El Arab SP | FRESH WATER BUILDING |  | MCS | Cable SChedule |  | A | Approved from CJV |  | Under SMO Review
Borg El Arab SP | FRESH WATER BUILDING |  | ACS | Equipment Layout Drawing |  | A
Borg El Arab SP | FRESH WATER BUILDING |  | ACS | System Overall Architecture (SLD) |  | A
Borg El Arab SP | FRESH WATER BUILDING |  | ACS | Cable Routing drawing |  | A
Borg El Arab SP | FRESH WATER BUILDING |  | ACS | Cable SChedule |  | A
Borg El Arab SP | FRESH WATER BUILDING |  | ACS | Panel Arrangement and Wiring Details |  | A
Borg El Arab SP | WPMS |  | MCS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 21056 |  | Approved with Comments
Borg El Arab SP | WPMS |  | MCS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 21056 |  | Approved with Comments
Borg El Arab SP | WPMS |  | MCS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 21056 |  | Approved with Comments
Borg El Arab SP | WPMS |  | MCS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | 21057 |  | Approved with Comments
Borg El Arab SP | WPMS |  | ACS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 21382 |  | Under Systra Review
Borg El Arab SP | WPMS |  | ACS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 21382 |  | Under Systra Review
Borg El Arab SP | WPMS |  | ACS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 21382 |  | Under Systra Review
Borg El Arab SP | WPMS |  | ACS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | 22005 |  | Approved with Comments
Borg El Arab SP | WPMS |  | ACS | Panel Arrangement and Wiring Details |  | A | Approved from CJV |  | Released to Systra | 21380 |  | Rejected
Borg El Arab SP | WPMS |  | UPS | Equipment Layout Drawing |  | A | Under HNWL update
Borg El Arab SP | WPMS |  | UPS | System Overall Architecture (SLD) |  | A | Under HNWL update
Borg El Arab SP | WPMS |  | UPS | Cable Routing drawing |  | A | Under HNWL update
Borg El Arab SP | WPMS |  | UPS | Cable SChedule |  | A | Under HNWL update
Borg El Arab SP | WPMS |  | UPS | PANEL BOARD |  | A | Under HNWL update
Borg El Arab SP | WPMS |  | CCTV | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | WF-021379 |  | Under Systra Review
Borg El Arab SP | WPMS |  | CCTV | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | WF-021379 |  | Under Systra Review
Borg El Arab SP | WPMS |  | CCTV | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | WF-021379 |  | Under Systra Review
Borg El Arab SP | WPMS |  | CCTV | Coverage Report / Field of View |  | A | Approved from CJV |  | Released to Systra | WF-021379 |  | Under Systra Review
Borg El Arab SP | WPMS |  | CCTV | cable schedule |  | A | Approved from CJV |  | Released to Systra | WF-021377 |  | Approved with Comments
Borg El Arab SP | STABLING YARD |  | MCS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 21007 |  | Approved with Comments
Borg El Arab SP | STABLING YARD |  | MCS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 21007 |  | Approved with Comments
Borg El Arab SP | STABLING YARD |  | MCS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 21007 |  | Approved with Comments
Borg El Arab SP | STABLING YARD |  | MCS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | 21008 |  | Approved with Comments
Borg El Arab SP | STABLING YARD |  | ACS | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 21370 |  | Rejected
Borg El Arab SP | STABLING YARD |  | ACS | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 21370 |  | Rejected
Borg El Arab SP | STABLING YARD |  | ACS | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 21370 |  | Rejected
Borg El Arab SP | STABLING YARD |  | ACS | Cable SChedule |  | A | Approved from CJV |  | Released to Systra | 21371 |  | Approved with Comments
Borg El Arab SP | STABLING YARD |  | ACS | Panel Arrangement and Wiring Details |  | A | Approved from CJV |  | Released to Systra | 21372 |  | Approved with Comments
Borg El Arab SP | STABLING YARD |  | UPS | Equipment Layout Drawing |  | A | Under HNWL update | 2026-03-29
Borg El Arab SP | STABLING YARD |  | UPS | System Overall Architecture (SLD) |  | A | Under HNWL update | 2026-03-29
Borg El Arab SP | STABLING YARD |  | UPS | Cable Routing drawing |  | A | Under HNWL update | 2026-03-29
Borg El Arab SP | STABLING YARD |  | UPS | Cable SChedule |  | A | Under HNWL update | 2026-03-29
Borg El Arab SP | STABLING YARD |  | UPS | PANEL BOARD |  | A | Under HNWL update | 2026-03-29
Borg El Arab SP | STABLING YARD |  | CCTV | Equipment Layout Drawing |  | A | Approved from CJV |  | Released to Systra | 21252 |  | Under Systra Review
Borg El Arab SP | STABLING YARD |  | CCTV | System Overall Architecture (SLD) |  | A | Approved from CJV |  | Released to Systra | 21252 |  | Under Systra Review
Borg El Arab SP | STABLING YARD |  | CCTV | Cable Routing drawing |  | A | Approved from CJV |  | Released to Systra | 21252 |  | Under Systra Review
Borg El Arab SP | STABLING YARD |  | CCTV | Coverage Report / Field of View |  | A | Approved from CJV |  | Released to Systra | 21252 |  | Under Systra Review
Borg El Arab SP | STABLING YARD |  | CCTV | cable schedule |  | A | Approved from CJV |  | Released to Systra | 21253 |  | Under Systra Review
Borg El Arab SP | STABLING YARD |  | PAS | Equipment Layout Drawing |  | A
Borg El Arab SP | STABLING YARD |  | PAS | System Overall Architecture (SLD) |  | A
Borg El Arab SP | STABLING YARD |  | PAS | Cable Routing drawing |  | A
Borg El Arab SP | STABLING YARD |  | PAS | acoustec report |  | A
Borg El Arab SP | STABLING YARD |  | PAS | Cable SChedule |  | A
Borg El Arab SP | STABLING YARD |  | PAS | Rack Layout |  | A
Borg El Arab SP | HP TRAIN WASH BUILDING |  | UPS | Equipment Layout Drawing |  | A | Under Safety Review | 2026-03-15
Borg El Arab SP | HP TRAIN WASH BUILDING |  | UPS | System Overall Architecture (SLD) |  | A | Under Safety Review | 2026-03-15
Borg El Arab SP | HP TRAIN WASH BUILDING |  | UPS | Cable Routing drawing |  | A | Under Safety Review | 2026-03-15
Borg El Arab SP | HP TRAIN WASH BUILDING |  | UPS | Cable SChedule |  | A | Under Safety Review | 2026-03-15
Borg El Arab SP | HP TRAIN WASH BUILDING |  | UPS | PANEL BOARD |  | A | Under Safety Review | 2026-03-15
Documents Status
[16 empty] | Total Number of Documents | 95
[16 empty] | Total Number of submitted from HNWLdoumcnts | 94
[16 empty] | Total Number of not submitted from HNWL documents | 1
[16 empty] | Under HNWL update | 20
[16 empty] | Under CJV Review | 0
[16 empty] | Under Safety Review | 5
[16 empty] | Under SMO Review | 4
[16 empty] | Released to Systra | 65
[16 empty] | Under Systra Review | 26
[16 empty] | Approved with Comments | 35
[16 empty] | Rejected | 4
New Capital Service point HSR-SOA-DRW-DWE-GL-1100067
Fresh water building
Stabling yard
OCS switching/sectioning hub
HP Train wash building

## Instalaltion Details
Cutoff 06-09-2026
|  |  |  | Internal Review |  | SMO Review |  |  | Systra Review
System | Document No. | Document Name | Rev. | Status With Honeywell | Status Date | Document through WF Status | WF no. | Date | Status with Systra | Status Date | REASONS OF RETURN | Comment
MCS | HSR-SOA-DES-TELMCS-GL-1200005 | General Installation Details – Master Clock System | C | Approved from CJV |  | Released to Systra | WF-022899 |  | Approved with Comments
ACS | HSR-SOA-DES-TELACS-GL-1200006 | General Installation Details – Access Control System | A | Approved from CJV |  | Released to Systra | WF-014489 |  | Approved with Comments
PAS | HSR-SOA-DES-TELPAS-GL-1200007 | General Installation Details – Public Address System | C | Approved from CJV |  | Released to Systra | WF-023039 |  | Approved with Comments
WIFI | HSR-SOA-DES-TELWIFI-GL-1200004 | General Installation Details – WiFi System | C | Approved from CJV |  | Released to Systra | WF-022575 |  | Approved with Comments
PIS | HSR-SOA-DES-TELPIS-GL-1200005 | General Installation Details – Passenger Information System | B | Approved from CJV |  | Released to Systra | WF-022502 |  | Approved with Comments
CCTV | HSR-SOA-DES-TELCCTV-GL-1200005 | General Installation Details - Closed Circuit Television System | B | Approved from CJV |  | Released to Systra | WF-022895 |  | Approved with Comments
OATS | HSR-SOA-DES-TELOATS-GL-1200007 | Installation Details - OATS | A | Approved from CJV |  | Released to Systra | WF-023641 |  | Under Systra Review
MSN-Passive | HSR-SOA-DES-TELMSN-GL-1200020 | Installation Details - Passive | A | Under HNWL update | 2026-05-03
UPS | HSR-SOA-DES-TELUPS-GL-1200009 | Installation Details - UPS | A
IDS | HSR-SOA-DES-TELACS-GL-1200011 | Installation Details – IDS | A
FO Enclosure on OCS | HSR-SOA-DRW-TELMSN-GL-1200033 | FO Enclosure Installation Details on OCS - Poles | A

## Provision Drawings (Stations)
Cutoff Date 03-09-2026
Station Name | Rev. | HNWL Status | Date | Systra Status | Date | Comments
Ain Al Sokhna |  | Approved from CJV | 2026-03-09 | under Systra review | 2026-03-09
New Capital |  | Approved from CJV | 23/8/2026 | under Systra review | 23/8/2026
Mohamed Naguib |  | Approved from CJV | 18-1-2026 | closed | 18/1/2026
Cairo |  | Approved from CJV | 15/2/2026 | closed | 15/2/2026
Giza |  | Approved from CJV | 16-5-2026 | Under Systra Review | 16-5-2026
October Gardens |  | Approved from CJV | 22-12-2026 | Closed | 22/12/2026
6th October |  | Approved from CJV | 2026-07-06 | Under Systra Review | 2026-07-06
Sphinx |  | Approved from CJV | 17/5/2026 | closed | 18/5/2026
Sadat
Wadi Al Natroun |  | Approved from CJV | 17/5/2026 | closed | 18/5/2026
Noubarya |  | Approved from CJV | 23-5-2026 | Under Systra Review | 23-5-2026
Borg Al Arab |  | Under HNWL update | 26-8-2026 | SYStra shared the As built for Platform | 26-8-2026
El Hammam |  | Under HNWL update | 26-8-2026 | Systra Shared their comments | 13-6-2026
Ras El Hekma |  | Approved from CJV | 2026-02-05 | Under Systra Review | 2026-02-05
El Dabaa |  | Approved from CJV | 2026-01-07 | Under Systra Review
Marsa Matrouh |  | Approved from CJV | 2026-07-04 | Under Systra Review | 2026-07-04
Army Stadium |  | Approved from CJV | 14/6/2026 | Under Systra Review | 14-6-2026
Alamein |  | Approved from CJV | 14-6-2026 | Under Systra Review | 14-6-2026
Sidi Abdelrahman |  | Approved from CJV | 21-5-2026 | Under Systra Review | 21-5-2026
Amrya
Alexandria

## SDS
Cutoff 06-09-2026
Serial | System Code | Submission Tittle | Doc No. | Rev. | Document Status | Status | Remarks | HNWL Status
0 | Workstations and Servers | System Design Specification | HSR-SOA-DES-TEL-GL-1200005 | A |  | Rejected | Currently under HNWL updated due to SYS comment | Under HNWL update
1 | MCS | System Design Specification | HSR-SOA-DES-TELMCS-GL-1200001 | A | Code B | Approved with Comments. | Approved with Comments.
2 | MSN (Active) | System Design Specification | HSR-SOA-DES-TELMSN-GL-1200001 | B | Code B | Approved with Comments. | Approved with Comments.
3 | MSN (Passive) | System Design Specification | HSR-SOA-DES-TELMSN-GL-1200011 | C | Code B | Approved with Comments. | Approved with Comments.
4 | ACS | System Design Specification | HSR-SOA-DES-TELACS-GL-1200001 | B | Code B | Approved with Comments. | Approved with Comments.
5 | IDS | System Design Specification | HSR-SOA-DES-TELACS-GL-1200008 | C |  | Under SYSTRA Review
6 | PAS | System Design Specification | HSR-SOA-DES-TELPAS-GL-1200001 | C |  | Rejected |  | Under HNWL update
7 | OATS | System Design Specification | HSR-SOA-DES-TELOATS-GL-1200001 | A | Code B | Approved with Comments. | Approved with Comments.
8 | VRS | System Design Specification | HSR-SOA-DES-TELVRS-GL-1200001 | B | Code B | Approved with Comments. | Approved with Comments.
9 | PIS | System Design Specification | HSR-SOA-DES-TELPIS-GL-1200001 | C | Code B | Approved with Comments. | Rev B. Approved with Comments.
10 | CCTV | System Design Specification | HSR-SOA-DES-TELCCTV-GL-1200001 | B | Code B | Approved with Comments. | Approved with Comments.
11 | WIFI | System Design Specification | HSR-SOA-DES-TELWIFI-GL-1200001 | A | Code B | Approved with Comments. | Approved with Comments.
12 | UPS | System Design Specification | HSR-SOA-DES-TELUPS-GL-1200002 | B |  | Under SYSTRA Review | Submitted officially to NAT/SYSTRA on 9/4/2026, and still awaiting for their feedback.
13 | Cybersecurity | System Design Specification | HSR-SOA-DES-TELMSN-GL-1200017 | B | Code B | Approved with Comments. | Approved with Comments.
14 | Fo Cable | Cabling Concept and Technical Specification of Fiber Optic Cables | HSR-SOA-DES-TELMSN-GL-1200010 | D | Code B | Approved with Comments.

## TPS
Cutoff Date 18-07-2026
[5 empty] | Internal Review |  | SMO Review |  |  | Systra Review
Location | TEL Sub-Systems | Document Title | Document No. | Rev. | Status With Honeywell | Status Date | Document through WF Status | WF no. | Date | Status with Systra | Status Date | REASONS OF RETURN | Comment
TSS | ACS | System Overall Architecture |  | B | Approved from CJV |  | Released to Systra | WF-019857 | 2026-02-28 | Approved with Comments | 2026-04-21
TSS | ACS | System Equipment Layout |  | B | Approved from CJV |  | Released to Systra | WF-019857 | 2026-02-25 | Approved with Comments | 2026-04-21
TSS | ACS | System Cable routing plan |  | B | Approved from CJV |  | Released to Systra | WF-019857 | 2026-02-25 | Approved with Comments | 2026-04-21
TSS | ACS | cable schedule |  | A | Approved from CJV |  | Released to Systra | WF-019839 | 2026-02-25 | Rejected | 2026-03-17
TSS | ACS | Panel Arrangement and Wiring Details |  | A | Approved from CJV |  | Released to Systra | WF-019840 | 2026-02-25 | Rejected
TSS | CCTV | System Overall Architecture |  | A | Approved from CJV |  | Released to Systra | WF-021066 | 2026-05-06 | Approved with Comments
TSS | CCTV | System Equipment Layout |  | A | Approved from CJV |  | Released to Systra | WF-021066 | 2026-05-06 | Approved with Comments
TSS | CCTV | System Cable routing plan |  | A | Approved from CJV |  | Released to Systra | WF-021066 | 2026-05-06 | Approved with Comments
TSS | CCTV | Coverage Study/Field of View |  | A | Approved from CJV |  | Released to Systra | WF-021066 | 2026-05-06 | Approved with Comments
TSS | CCTV | cable schedule |  | A | Approved from CJV |  | Released to Systra | WF-021066 | 2026-05-06 | Approved with Comments
TSS | MCS | System Overall Architecture |  | C | Approved from CJV |  | Released to Systra | WF-019832 | 2026-02-28 | Approved with Comments | 2026-05-11
TSS | MCS | System Equipment Layout |  | C | Approved from CJV |  | Released to Systra | WF-019832 | 2026-02-28 | Approved with Comments | 2026-05-11
TSS | MCS | System Cable routing plan |  | C | Approved from CJV |  | Released to Systra | WF-019832 | 2026-02-28 | Approved with Comments | 2026-05-11
TSS | MCS | cable schedule |  | A | Approved from CJV |  | Released to Systra | WF-019831 | 2026-02-28 | Under Systra Review | 2026-02-28
TSS | MSN | System Overall Architecture |  | A | Approved from CJV |  | Released to Systra | WF-019933 | 2026-01-27 | Rejected
TSS | MSN | System Equipment Layout |  | A | Approved from CJV |  | Released to Systra | WF-019933 | 2026-01-27 | Rejected
TSS | MSN | System Cable routing plan |  | A | Approved from CJV |  | Released to Systra | WF-019933 | 2026-01-27 | Rejected
TSS | OATS | System Overall Architecture |  | B | Approved from CJV |  | Released to Systra | WF-018505 | 2026-01-29 | Approved with Comments | 2026-02-26
TSS | OATS | System Equipment Layout |  | B | Approved from CJV |  | Released to Systra | WF-018505 | 2026-01-29 | Approved with Comments | 2026-02-26
TSS | OATS | System Cable routing plan |  | B | Approved from CJV |  | Released to Systra | WF-018505 | 2026-01-29 | Approved with Comments | 2026-02-25
TSS | OATS | cable schedule |  | A | Approved from CJV |  | Released to Systra | WF-019818 | 2026-02-28 | Approved with Comments | 2026-04-26
TSS | UPS | System Overall Architecture |  | A | Under CJV review
TSS | UPS | System Equipment Layout |  | A | Under CJV review
TSS | UPS | System Cable routing plan |  | A | Under CJV review
TSS | UPS | Cable Schedule |  | A | Under CJV review
TSS | UPS | Distribution board loads schedule |  | A | Under CJV review
SP | ACS | System Overall Architecture |  | B | Approved from CJV |  | Released to Systra | WF-019842 | 2026-02-28 | Approved with Comments | 2026-04-21
SP | ACS | System Equipment Layout |  | B | Approved from CJV |  | Released to Systra | WF-019842 | 2026-02-28 | Approved with Comments | 2026-04-21
SP | ACS | System Cable routing plan |  | B | Approved from CJV |  | Released to Systra | WF-019842 | 2026-02-28 | Approved with Comments | 2026-04-21
SP | ACS | cable schedule |  | A | Approved from CJV |  | Released to Systra | WF-019843 | 2026-02-25 | Rejected | 2026-04-20
SP | ACS | Panel Arrangement and Wiring Details |  | A | Approved from CJV |  | Released to Systra | WF-019848 | 2026-02-28 | Rejected
SP | CCTV | System Overall Architecture |  | A | Approved from CJV |  | Released to Systra | WF-021070 | 2026-05-06 | Approved with Comments
SP | CCTV | System Equipment Layout |  | A | Approved from CJV |  | Released to Systra | WF-021070 | 2026-05-06 | Approved with Comments
SP | CCTV | System Cable routing plan |  | A | Approved from CJV |  | Released to Systra | WF-021070 | 2026-05-06 | Approved with Comments
SP | CCTV | Coverage Study/Field of View |  | A | Approved from CJV |  | Released to Systra | WF-021070 | 2026-05-06 | Approved with Comments
SP | CCTV | cable schedule |  | A | Approved from CJV |  | Released to Systra | WF-021086 | 2026-05-06 | Approved with Comments
SP | MCS | System Overall Architecture |  | B | Approved from CJV |  | Released to Systra | WF-019827 | 2026-02-25 | Approved with Comments | 2026-04-07
SP | MCS | System Equipment Layout |  | B | Approved from CJV |  | Released to Systra | WF-019827 | 2026-02-25 | Approved with Comments | 2026-04-07
SP | MCS | System Cable routing plan |  | B | Approved from CJV |  | Released to Systra | WF-019827 | 2026-02-25 | Approved with Comments | 2026-04-07
SP | MCS | cable schedule |  | A | Approved from CJV |  | Released to Systra | WF-019826 | 2026-02-28 | Approved with Comments | 2026-04-07
SP | MSN | System Overall Architecture |  | A | Approved from CJV |  | Released to Systra | WF-015287 | 2025-07-16 | Rejected
SP | MSN | System Equipment Layout |  | A | Approved from CJV |  | Released to Systra | WF-015287 | 2025-07-16 | Rejected
SP | MSN | System Cable routing plan |  | A | Approved from CJV |  | Released to Systra | WF-015287 | 2025-07-16 | Rejected
SP | OATS | System Overall Architecture |  | B | Approved from CJV |  | Released to Systra | WF-018507 | 2026-01-29 | Approved with Comments | 2026-02-26
SP | OATS | System Equipment Layout |  | B | Approved from CJV |  | Released to Systra | WF-018507 | 2026-01-29 | Approved with Comments | 2026-02-26
SP | OATS | System Cable routing plan |  | B | Approved from CJV |  | Released to Systra | WF-018507 | 2026-01-29 | Approved with Comments | 2026-02-26
SP | OATS | cable schedule |  | A | Approved from CJV |  | Released to Systra | WF-019815 | 2026-02-26 | Approved with Comments | 2026-04-10
SP | UPS | System Equipment Layout |  | A
SP | UPS | System Cable routing plan |  | A
SP | UPS | cable schedule |  | A
PP | ACS | System Overall Architecture |  | B | Approved from CJV |  | Released to Systra | WF-019851 | 2026-02-28 | Approved with Comments | 2026-04-21
PP | ACS | System Equipment Layout |  | B | Approved from CJV |  | Released to Systra | WF-019851 | 2026-02-28 | Approved with Comments | 2026-04-21
PP | ACS | System Cable routing plan |  | B | Approved from CJV |  | Released to Systra | WF-019851 | 2026-02-28 | Approved with Comments | 2026-04-21
PP | ACS | cable schedule |  | A | Approved from CJV |  | Released to Systra | WF-019852 | 2026-02-28 | Rejected | 2026-04-23
PP | ACS | Panel Arrangement and Wiring Details |  | A | Approved from CJV |  | Released to Systra | WF-022197 | 2026-04-28 | Approved with Comments
PP | CCTV | System Overall Architecture |  | A | Approved from CJV |  | Released to Systra | WF-021089 | 2026-05-06 | Approved with Comments
PP | CCTV | System Equipment Layout |  | A | Approved from CJV |  | Released to Systra | WF-021089 | 2026-05-06 | Approved with Comments
PP | CCTV | System Cable routing plan |  | A | Approved from CJV |  | Released to Systra | WF-021089 | 2026-05-06 | Approved with Comments
PP | CCTV | Coverage Study/Field of View |  | A | Approved from CJV |  | Released to Systra | WF-021089 | 2026-05-06 | Approved with Comments
PP | CCTV | cable schedule |  | A | Approved from CJV |  | Released to Systra | WF-021090 | 2026-05-06 | Approved with Comments
PP | MCS | System Overall Architecture |  | C | Approved from CJV |  | Released to Systra | WF-019824 | 2026-02-25 | Approved with Comments | 2026-04-07
PP | MCS | System Equipment Layout |  | C | Approved from CJV |  | Released to Systra | WF-019824 | 2026-02-25 | Approved with Comments | 2026-04-07
PP | MCS | System Cable routing plan |  | C | Approved from CJV |  | Released to Systra | WF-019824 | 2026-02-25 | Approved with Comments | 2026-04-07
PP | MCS | cable schedule |  | A | Approved from CJV |  | Released to Systra | WF-019821 | 2026-02-28 | Approved with Comments | 2026-04-07
PP | MSN | System Overall Architecture |  |  | Approved from CJV |  | Released to Systra | WF-015600 | 2025-07-28 | Rejected
PP | MSN | System Equipment Layout |  |  | Approved from CJV |  | Released to Systra | WF-015600 | 2025-07-28 | Rejected
PP | MSN | System Cable routing plan |  |  | Approved from CJV |  | Released to Systra | WF-015600 | 2025-07-28 | Rejected
PP | OATS | System Overall Architecture |  | B | Approved from CJV |  | Released to Systra | WF-018506 | 2026-01-29 | Approved with Comments | 2026-02-26
PP | OATS | System Equipment Layout |  | B | Approved from CJV |  | Released to Systra | WF-018506 | 2026-01-29 | Approved with Comments | 2026-02-26
PP | OATS | System Cable routing plan |  | B | Approved from CJV |  | Released to Systra | WF-018506 | 2026-01-29 | Approved with Comments | 2026-02-25
PP | OATS | cable schedule |  | A | Approved from CJV |  | Released to Systra | WF-019834 | 2026-02-26 | Approved with Comments | 2026-04-20
PP | UPS | System Equipment Layout |  | A | Under CJV review
PP | UPS | System Cable routing plan |  | A | Under CJV review
PP | UPS | cable schedule |  | A | Under CJV review
[14 empty] | Documents Status | Total | ICT | ELV
[14 empty] | Total Number of Documents | 76 | 21 | 55
[14 empty] | Total Number of submitted from HNWLdoumcnts | 71 | 21 | 50
[14 empty] | Total Number of not submitted from HNWL documents | 5 | 0 | 5
[14 empty] | Under HNWL update | 0 | 0 | 0
[14 empty] | Under CJV Review | 8 | 0 | 8
[14 empty] | Under Safety Review | 0 | 0 | 0
[14 empty] | Under SMO Review | 0 | 0 | 0
[14 empty] | Released to Systra | 63 | 21 | 42
[14 empty] | Under Systra Review | 1 | 0 | 1
[14 empty] | Approved with Comments | 48 | 12 | 36
[14 empty] | Rejected | 14 | 9 | 5

## TSS3
Cutoff 18-07-2026
HSR-SOA-DRW-TELCCTV-GLDTSS03-1200004 | System Overall Architecture (SLD) | A | TEL-CCTV | GL-D-TSS03 Traction Supply Station 03 | Approved with Comments | 021093
HSR-SOA-DRW-TELCCTV-GLDTSS03-1200005 | System Cable routing plan | A | TEL-CCTV | GL-D-TSS03 Traction Supply Station 03 | Approved with Comments | 021093
HSR-SOA-DRW-TELCCTV-GLDTSS03-1200006 | System Equipment Layout | A | TEL-CCTV | GL-D-TSS03 Traction Supply Station 03 | Approved with Comments | 021093
HSR-SOA-DES-TELCCTV-GLDTSS03-1200004 | Cable Schedule | A | TEL-CCTV | GL-D-TSS03 Traction Supply Station 03 | Approved with Comments | 021094
HSR-SOA-DES-TELCCTV-GLDTSS03-1200005 | Coverage Report / Field of View | A | TEL-CCTV | GL-D-TSS03 Traction Supply Station 03 | Approved with Comments | 021093

## RCP
Cutoff 05-08-2026
S/n | Station Name | Systra Status
1 | Station Ain El Sokhna | Released to Systra | Main Halls
2 | Station New Capital | Released to Systra | Full Station |  |  | Coordinated | SYS-SOAC-G-EET-0318-9693
3 | Station Mohamed Naguib | Released to Systra | Full Station |  |  | Coordinated | SYS-SOAC-G-EET-0302-9436
4 | Station Cairo | Released to Systra | Full Station |  |  | Coordinated | SYS-SOAC-G-EET-0329-9745
5 | Station Giza | Released to Systra | Full Station | Sent by mail to systra 02-25-2026 | SYS-RFI-000790 | Coordinated | SYS-SOAC-G-EET-0423-10068
6 | Station October Gardens | Released to Systra | Full Station |  |  | Coordinated | SYS-SOAC-G-EET-0409-9913 -
7 | Station 6th October |  | Did not Received from SYSTRA
9 | Station Sphinx | Released to Systra | Full Station | Sent by mail to systra 03-18-2026 | SYS-RFI-000753 | Coordinated | SYS-SOAC-G-EET-0430-10142
10 | Station Al Sadat | Released to Systra | Full Station |  |  | Coordinated | SYS-SOAC-G-EET-0412-9919 -
11 | Station Wadi El Natroun | Released to Systra | Full Station |  |  | Coordinated | SYS-SOAC-G-EET-0329-9743 -
12 | Station Al Noubarya | Released to Systra | Full Station | Sent by mail to systra 04-05-2026 | SYS-RFI-000825 | Coordinated | SYS-SOAC-G-EET-0412-9920
13 | Station Borg Al Arab | Released to Systra | Full Station | Sent by mail to systra 03-28-2026 | SYS-RFI-000992 | Coordinated
14 | Station Al Hamam | Released to Systra | Full Station | Sent by mail to systra 03-30-2026 | SYS-RFI-000993 | Coordinated
15 | Station Al Alameen | Released to Systra | Full Station | Sent by mail to systra 04-23-2026 | SYS-RFI-000691
16 | Station Al Daaba | Released to Systra | Full Station | Sent by mail to systra 03-18-2026 | SYS-RFI-000824 | Coordinated
17 | Station Sidi abdalruhman | Released to Systra | Full Station | Sent by mail to systra 03-12-2026 | SYS-RFI-000796 | Coordinated | SYS-SOAC-G-EET-0430-10143 -
18.35 | Station Ras El Hakma | Released to Systra | Full Station | Sent by mail to systra 03-10-2026 | HSRGL-JV-GC-002753 | Coordinated | SYS-SOAC-G-EET-0430-10141
19.4426 | Station Marsa Matrouh | Released to Systra | Full Station | Sent by mail to systra 04-01-2026 | SYS-RFI-001019
20 | Army Staduim | Released to Systra | Full Station |  |  | Coordinated
[5 empty] | Released to Systra | 17

## Inspection Test Report (ITP)
Document Name | Document Number | Rev. | Status | WF
Installation of Multiservice System (MSN) Passive | HSR-SOA-TPR-TELMSN-GL-1400001 | A | Not Submitted
Installation of Multiservice System (MSN) Active | HSR-SOA-TPR-TELMSN-GL-1400002 | A | Under Systra Review | WF-020135
Installation of Master Clock System (MCS) | HSR-SOA-TPR-TELMCS-GL-1400001 | D | Under Systra Review | WF-021157
Installation of Video Surveillance System (CCTV) | HSR-SOA-TPR-TELCCTV-GL-1400001 | A | Rejected | WF-020134
Installation of Public Address System (PAS) | HSR-SOA-TPR-TELPAS-GL-1400001 | C | Approved with Comments | WF-019822
Installation of Passenger Information System (PIS) | HSR-SOA-TPR-TELPIS-GL-1400001 | A | Rejected | WF-018898
Installation of Access Control System (ACS) | HSR-SOA-TPR-TELACS-GL-1400001 | A | Not Submitted
Installation of Railway Wi-Fi System (WIFI) | HSR-SOA-TPR-TELWIFI-GL-1400001 | D | Under Systra Review | WF-020852
Installation of Operational and Administrative Telephone System (OATS) |  | A | Not Submitted
Installation of Uninterruptible Power Supply (UPS) |  | A | Not Submitted
Installation of Voice Recording System (VRS) |  | A | Not Submitted
Test Procedures Inspection and Test Plan (ITP)Cable Pulling & Fiber Splicing | HSR-SOA-TPR-TEL-GL-1400001 | B | Approved with Comments | WF-017289

## Technical Rooms
Cutoff: 03-09-2026
Station Name | Room Name | Status with HNWL | Execution status( Site) | As built vs Shop Drawing | Completion % | Remarks | Comments | status With SMO | WF.NO | Date | Status with Systra | Date
New Capital | BAT-TEL
| IT-S BS 206 | Approved from CJV | In Progress |  | 65% |  |  | Released to systra | WF-020010 | 31/1/2026 | Approved with Comments | 29/4/2026
| IT-S BS 303 | Approved from CJV | In Progress |  | 65% |  |  | Released to systra | WF-020010 | 31/1/2026 | Approved with Comments | 29/4/2026
| IT-S BS 115 | Approved from CJV | In Progress |  | 65% |  |  | Released to systra | WF-020010 | 31/1/2026 | Approved with Comments | 29/4/2026
| IT-S BS 010 | Approved from CJV | In Progress |  | 65% |  |  | Released to systra | WF-020010 | 31/1/2026 | Approved with Comments | 29/4/2026
| IT-S GR 153 | Approved from CJV | In Progress |  | 45% |  |  | Released to systra | WF-020010 | 31/1/2026 | Approved with Comments | 29/4/2026
| IT-S GR 208 | Approved from CJV | In Progress |  | 30% |  |  | Released to systra | WF-021231 | 17/3/2026 | Under Systra Review | 2026-01-04
| TEL-S GR 137 | Under HNWL update | In Progress | the same entrance of the cable trays | 75% |  | waiting HNWL to cover RCS comments.
| IT-S MZ 123 | Approved from CJV | In Progress | the cable tryas locations will be changes as ber P3 As built | 0% |  |  | Released to systra | WF-020010 | 31/1/2026 | Approved with Comments | 29/4/2026
| IT-S MZ 023 | Approved from CJV | In Progress | the cable tryas locations will be changes as ber P3 As built | 0% |  |  | Released to systra | WF-020010 | 31/1/2026 | Approved with Comments | 29/4/2026
| IT-S MZ 313 | Approved from CJV | In Progress | the cable tryas locations will be changes as ber P3 As built | 0% |  |  | Released to systra | WF-020010 | 31/1/2026 | Approved with Comments | 29/4/2026
| IT-S MZ 209 | Approved from CJV | In Progress | the cable tryas locations will be changes as ber P3 As built | 0% |  |  | Released to systra | WF-020010 | 31/1/2026 | Approved with Comments | 29/4/2026
| IT-S FR 018 | Approved from CJV | Not started |  | 0% |  |  | Released to systra | WF-020011 | 31/1/2026 | Approved with Comments | 2026-04-05
| IT-S FR 147 | Approved from CJV | Not started |  | 0% |  |  | Released to systra | WF-020011 | 31/1/2026 | Approved with Comments | 2026-04-05
| IT-S FR 333 | Approved from CJV | Not started |  | 0% |  |  | Released to systra | WF-020011 | 31/1/2026 | Approved with Comments | 2026-04-05
| IT-S FR 205 | Approved from CJV | Not started |  | 0% |  |  | Released to systra | WF-020011 | 31/1/2026 | Approved with Comments | 2026-04-05
| SOAC Cable Room BS-316 | Approved from CJV | Unde HNWL update | Unde HNWL update | Unde HNWL update | Unde HNWL update | CJV shared the drawings with SMO via Aconex mail | Under SMO Review | WF-020012 | 31/1/2026
| SOAC Cable Room BS-226 | Approved from CJV |  |  |  | CJV will held a meeting with SMO |  | Under SMO Review | WF-020012 | 31/1/2026
| SOAC Cable Room BS-110 | Approved from CJV |  |  |  | CJV will held a meeting with SMO |  | Under SMO Review | WF-020012 | 31/1/2026
| SOAC Cable Room BS-016 | Approved from CJV |  |  |  | CJV will held a meeting with SMO |  | Under SMO Review | WF-020012 | 31/1/2026
| SOAC Cable Room GR-152 | Approved from CJV |  |  |  | CJV will held a meeting with SMO |  | Under SMO Review | WF-020012 | 31/1/2026
| SOAC Cable Room GR-030 | Approved from CJV |  |  |  | CJV will held a meeting with SMO |  | Under SMO Review | WF-020012 | 31/1/2026
| SOAC Cable Room GR-210 | Approved from CJV |  |  |  | CJV will held a meeting with SMO |  | Under SMO Review | WF-020012 | 31/1/2026
| SOAC Cable Room GR-347 | Approved from CJV |  |  |  | CJV will held a meeting with SMO |  | Under SMO Review | WF-020012 | 31/1/2026
Mohamed Naguib | BAT -TEL-S GR-001 | Under HNWL update | Not started |  | 0%
| TEL-S GR-004 | Approved from CJV | In Progress |  | 40% |  |  | Released to systra | WF-024131 | 21-7-2026 | Under Systra Review | 21-7-2026
| IT-S GR-243 | Approved from CJV | In Progress |  | 55% |  |  | Released to systra | WF-024131 | 21-7-2026 | Under Systra Review | 21-7-2026
| IT-S GR-239 | Approved from CJV | In Progress |  | 55% |  |  | Released to systra | WF-024131 | 21-7-2026 | Under Systra Review | 21-7-2026
| IT-S MZ-124 | Approved from CJV | In Progress |  | 45% |  |  | Released to systra | WF-024131 | 21-7-2026 | Under Systra Review | 21-7-2026
| IT-S MZ-002 | Approved from CJV | In Progress |  | 45% |  |  | Released to systra | WF-024131 | 21-7-2026 | Under Systra Review | 21-7-2026
| IT-S FR-005 | Approved from CJV | In Progress |  | 45% |  |  | Released to systra | WF-024131 | 21-7-2026 | Under Systra Review | 21-7-2026
| IT-S FR-134 | Approved from CJV | In Progress |  | 45% |  |  | Released to systra | WF-024131 | 21-7-2026 | Under Systra Review | 21-7-2026
| SOAC Cable Room GR-019 | Under CJV Review |  |  |  | CJV will held a meeting with SMO | waiting SMO's comments on New Capital
| SOAC Cable Room GR-119 | Under CJV Review |  |  |  | CJV will held a meeting with SMO
cairo | BAT-TEL-S GR-001 | Under HNWL update | Under CJV review | Under CJV review | Under CJV review | Under CJV review
| TEL-S GR-004 | Approved from CJV | In Progress |  | 20% |  |  | Released to Systra | WF-021518 | 31/1/2026 | Approved with comments | 2026-05-17
| IT-S GR-239 | Approved from CJV | In Progress |  | 25% |  |  | Released to Systra | WF-021518 | 31/1/2026 | Approved with comments | 2026-05-17
| IT-S GR-243 | Approved from CJV | In Progress | the shop drawing has some changes about Site | 45% |  |  | Released to Systra | WF-021518 | 31/1/2026 | Approved with comments | 2026-05-17
| IT-S MZ-002 | Approved from CJV | In Progress |  | 10% |  |  | Released to Systra | WF-021518 | 31/1/2026 | Approved with comments | 2026-05-17
| IT-S MZ-124 | Approved from CJV | In Progress |  | 10% |  |  | Released to Systra | WF-021518 | 31/1/2026 | Approved with comments | 2026-05-17
| IT-S FR-134 | Approved from CJV | In Progress |  | 10% |  |  | Released to Systra | WF-021518 | 31/1/2026 | Approved with comments | 2026-05-17
| IT-S FR-005 | Approved from CJV | In Progress |  | 10% |  |  | Released to Systra | WF-021518 | 31/1/2026 | Approved with comments | 2026-05-17
| SOAC CABLE ROOM-S GR-019 | Under CJV Review |  |  |  | CJV will held a meeting with SMO | waiting SMO's comments on New Capital
| SOAC CABLE ROOM-S GR-119 | Under CJV Review |  |  |  | CJV will held a meeting with SMO
Giza | IT-S LG-083 | Approved from CJV | In Progress |  | 20% |  |  | released to Systra | WF-021181 | 15/3/2026 | Approved with Comments | 2026-05-04
| IT-S LG-084 | Approved from CJV | In Progress |  | 10% |  |  | released to Systra | WF-021181 | 15/3/2026 | Approved with Comments | 2026-05-04
| IT-S GR-074 | Approved from CJV | In Progress |  | 45% |  |  | released to Systra | WF-021181 | 15/3/2026 | Approved with Comments | 2026-05-04
| IT-S GR-107 | Approved from CJV | In Progress |  | 10% |  |  | released to Systra | WF-021181 | 15/3/2026 | Approved with Comments | 2026-05-04
| IT-S MZ-078 | Approved from CJV | In Progress |  | 25% |  |  | released to Systra | WF-021181 | 15/3/2026 | Approved with Comments | 2026-05-04
| IT-S MZ-103 | Approved from CJV | In Progress |  | 30% |  |  | released to Systra | WF-021181 | 15/3/2026 | Approved with Comments | 2026-05-04
| TEL-S MZ-049 | Approved from CJV | Not started |  | 0% |  |  | released to Systra | WF-021181 | 15/3/2026 | Approved with Comments | 2026-05-04
| IT-S FR-078 | Approved from CJV | In Progress |  | 25% |  |  | released to Systra | WF-021181 | 15/3/2026 | Approved with Comments | 2026-05-04
| BAT-TEL MZ-046 | Under HNWL update | Not started |  | 0%
October Gardens | BAT-TEL-S GR-A001 |  | In Progress |  | 15%
| TEL-S GR-A004 | Under HNWL update | In Progress |  | 45% |  | CJV discussed the comments with HNWL on 4-5-2026
| IT-S (GR-B001) | Under HNWL update | Not started |  | 0%
| IT-S (GR-B153) | Under HNWL update | Not started |  | 0%
| IT-S (MZ-A002) | Under HNWL update | In Progress |  | 40%
| IT-S (MZ-A124) | Under HNWL update | In Progress |  | 40%
| IT-S(MZ-B124) | Under HNWL update | Not started |  | 0%
| IT-S (MZ-B002) | Under HNWL update | Not started |  | 0%
| IT-S (FR-A005) | Under HNWL update | In Progress |  | 40%
| IT-S (FR-A134) | Under HNWL update | In Progress |  | 40%
| IT-S (FR-B005) | Under HNWL update | Not started |  | 0%
| IT-S(FR-B134) | Under HNWL update | Not started |  | 0%
| SOAC CABLE ROOM GR-A119 | Approved from CJV |  |  |  | CJV will held a meeting with SMO | waiting SMO's comments on New Capital | Under SMO Review | WF-024722 | 15/8/2026
| SOAC CABLE ROOM GR-A019 | Approved from CJV |  |  |  | CJV will held a meeting with SMO |  | Under SMO Review | WF-024722 | 15/8/2026
| SOAC CABLE ROOM (GR-B119) | Approved from CJV |  |  |  | CJV will held a meeting with SMO |  | Under SMO Review | WF-024722 | 15/8/2026
| SOAC CABLE ROOM (GR-B019) | Approved from CJV |  |  |  | CJV will held a meeting with SMO |  | Under SMO Review | WF-024722 | 15/8/2026
6th October | IT-S (GR-235) |  | Not started |  | 0%
| IT-S (GR-241) |  | Not started |  | 0%
| IT-S (MZ-106) |  | Not started |  | 0%
| IT-S (MZ-105) |  | Not started |  | 0%
| IT-S FR-096 |  | Not started |  | 0%
| TEL-S FR-060 |  | Not started |  | 0%
| BAT TEL-S FR-113 |  | Not started |  | 0%
| SOAC CABLE ROOM MZ-103 | Under CJV Review | Not started |  |  | CJV will held a meeting with SMO | waiting SMO's comments on New Capital
| SOAC CABLE ROOM MZ-104 | Under CJV Review | Not started |  |  | CJV will held a meeting with SMO
Sphinx | BAT-TEL-S GR-001
| TEL-S GR-002 | Approved from CJV | In Progress |  | 55% |  | CJV discussed the comments with HNWL on 4-5-2026 | released to Systra | WF-024119 | 20-7-2026 | Under Systra Review
| IT-S GR-164 | Approved from CJV | In Progress |  | 15% |  |  | released to Systra | WF-024119 | 20-7-2026 | Under Systra Review
| IT-S GR-160 | Approved from CJV | In Progress |  | 20% |  |  | released to Systra | WF-024119 | 20-7-2026 | Under Systra Review
| IT-S MZ-003 | Approved from CJV | In Progress |  | 20% |  |  | released to Systra | WF-024119 | 20-7-2026 | Under Systra Review
| IT-S MZ-128 | Approved from CJV | In Progress |  | 25% |  |  | released to Systra | WF-024119 | 20-7-2026 | Under Systra Review
| IT-S FR-003 | Approved from CJV | In Progress |  | 25% |  |  | released to Systra | WF-024119 | 20-7-2026 | Under Systra Review
| IT-S FR-124 | Approved from CJV | In Progress |  | 35% |  |  | released to Systra | WF-024119 | 20-7-2026 | Under Systra Review
| SOAC CABLE ROOM BS-016 | Under CJV Review |  |  |  | CJV will held a meeting with SMO | waiting SMO's comments on New Capital
| SOAC CABLE ROOM BS-107 | Under CJV Review |  |  |  | CJV will held a meeting with SMO
| SOAC CABLE ROOM GR-019 | Under CJV Review |  |  |  | CJV will held a meeting with SMO
| SOAC CABLE ROOM GR-117 | Under CJV Review |  |  |  | CJV will held a meeting with SMO
Sadat | IT-S GR-101 | Approved from CJV | In Progress |  | 10% |  |  | released to Systra | WF-021958 | 19/4/2026 | Under Systra Review
| IT-S GR-052 | Approved from CJV | In Progress |  | 20% |  |  | released to Systra | WF-021958 | 19/4/2026 | Under Systra Review
| IT-S MZ-058 | Approved from CJV | In Progress |  | 10% |  |  | released to Systra | WF-021958 | 19/4/2026 | Under Systra Review
| IT-S MZ-028 | Approved from CJV | In Progress |  | 10% |  |  | released to Systra | WF-021958 | 19/4/2026 | Under Systra Review
| TEL-S MZ-044 | Approved from CJV | Not started |  | 0% |  | on hold until receiving the updated DRW from Honeywell | released to Systra | WF-021958 | 19/4/2026 | Under Systra Review
| BAT-TEL-S MZ-042 | Under HNWL update | Not started |  | 0%
| IT-S FR-007 | Approved from CJV | In Progress |  | 10% |  |  | Under SMO Review | WF-021958 | 19/4/2026
Wadi Al Natroun | BAT - TEL-S GR-001 | Under HNWL update | Not started |  | 0% |  | CJV discussed the comments with HNWL on 4-5-2026
| TEL-S GR-002 | Under HNWL update | In Progress |  | 15%
| IT-S GR-164 | Under HNWL update | In Progress |  | 45%
| IT-S GR-160 | Under HNWL update | In Progress |  | 30%
| IT-S MZ-003 | Under HNWL update | In Progress |  | 35%
| IT-S MZ-128 | Under HNWL update | In Progress |  | 20%
| IT-S FR-124 | Under HNWL update | In Progress |  | 15%
| IT-S FR-003 | Under HNWL update | In Progress |  | 15%
| SOAC CABLE ROOM BS-016 | Under CJV Review |  |  |  | CJV will held a meeting with SMO | waiting SMO's comments on New Capital
| SOAC CABLE ROOM BS-107 | Under CJV Review |  |  |  | CJV will held a meeting with SMO
| SOAC CABLE ROOM GR-019 | Under CJV Review |  |  |  | CJV will held a meeting with SMO
| SOAC CABLE ROOM GR-117 | Under CJV Review |  |  |  | CJV will held a meeting with SMO
Noubarya | BAT-TEL-S GR-012 | Under HNWL update | In Progress |  | 15%
| TEL-S GR-001 | Approved from CJV | In Progress |  | 45% |  |  | Released to Systra | WF-020970 | 2026-08-03 | Approved with Comments | 30/4/2026
| IT-2-S MZ-014 | Approved from CJV | In Progress |  | 15% |  |  | Released to Systra | WF-020970 | 2026-08-03 | Approved with Comments | 30/4/2026
| IT-1-S MZ-122 | Approved from CJV | In Progress |  | 10% |  |  | Released to Systra | WF-020970 | 2026-08-03 | Approved with Comments | 30/4/2026
| IT-S FR-012 | Approved from CJV | In Progress |  | 10% |  |  | Released to Systra | WF-020970 | 2026-08-03 | Approved with Comments | 30/4/2026
| IT-S FR-110 | Approved from CJV | In Progress |  | 10% |  |  | Released to Systra | WF-020970 | 2026-08-03 | Approved with Comments | 30/4/2026
| SOAC CABLE ROOM GR-058 | Under CJV Review |  |  |  | CJV will held a meeting with SMO | waiting SMO's comments on New Capital
| SOAC CABLE ROOM GR-152 | Under CJV Review |  |  |  | CJV will held a meeting with SMO
Army stadium | BAT TEL-S GR-003 |  | Not started |  | 0%
| TEL-S GR-001 | Under HNWL update | Not started |  | 0% |  | CJV will arrange a meeting with HNWL on 19-7-2026 to discuss the comments.
| IT-S GR-202 | Under HNWL update | Not started |  | 0%
| IT-S GR-129 | Under HNWL update | Not started |  | 0%
| IT-S GR-207 | Under HNWL update | Not started |  | 0%
| IT-S MZ-003 | Under HNWL update | Not started |  | 0%
| IT-S MZ-070 | Under HNWL update | Not started |  | 0%
| IT-S FR 008 | Under HNWL update | Not started |  | 0%
| IT-S FR 034 | Under HNWL update | Not started |  | 0%
| SOAC CABLE ROOM GR-021 | Under CJV Review | Not started |  | 0%
| SOAC CABLE ROOM GR-110 | Under CJV Review | Not started |  | 0%
Borg Al Arab | BAT TEL-S GR-012 |  | Not started |  | 0%
| TEL-S GR-001 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021513 |  | Approved with comments | 2026-04-27
| IT-S GR-165 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021513 |  | Approved with comments | 2026-04-27
| IT-S GR-147 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021513 |  | Approved with comments | 2026-04-27
| IT-S MZ-014 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021513 |  | Approved with comments | 2026-04-27
| IT-S MZ-250 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021513 |  | Approved with comments | 2026-04-27
| IT-S FR-240 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021513 |  | Approved with comments | 2026-04-27
| IT-S FR-241 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021513 |  | Approved with comments | 2026-04-27
| SOAC CABLE ROOM GR-170 | Under CJV Review | Not started |  |  | CJV will held a meeting with SMO | waiting SMO's comments on New Capital
| SOAC CABLE ROOM GR-180 | Under CJV Review | Not started |  |  | CJV will held a meeting with SMO
| SOAC CABLE ROOM GR-152 | Under CJV Review | Not started |  |  | CJV will held a meeting with SMO
| SOAC CABLE ROOM GR-058 | Under CJV Review | Not started |  |  | CJV will held a meeting with SMO
El Hamam | BAT TEL-S GR-004 |  | Not started |  | 0%
| TEL-S GR-001 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021502 |  | Approved with comments | 2026-04-27
| IT-S GR-165 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021502 |  | Approved with comments | 2026-04-27
| IT-S MZ-002 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021502 |  | Approved with comments | 2026-04-27
| IT-S MZ-080 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021502 |  | Approved with comments | 2026-04-27
| IT-S FR-007 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021502 |  | Approved with comments | 2026-04-27
| IT-S FR-018 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021502 |  | Approved with comments | 2026-04-27
| SOAC CABLE ROOM GR-180 | Under CJV Review | Not started |  |  | CJV will held a meeting with SMO
| SOAC CABLE ROOM GR-170 | Under CJV Review | Not started |  |  | CJV will held a meeting with SMO
| SOAC CABLE ROOM GR-017 | Under CJV Review | Not started |  |  | CJV will held a meeting with SMO
| SOAC CABLE ROOM GR-086 | Under CJV Review | Not started |  |  | CJV will held a meeting with SMO
AlAmein | IT-S (LG-005) | Under HNWL update | In Progress |  | 10%
| IT-S (LG-098) | Under HNWL update | In Progress |  | 35%
| IT-S (GR-202) | Under HNWL update | In Progress |  | 0%
| IT-S (GR-004) | Under HNWL update | In Progress |  | 10%
| IT-S (GR-071) | Under HNWL update | In Progress |  | 15%
| IT-S (GR-236) | Under HNWL update | In Progress |  | 0%
| IT-S (MZ-202) | Under HNWL update | In Progress |  | 0%
| IT-S (MZ-213) | Under HNWL update | In Progress |  | 0%
| IT-S (MZ-002) | Under HNWL update | In Progress |  | 10%
| IT-S (MZ-068) | Under HNWL update | In Progress |  | 10%
| TEL-S (MZ-001) | Under HNWL update | In Progress |  | 45%
| BAT-TEL-S (MZ-016) |  | In Progress
| IT-S (FR-004) | Under CJV Review | In Progress |  | 10%
| IT-S (FR-058) | Under CJV Review | In Progress |  | 10%
| IT-S (FR-216) | Under CJV Review | In Progress |  | 0%
| IT-S (FR-213) | Under CJV Review | In Progress |  | 0%
| SOAC CABLE ROOM (GR-024) | Under CJV Review | In Progress |  |  | CJV will held a meeting with SMO
| SOAC CABLE ROOM (GR-065) | Under CJV Review | In Progress |  |  | CJV will held a meeting with SMO
| SOAC CABLE ROOM (MZ-017) | Under CJV Review | In Progress |  |  | CJV will held a meeting with SMO
| SOAC CABLE ROOM (MZ-062) | Under CJV Review | In Progress |  |  | CJV will held a meeting with SMO
| SOAC CABLE ROOM (FR-011) | Under CJV Review | In Progress |  |  | CJV will held a meeting with SMO
| SOAC CABLE ROOM (FR-050) | Under CJV Review | In Progress |  |  | CJV will held a meeting with SMO
| SOAC CABLE ROOM (GR-214) | Under CJV Review | In Progress |  |  | CJV will held a meeting with SMO
| SOAC CABLE ROOM (GR-249) | Under CJV Review | In Progress |  |  | CJV will held a meeting with SMO
Sidi Abdelrahman | IT-S LG-045 | Under HNWL update | Not started |  | 0% |  | CJV shared the comments with HNWL on 2-9-2026
| IT-S LG-143 | Under HNWL update | Not started |  | 0%
| IT-S GR-207 | Under HNWL update | Not started |  | 0%
| IT-S GR-202 | Under HNWL update | Not started |  | 0%
| TEL-S GR-001 | Under HNWL update | Not started |  | 0%
| IT-S MZ-002 | Under HNWL update | Not started |  | 0%
| IT-S MZ-140 | Under HNWL update | Not started |  | 0%
| BAT TEL- S MZ-001 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-022564 |  | Rejected | 2026-05-07
| IT-S FR-104 | Under HNWL update | Not started |  | 0%
| IT-S FR-151 | Under HNWL update | Not started |  | 0%
Dabaa | BAT-TEL-S GR-012 |  | Not started |  | 0%
| TEL-S GR-001 | Approved from CJV | Not started |  | 0% |  | received from HNWL on 16-7-2026 and CJV discussed the comments with HNWL on 20-7-2026. | Released to Systra | WF-024409 |  | Under Systra Review
| IT-S GR-147 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-024409 |  | Under Systra Review
| IT-S GR-247 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-024409 |  | Under Systra Review
| IT-S GR-243 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-024409 |  | Under Systra Review
| IT-S MZ-014 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-024409 |  | Under Systra Review
| IT-S MZ-250 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-024409 |  | Under Systra Review
| IT-S FR-240 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-024409 |  | Under Systra Review
| IT-S FR-241 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-024409 |  | Under Systra Review
| SOAC CABLE ROOM GR-058 | Under CJV Review | Not started |  |  | CJV will held a meeting with SMO | waiting SMO's comments on New Capital station. the shop drawing
| SOAC CABLE ROOM GR-152 | Under CJV Review | Not started |  |  | CJV will held a meeting with SMO
Ras El-Hekma | BAT-TEL-S (GR-012) | Under HNWL update | Not started |  | 0%
| TEL-S (GR-001) | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021183 | 2026-03-15 | Approved with comments | 2026-06-09
| IT-S (GR-202) | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021183 | 2026-03-15 | Approved with comments | 2026-06-09
| IT-S (GR-207) | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021183 | 2026-03-15 | Approved with comments | 2026-06-09
| IT-S (GR-147) | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021183 | 2026-03-15 | Approved with comments | 2026-06-09
| IT-S MZ-014 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021183 | 2026-03-15 | Approved with comments | 2026-06-09
| IT-S MZ-250 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021183 | 2026-03-15 | Approved with comments | 2026-06-09
| IT-S FR-240 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021183 | 2026-03-15 | Approved with comments | 2026-06-09
| IT-S FR-241 | Approved from CJV | Not started |  | 0% |  |  | Released to Systra | WF-021183 | 2026-03-15 | Approved with comments | 2026-06-09
| SOAC CABLE ROOM GR-058 | Under CJV Review | Not started |  |  | CJV will held a meeting with SMO | waiting SMO's comments on New Capital station. the shop drawing
| SOAC CABLE ROOM GR-152 | Under CJV Review | Not started |  |  | CJV will held a meeting with SMO
Marsa Matrouh | BAT TEL-S GR-157 |  | Not started |  | 0%
| TEL-S GR-153 | Approved from CJV | Not started |  | 0% |  |  | Under SMO Review
| IT-S GR-138 | Approved from CJV | Not started |  | 0% |  |  | Under SMO Review
| IT-S GR-075 | Approved from CJV | Not started |  | 0% |  |  | Under SMO Review
| IT-S MZ-008 | Approved from CJV | Not started |  | 0% |  |  | Under SMO Review
| IT-S MZ-030 | Approved from CJV | Not started |  | 0% |  |  | Under SMO Review
| IT-S FR-010 | Approved from CJV | Not started |  | 0% |  |  | Under SMO Review
| IT-S FR-005 | Approved from CJV | Not started |  | 0% |  |  | Under SMO Review
| SOAC CABLE ROOM GR-053 | Under CJV Review | Not started |  | 0% |  | waiting SMO's comments on New Capital station.
| SOAC CABLE ROOM GR-156 | Under CJV Review | Not started |  | 0%
Ain Al-sokhna | TEL-S FR-026 | Under HNWL update
| IT-S MZ-033 | Under HNWL update
| IT-S MZ-044 | Under HNWL update |  |  |  |  | CJV shared the comments with HNWL on 26-7-2026 |  | CJV shared the comments with HNWL on 26-7-2026
| IT-S GR-018 | Under HNWL update
| IT-S GR-034 | Under HNWL update
| IT-S GR-130 | Under HNWL update
| IT-S GR-184 | Under HNWL update
| IT-S GR-240 | Under HNWL update
| IT-S FR-020 | Under HNWL update
| IT-S GR 148 | Under HNWL update
| IT-S GR 259 | Under HNWL update
| IT-S GR-216 | Under HNWL update
| IT-S GR-093 | Under HNWL update
| IT-S GR-053 | Under HNWL update
BAT-TEL FR-027
[13 empty] | Total Number of Documents | 256
[13 empty] | Total Number of submitted from HNWLdoumcnts | 215
[13 empty] | Total Number of not submitted from HNWL documents | 41
[13 empty] | Under HNWL update | 68
[13 empty] | Under CJV Review | 44
[13 empty] | Under Safety Review | 0
[13 empty] | Under SMO Review | 20
[13 empty] | Released to Systra | 83
[13 empty] | Under Systra Review | 28
[13 empty] | Approved with Comments | 54
[13 empty] | Rejected | 1

## Method of Statement (MOS)
Cutoff 02-09-2026
Systems | Document Number | WF # | Status | Date
MCS | HSR-SOA-MET-TELMCS-GL-1400001[C] | WF-017693 | Code 2 Approved | 2025-12-01
MSN-ACTIVE | HSR-SOA-MET-TELMSN-GL-1400002[A] | WF-021727 | code 3 Rejected | 2026-06-22
MSN-PASSIVE | HSR-SOA-MET-TELMSN-GL-1400001[A] | 23166 | Under Systra Review
ACS | HSR-SOA-MET-TELACS-GL-1400001[B] | WF-020868 | Code 2 Approved | 2026-07-07
PAS | HSR-SOA-MET-TELPAS-GL-1400001[B] | WF-017777 | Code 2 Approved | 2025-12-01
OATS | Did not received any documents from HNWL
VRS | Did not received any documents from HNWL
PIS | HSR-SOA-MET-TELPIS-GL-1400001[A] | WF-018090 | code 3 Rejected | 22/12/2025
CCTV | HSR-SOA-MET-TELCCTV-GL-1400001[B] | WF-020262 | Code 2 Approved | 15/6/2026
WIFI | HSR-SOA-MET-TELWIFI-GL-1400001[B] | WF-017608 | Code 2 Approved | 14/12/2025
UPS | Did not received any documents from HNWL
Cybersecurity | Did not received any documents from HNWL
Cable Pulling And Fiber Splicing indoor | HSR-SOA-MET-TEL-GL-1400001[C] | WF-020724 | Code 2 Approved | 26/4/2026
IDS |  | Did not received any documents from HNWL

## Factory Test Acceptance (FAT)
Cutoff 06-09-2026
system code | submission title |  | REV | officially Aconex release to systra | received from systra | Document status
MCS | FAT procedure | HSR-SOA-TPR-TELMCS-GL-1300001 | A | 18/2/2025 | 2025-09-05 | Approved with comments
MSN (Active) | FAT procedure | HSR-SOA-TPR-TELMSN-GL-1300003 | B | 2025-12-08 | 19/8/2025 | Approved with comments
MSN (Passive) | FAT procedure | HSR-SOA-TPR-TELMSN-GL-1300001 | A | 21/8/2025 | 15/10/2025 | Approved with comments
ACS | FAT procedure | HSR-SOA-TPR-TELACS-GL-1300001 | A | 26/7/2026 | 18/8/2025 | Approved with comments
PAS | FAT procedure | HSR-SOA-TPR-TELPAS-GL-1300001 | B | 26/7/2026 | 19/8/2025 | Approved with comments
PIS | FAT procedure | HSR-SOA-TPR-TELPIS-GL-1300001 | B |  |  | Under Systra Review
OATS | FAT procedure | HSR-SOA-TPR-TELOATS-GL-1300001 | A | 15/10/2025 | 2025-03-11 | Approved with comments
VRS | FAT procedure | HSR-SOA-TPR-TELVRS-GL-1300001 | C | 22/10/2025 | 24/10/2025 | Approved with comments
WIFI | FAT procedure | HSR-SOA-TPR-TELWIFI-GL-1300001 | C | 26/7/2026 | 19/8/2025 | Approved with comments
FO | FAT procedure | HSR-SOA-TPR-TEL-GL-1300001 | B | 19/11/2025 | 2025-04-12 | Approved with comments
CCTV | FAT procedure | HSR-SOA-TPR-TELCCTV-GL-1300001 |  |  |  | Under HNWL update
Cybersecurity | FAT procedure | HSR-SOA-TPR-TELMSN-GL-1300005 |  |  |  | Not sumitted yet
IDS | FAT procedure | HSR-SOA-TPR-TELACS-GL-1300003 |  |  |  | Not sumitted yet
UPS | FAT procedure | HSR-SOA-TPR-TELUPS-GL-1300001 |  |  |  | Not sumitted yet
Power Cables | FAT procedure | HSR-SOA-TPR-TEL-GL-1300002 | A |  |  | Under Systra Review
FAT Procedures – Multi Service Network – Passive Components – Indoor Racks | FAT procedure | HSR-SOA-TPR-TELMSN-GL-1300004 | A |  |  | Submitted under CJV Review

## LLD
|  |  |  | Internal Review |  | SMO Review |  |  | Systra Review
System Code | Submission Tittle | Doc No. | Rev. | Status With Honeywell | Status Date | Document through WF Status | WF no. | Date | Status with Systra | Status Date
PAS | Public Address System – System Configuration File | HSR-SOA-DES-TELPAS-GL-1200008 | Draft | Approved from CJV | 2026-06-28 | The Draft sent to SMO by mail |  | 2026-06-28
MSN | IP Addressing Plan | HSR-SOA-DES-TELMSN-GL-1200021 | A | Approved from CJV | 2026-06-28 | Under SMO Review | WF-023593 | 2026-06-29